## TaskList
Task | Contractor | Start | Finish | Duration (wd) | Section
Wall & floor tiling JD tiling |  | 2025-08-11 | 2025-08-15 | 5
Plumbing final/shower screens |  | 2025-08-14 | 2025-08-15 | 2
Plumbing final/shower screens |  | 2025-08-18 | 2025-08-18 | 1
kitchen 1st fix,units tops & appliances WREN | MCL | 2025-08-19 | 2025-08-22 | 4
kitchen 1st fix,units tops & appliances WREN | MCL | 2025-08-26 | 2025-08-26 | 1
Wall & floor tiling JD tiling | PANACEA | 2025-08-11 | 2025-08-15 | 5
Plumbing final fix /shower screens GPL | MCL | 2025-08-18 | 2025-08-21 | 4
Plumbing final fix /shower screens GPL | Edencroft | 2025-08-28 | 2025-08-29 | 2
Plumbing final fix /shower screens GPL | Edencroft | 2025-09-01 | 2025-09-03 | 3
kitchen 1st fix,units tops & appliances | PANACEA | 2025-08-26 | 2025-08-29 | 4
kitchen 1st fix,units tops & appliances | PANACEA | 2025-09-01 | 2025-09-01 | 1
Wall & floor tiling JD tiling | PANACEA | 2025-08-14 | 2025-08-15 | 2
Wall & floor tiling JD tiling | PANACEA | 2025-08-18 | 2025-08-20 | 3
Plumbing final fix /shower screens GPL | MCL | 2025-09-04 | 2025-09-05 | 2
Plumbing final fix /shower screens GPL | MCL | 2025-09-08 | 2025-09-10 | 3
Floor and wall tiling JD tiling | PANACEA | 2025-08-21 | 2025-08-22 | 2
Floor and wall tiling JD tiling | PANACEA | 2025-08-26 | 2025-08-28 | 3
Kitchen 1st fix,units tops & appliances | MCL | 2025-09-01 | 2025-09-04 | 4
Floor and wall tiling JD tiling | MCL | 2025-08-26 | 2025-08-29 | 4
Floor and wall tiling JD tiling | MCL | 2025-09-01 | 2025-09-01 | 1
Ceilings - metal | GPL | 2025-08-13 | 2025-08-15 | 3
Sprinkler 2nd fix & test Armstrong preistly | ARMSTRONG | 2025-08-14 | 2025-08-15 | 2
Kitchen 1st fix,units tops & appliances | PANACEA | 2025-09-08 | 2025-09-12 | 5
Ceilings metal only | MCL | 2025-08-19 | 2025-08-22 | 4
Ceilings metal only | PANACEA | 2025-08-28 | 2025-08-29 | 2
Ceilings metal only | PANACEA | 2025-09-01 | 2025-09-01 | 1
Drying out |  | 2025-12-17 | 2025-12-31 | 11
1st fix partitions/pattreses one side |  | 2025-08-13 | 2025-08-15 | 3
1st fix partitions/pattreses one side |  | 2025-08-18 | 2025-08-19 | 2
1st fix partitions/pattreses one side |  | 2025-08-20 | 2025-08-22 | 3
1st fix partitions/pattreses one side |  | 2025-08-26 | 2025-08-27 | 2