## Block 1
Downtown Victoria North Block 1
|  | Date 11.08.25 | Subcontractor | February |  |  |  |  | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
|  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
|  | Activity |  | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| 1 | L1 apartment fit out cluster 1
| 2 | kitchen 1st fix,units tops & appliances
| 3 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | PANACEA
| 4 | Wall & floor tiling JD tiling | bar: August M 11 to August F 15
| 5 | service cupbaord -plywood flooring | TECL
Service cupboard board ceiling &finish | bar: August T 12 to August T 14
| 6 | service cupboard decoration
| 7 | service cupboard cylinder MVHR pipework installation & ducts | CARA
Amtico flooring /Bathrooms | bar: August W 13 to August F 15
| 8 | Plumbing final/shower screens |  | August T 14: GPL; August F 15: GPL; August M 18: GPL
| 8 | Electrical 2nd fix | PANACEA
| 9 | Builders clean | Edencroft
| 10 | Pre -dec -snagging | CPL
| 11 | Decoration | Armstrong
| 12 | Amtico flooring /Carpets
| 13 | De snag all trades | MCL
| 14 | Sparkle clean | PANACEA
| 15 | Mastic | TECL | bar: June W 11 to June F 13; June M 16 to June T 19
| 16 | Level 1 Apartment fit out cluster 2 | bar: August T 26
| 17 | kitchen 1st fix,units tops & appliances WREN | MCL | bar: August T 19 to August F 22; August T 26
| 18 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | Armstrong | bar: June T 17 to June F 20; August M 11 to August T 14
| 19 | Wall & floor tiling JD tiling | PANACEA | bar: June M 9 to June F 13; August M 11 to August F 15
Service cupboard board ceiling &finish | bar: June M 9 to June F 13
Board ceilings |  | service cupbaord -plywood flooring | bar: June M 23 to June F 27; June M 30 to July T 1; August W 13 to August T 14
| 20 | service cupboard decoration | PANACEA | bar: July W 2 to July F 4; July M 7 to July F 11; August F 15
| 21 | service cupboard cylinder MVHR pipework installation & ducts | Active flooring | bar: July T 10 to July F 11; July M 14 to July W 16
Amtico flooring /Bathrooms | bar: July T 10 to July F 11; July M 14 to July W 16; August M 18 to August W 20
RICKWORK | 22 | Plumbing final fix /shower screens GPL | MCL | July S 12: M; July S 13: M; July M 14: M; July T 15: M; July W 16: M; July T 17: M; August M 18: GPL; August T 19: GPL; August W 20: GPL; August T 21: GPL
| 23 | Electrical 2nd fix | Smiths | bar: July W 16 to July F 18
| 24 | Builders clean | MCL
| 25 | Pre -dec -snagging | Active flooring | bar: July M 14 to July W 16
| 26 | Decoration | Branniff | bar: July M 14 to July F 18
|  | Amtico flooring /Carpets | Wren | bar: July W 23 to July F 25; July M 28 to July T 29
De snag all trades
Sparkle clean | bar: July T 15 to July F 18
Mastic | bar: July W 16 to July F 18
Level 2 Apartment fit out -cluster 1
kitchen 1st fix,units tops & appliances WREN | bar: August T 19 to August F 22; August T 26
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: August M 11 to August F 15
Plumbing mid fix ,bath ,showers cisterns
Water on |  | Wall & floor tiling JD tiling | bar: August T 12 to August F 15; August M 18
Service cupboard board ceiling &finish | bar: August T 12 to August T 14
service cupbaord -plywood flooring | bar: August T 14 to August F 15
service cupboard decoration | bar: August F 15
| 28 | service cupboard cylinder MVHR pipework installation & ducts | PANACEA
Amtico flooring /Bathrooms | bar: August T 21 to August F 22; August T 26
| 29 | Plumbing final fix /shower screens GPL | Edencroft | August T 28: GPL; August F 29: GPL; September M 1: GPL; September T 2: GPL; September W 3: GPL
| 30 | Electrical 2nd fix | GPL
| 31 | Builders clean | Armstrong
| 32 | Pre -dec -snagging
| 33 | Decoration | MCL
| 34 | Amtico flooring /Carpets | PANACEA | bar: October M 27
| 35 | De snag all trades | TECL | June M 16: TECL; June T 17: TECL; June W 18: TECL; June T 19: TECL
| 36 | Sparkle clean | bar: October M 27
| 37 | Mastic | MCL | bar: October M 27
| 38 | Level 2 Apartment fit out cluster 2 | Armstrong | bar: June T 17 to June F 20; October M 27
Vanity 1st fix framing | bar: June T 17 to June F 20; October M 27
| 39 | kitchen 1st fix,units tops & appliances | PANACEA | bar: June T 10 to June F 13; August T 26 to August F 29; September M 1; October M 27
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: June M 23 to June F 27; August M 18 to August F 22; October M 27
Plumbing mid fix ,bath ,showers cisterns | bar: June M 23 to June F 27; October M 27
| 40 | Wall & floor tiling JD tiling | PANACEA | bar: June T 26 to June F 27; June M 30 to July F 4; July M 7 to July F 11; August T 14 to August F 15; August M 18 to August W 20; October M 27
Service cupboard board ceiling &finish | bar: June T 26 to June F 27; June M 30 to July F 4; July M 7 to July F 11; August M 18 to August T 21; October M 27
| 41 | service cupbaord -plywood flooring | Active flooring | bar: July T 10 to July F 11; July M 14 to July W 16; August T 14 to August F 15; October M 27
| 42 | service cupboard decoration | MCL | bar: July F 11 to July T 17; October M 27
| 43 | service cupboard cylinder MVHR pipework installation & ducts | Smiths | bar: July T 15 to July T 17; October M 27
Amtico flooring /Bathrooms | bar: July T 15 to July T 17; August W 27 to August F 29; October M 27
| 44 | Plumbing final fix /shower screens GPL | MCL | June M 16: M; September T 4: GPL; September F 5: GPL; September M 8: GPL; September T 9: GPL; September W 10: GPL
|  | Electrical 2nd fix | Active flooring | bar: July M 14 to July W 16; October M 27
|  | Builders clean | Branniff | bar: July M 14 to July F 18; October M 27
|  | Pre -dec -snagging | Wren | bar: July W 23 to July F 25; July M 28 to July T 29; October M 27
| 45 | Decoration | bar: October M 27
| 46 | Amtico flooring /Carpets | bar: July M 21 to July T 24; October M 27
| 47 | De snag all trades | bar: July W 23 to July F 25; October M 27
| 48 | Sparkle clean |  | August M 4: GPL; August T 5: GPL; August W 6: GPL; August T 7: GPL; August F 8: GPL
| 49 | Mastic |  | August M 4: GPL; August T 5: GPL; August W 6: GPL; August T 7: GPL; August F 8: GPL
| 50 | Level 3 Apartment fit out -cluster 1 | bar: October M 27
| 51 | Levveling screed /smoothing compound | bar: August M 11 to August F 15; October M 27
| 52 | Drying out | bar: October M 27
| 53 | Mist coat | bar: August T 14 to August F 15; October M 27
Vanity b |  | Vanity 1st fix framing | bar: August T 12 to August W 13; October M 27
Kitchen 1st fix,units tops & appliances | bar: September M 1 to September F 5; October M 27
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: August W 20 to August F 22; August T 26 to August W 27; October M 27
|  | Plumbing mid fix ,bath ,showers cisterns |  | August M 18: GPL; August T 19: GPL; August W 20: GPL
| 54 | Floor and wall tiling JD tiling | PANACEA | bar: August T 21 to August F 22; August T 26 to August T 28; October M 27
Service cupboard board ceiling &finish | bar: August W 13 to August F 15; October M 27
| 55 | service cupbaord -plywood flooring | Edencroft | bar: August M 18 to August T 19; October M 27
| 56 | service cupboard decoration | GPL | bar: June M 9 to June F 13; August M 18 to August T 19; October M 27
service cupboard cylinder MVHR pipework installation & ducts | bar: June M 9 to June F 13; October M 27
Amtico flooring /Bathrooms | bar: June M 9 to June F 13; September M 1 to September W 3; October M 27
| 57 | Plumbing final fix /shower screens GPL | ARMSTRONG | bar: October M 27
| 58 | Electrical 2nd fix
| 59 | Builders clean | MCL
| 60 | Pre -dec -snagging | PANACEA
Decoration | bar: June M 9 to June F 13
|  | Amtico flooring /Carpets |  | June M 23: TECL; June T 24: TECL; June W 25: TECL
| 62 | De snag all trades
| 63 | Sparkle clean | MCL | June T 17: MCL
| 65 | Mastic | PANACEA | bar: June M 16 to June F 20
Level 3 Apartment fit out -cluster 2 | bar: June T 26 to June F 27
Levveling screed /smoothing compound | bar: June M 30 to July F 4; July M 7 to July T 8; August M 11 to August F 15
| 66 | Drying out | PANACEA | bar: July W 9 to July F 11
| 67 | Mist coat | Active flooring | bar: July M 14 to July F 18; August T 14 to August F 15; August M 18
Vanity 1st fix framing | bar: July M 14 to July F 18; August W 13 to August F 15
| 68 | Kitchen 1st fix,units tops & appliances | MCL | bar: July W 16 to July T 22; September M 1 to September T 4
| 69 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | Smiths | bar: July F 18; July M 21 to July T 22; August T 28 to August F 29; September M 1 to September W 3
|  | Plumbing mid fix ,bath ,showers cisterns |  | August T 21: GPL; August F 22: GPL; August T 26: GPL
| 70 | Floor and wall tiling JD tiling | MCL | bar: July T 8 to July T 10; August T 26 to August F 29; September M 1
service cupbaord -plywood flooring | bar: July T 24 to July F 25; July M 28
service cupboard decoration | bar: July W 30 to August F 1; August M 4 to August T 5
| 72 | service cupboard cylinder MVHR pipework installation & ducts | Branniff | bar: July M 21 to July F 25
Amtico flooring /Bathrooms | bar: July M 21 to July F 25; September T 4 to September F 5; September M 8
Plumbing second fix sanitaryware & pressure testing
Electrical 2nd fix | bar: July W 23 to July F 25; July M 28 to July T 29
Builders clean | bar: August M 4 to August W 6
Pre -dec -snagging
Decoration
Amtico flooring /Carpets
De snag all trades
Sparkle clean
| 73 | Mastic
| 74 | Level 4 Apartment fit out -cluster 1 | PANACEA
| 75 | Ceiling void closure checklist sign off | Edencroft
| 76 | Ceilings - metal | GPL | bar: August W 13 to August F 15
| 77 | Sprinkler 2nd fix & test Armstrong preistly | ARMSTRONG | bar: June T 10 to June W 11; August T 14 to August F 15
Ceilings board | bar: June M 9 to June F 13; August T 14 to August F 15; August M 18 to August T 19
Plaster spray | bar: June M 9 to June F 13; August F 15; August M 18 to August F 22
Levveling screed /smoothing compound
| 78 | Drying out
| 79 | Mist coat | MCL | bar: August T 26 to August W 27
Vanity 1st fix framing | bar: August M 18 to August T 19
| 80 | Kitchen 1st fix,units tops & appliances | PANACEA | bar: June T 10 to June F 13; September M 8 to September F 12
|  | Plumbing mid fix ,bath ,showers cisterns |  | August W 27: GPL; August T 28: GPL; August F 29: GPL
| 81 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | TECL | bar: June M 16 to June F 20
|  | Floor and wall tiling |  | June M 23: TECL; June T 24: TECL; June W 25: TECL; June T 26: TECL
| 82 | service cupbaord -plywood flooring | bar: June F 27
| 83 | service cupboard decoration | MCL | bar: August W 27 to August T 28
| 85 | service cupboard cylinder MVHR pipework installation & ducts | PANACEA | bar: June M 23 to June F 27
Plumbing second fix sanitaryware & pressure testing | bar: June T 26 to June F 27
Electrical 2nd fix | bar: June M 30 to July F 4
| 86 | Builders clean | PANACEA | bar: July M 7 to July F 11
| 87 | Pre -dec -snagging | Active flooring | bar: July M 21 to July F 25
| 88 | Decoration | MCL | July M 21: MCL; July T 22: MCL; July W 23: MCL; July T 24: MCL; July F 25: MCL; July S 26: MCL; July S 27: MCL; July M 28: MCL
| 89 | Amtico flooring /Carpets | Smiths | bar: July F 25; July M 28 to July T 29
| 90 | De snag all trades | MCL | July M 28: MCL; July T 29: MCL
Sparkle clean
Mastic | bar: August W 6 to August F 8
Level 4 Apartment fit out -cluster 2 | bar: July W 23 to July F 25; July M 28 to July T 29
Ceiling void closure checklist sign off | bar: July M 21 to July T 22
Ceilings - metal | bar: August W 13 to August F 15
Sprinkler 2nd fix & test Armstrong preistly | bar: July W 30 to August F 1; August M 4 to August T 5; August T 14 to August F 15
Ceilings board | bar: August W 6 to August F 8; August M 18 to August W 20
Plaster spray | bar: August W 20 to August F 22
Levveling screed /smoothing compound | bar: August T 26 to August F 29
Drying out
Mist coat
Kitchen 1st fix,units tops & appliances | bar: September M 15 to September F 19
| 91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
| 92 | Floor and wall tiling | PANACEA
| 93 | service cupbaord -plywood flooring | Edencroft
| 94 | service cupboard decoration | GPL
| 95 | service cupboard cylinder MVHR pipework installation & ducts | ARMSTRONG | bar: June T 12 to June F 13; June W 18 to June F 20; June M 23 to June F 27
Plumbing second fix sanitaryware & pressure testing | bar: June M 16 to June F 20
Electrical 2nd fix | bar: June M 16 to June F 20
|  | Builders clean |  | June M 30: TECL; July T 1: TECL; July W 2: TECL; July T 3: TECL; July F 4: TECL
| 96 | Pre -dec -snagging
| 97 | Decoration | MCL
| 98 | Amtico flooring /Carpets | PANACEA | bar: June M 23 to June F 27
| 99 | De snag all trades | TECL | bar: June M 30 to July F 4
| 100 | Sparkle clean
| 101 | Mastic | MCL
| 103 | Level 5 Apartment fit out -cluster 1 | PANACEA | bar: July M 7 to July F 11
2nd fix Partitions - insulation and board | bar: July T 10 to July F 11; July M 14; August M 11 to August W 13
Ceilings board |  | Install Vents/ducts |  | July T 15: P; July W 16: P; July T 17: P; July F 18: P; August W 13: GPL; August T 14: GPL; August F 15: GPL; August M 18: GPL; August T 19: GPL
CONTROL POINT 3 CP3 | bar: July T 15 to July F 18
| 105 | Ceiling void closure checklist sign off | Active flooring | bar: July M 28 to August F 1
| 106 | Ceilings metal only | MCL | July T 31: MCL; August F 1: MCL; August S 2: MCL; August S 3: MCL; August M 4: MCL; August T 5: MCL; August T 19: P; August W 20: P; August T 21: P; August F 22: P
| 107 | Sprinkler 1st fix & test | bar: August M 4 to August W 6
| 108 | Ceilings - board (cut holes for lights) | MCL | August M 4: MCL; August T 5: MCL
| 109 | Plaster spray | Active flooring
| 110 | Levveling screed /smoothing compound | Branniff | bar: August M 4 to August F 8
|  | Drying out | Wren
Mist coat | bar: August W 6 to August F 8
| 111 | Kitchen 1st fix,units tops & appliances
| 112 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | PANACEA
| 113 | Floor and wall tiling | Edencroft
Control point 4 CP 4
| 114 | service cupbaord -plywood flooring | GPL | bar: June F 13
| 115 | service cupboard decoration | bar: June M 30 to July F 4
service cupboard cylinder MVHR pipework installation & ducts
Plumbing second fix sanitaryware & pressure testing | bar: June M 23 to June F 27
|  | Electrical 2nd fix |  | June M 30: TECL; July T 1: TECL; July W 2: TECL; July T 3: TECL; July F 4: TECL
| 116 | Builders clean
| 117 | Pre -dec -snagging | MCL
| 118 | Decoration | PANACEA | bar: June T 26 to June F 27; June M 30 to July T 1
| 119 | Amtico flooring /Carpets | TECL | bar: July M 7 to July F 11
| 120 | De snag all trades
| 121 | Sparkle clean | MCL
| 122 | Mastic | ARMSTRONG | bar: July M 14 to July F 18
Level 5Apartment fit out -cluster 2 | bar: July T 15 to July F 18
|  | CONTROL POINT 2 (CP2) |  | June T 24: MCL; June W 25: MCL; June T 26: MCL
| 128 | Wall void closure checklist sign off | MCL
2nd fix Partitions - insulation and board | bar: August T 14 to August F 15; August M 18 to August T 19
|  | Install Vents/ducts |  | August W 20: GPL; August T 21: GPL; August F 22: GPL; August T 26: GPL; August W 27: GPL
CONTROL POINT 3 (CP3)
| 129 | Ceiling void closure checklist sign off
| 130 | Ceilings metal only | PANACEA | bar: August T 28 to August F 29; September M 1
| 131 | Sprinkler 1st fix & test | CARA
| 132 | Ceilings - board (cut holes for lights)
| 133 | Plaster spray | GPL | bar: July W 2 to July F 4; July M 7 to July T 8
Levveling screed /smoothing compound | bar: July M 7 to July F 11
Drying out | bar: June M 30 to July F 4
| 134 | Mist coat | PANACEA
| 135 | Kitchen 1st fix,units tops & appliances | CARA
| 136 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
| 137 | Floor and wall tiling | RED | bar: July M 14 to July F 18
| 138 | Control point 4 CP 4 | PANACEA
| 139 | service cupbaord -plywood flooring | PANACEA
| 140 | service cupboard decoration | bar: July T 17 to July F 18; July M 21 to July T 24
| 141 | service cupboard cylinder MVHR pipework installation & ducts | step on safety | bar: July W 23 to July F 25
| 142 | Plumbing second fix sanitaryware & pressure testing | PANACEA | bar: July F 25; July M 28 to July T 31
| 143 | Electrical 2nd fix | bar: August F 1; August M 4 to August T 7
| 144 | Builders clean
| 145 | Pre -dec -snagging | RED
| 146 | Decoration | PANACEA
| 147 | Amtico flooring /Carpets | CARA
De snag all trades
| 148 | Sparkle clean
| 149 | Mastic | RED
| 150 | Level 6Apartment fit out -cluster 1 | PANACEA
1st fix electrical back boxes Edencroft
| 151 | 1st fix partitions/pattreses one side | CARA | bar: June M 9 to June T 10
| 152 | First fix wire -ceilings/walls
| 153 | first fix plumbing | RED
| 154 | SVP & RWP install | PANACEA | bar: July W 9 to July F 11; July M 14 to July T 15
Firestop to RWP & SVP | bar: July M 14 to July F 18
CONTROL POINT 2 (CP2) | bar: July M 7 to July F 11
|  | Wall void closure checklist sign off |  | July M 14: TECL; July T 15: TECL; July W 16: TECL; July T 17: TECL; July F 18: TECL
| 155 | 2nd fix Partitions - insulation and board | CARA
| 156 | Install Vents/ducts
| 157 | CONTROL POINT 3 (CP3) | RED | bar: July M 14 to July F 18; July M 21 to July W 23
| 158 | Ceiling void closure checklist sign off | PANACEA | bar: July M 21 to July F 25
| 159 | Ceilings metal only | CARA
| 160 | Sprinkler 1st fix & test
| 161 | Ceilings - board (cut holes for lights) | bar: July M 28 to August F 1
| 162 | Plaster spray | bar: July T 31 to August F 1; August M 4 to August T 5
| 163 | Levveling screed /smoothing compound | bar: August M 4 to August F 8
| 164 | Drying out | bar: December W 17 to December W 31
| 165 | Mist coat
| 166 | Kitchen 1st fix,units tops & appliances
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
Floor and wall tiling
Control point 4 CP 4
service cupbaord -plywood flooring
service cupboard decoration
service cupboard cylinder MVHR pipework installation & ducts
| 167 | Plumbing second fix sanitaryware & pressure testing
| 169 | Electrical 2nd fix
| 170 | Builders clean
| 171 | Pre -dec -snagging
| 172 | Decoration
| 173 | Amtico flooring /Carpets
| 174 | De snag all trades
| 175 | Sparkle clean
| 176 | Mastic | bar: June M 9 to June F 13; June M 16 to June W 18
177 | bar: June T 19 to June F 20; June M 23 to June W 25
| 178 | Level 6Apartment fit out -cluster 2 | bar: June T 26 to June F 27; June M 30 to July W 2
| 179 | 1st fix electrical back boxes Edencroft | bar: July W 16 to July F 18; July M 21 to July T 22
1st fix partitions/pattreses one side | bar: July M 21 to July F 25
| 180 | First fix wire -ceilings/walls | bar: July W 9 to July F 11; July M 14 to July T 15
| 181 | first fix plumbing |  | July M 14: TECL; July T 15: TECL; July W 16: TECL; July T 17: TECL; July F 18: TECL
| 182 | SVP & RWP install
| 183 | Firestop to RWP & SVP
| 184 | CONTROL POINT 2 (CP2) | bar: July M 21 to July F 25
| 185 | Wall void closure checklist sign off | bar: July M 28 to August F 1
| 186 | 2nd fix Partitions - insulation and board
| 187 | Install Vents/ducts
| 188 | CONTROL POINT 3 (CP3) | bar: August M 4 to August T 7
| 189 | Ceiling void closure checklist sign off | bar: August W 6 to August F 8
| 190 | Ceilings metal only
| 191 | Sprinkler 1st fix & test
| 192 | Ceilings - board (cut holes for lights)
| 193 | Plaster spray
| 194 | Levveling screed /smoothing compound
| 195 | Drying out
| 196 | Mist coat
| 197 | Kitchen 1st fix,units tops & appliances
| 198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
Floor and wall tiling
| 199 | Control point 4 CP 4
| 200 | service cupbaord -plywood flooring
| 201 | service cupboard decoration | bar: June T 26 to June F 27; June M 30 to July W 2
| 202 | service cupboard cylinder MVHR pipework installation & ducts | bar: July T 3 to July F 4; July M 7 to July W 9
| 203 | Plumbing second fix sanitaryware & pressure testing | bar: July W 23 to July F 25; July M 28 to July T 29
Electrical 2nd fix | bar: July M 28 to August F 1
| 204 | Builders clean | bar: July W 16 to July F 18
| 205 | Pre -dec -snagging |  | July T 17: TECL; July F 18: TECL; July M 21: TECL; July T 22: TECL; July W 23: TECL
| 206 | Decoration
| 207 | Amtico flooring /Carpets
| 208 | De snag all trades | bar: August F 1; August M 4 to August W 6
| 209 | Sparkle clean | bar: August T 5 to August F 8
| 210 | Mastic
211
| 212 | Level 7Apartment fit out -cluster 1
| 213 | 1st fix electrical back boxes Edencroft | bar: August M 11 to August T 12
| 214 | 1st fix partitions/pattreses one side | bar: August W 13 to August F 15; August M 18 to August T 19
| 215 | First fix wire -ceilings/walls
| 216 | first fix plumbing
| 217 | SVP & RWP install
| 218 | Firestop to RWP & SVP
| 219 | CONTROL POINT 2 (CP2)
| 220 | Wall void closure checklist sign off
| 221 | 2nd fix Partitions - insulation and board
| 222 | Install Vents/ducts
CONTROL POINT 3 (CP3)
| 223 | Ceiling void closure checklist sign off
| 224 | Ceilings metal only
| 225 | Sprinkler 1st fix & test
| 226 | Ceilings - board (cut holes for lights)
| 227 | Plaster spray
| 228 | Levveling screed /smoothing compound
| 229 | Drying out
| 230 | Mist coat
| 231 | Kitchen 1st fix,units tops & appliances
| 232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: June M 30 to July F 4
| 233 | Floor and wall tiling | bar: July M 7 to July F 11
| 234 | Control point 4 CP 4 | bar: July M 14 to July F 18
| 235 | service cupbaord -plywood flooring | bar: July W 30 to August F 1; August M 4 to August T 5
| 236 | service cupboard decoration | bar: July M 28 to August F 1
| 237 | service cupboard cylinder MVHR pipework installation & ducts |  | August M 4: TECL; August T 5: TECL; August W 6: TECL
| 238 | Plumbing second fix sanitaryware & pressure testing
| 239 | Electrical 2nd fix
| 240 | Builders clean
| 241 | Pre -dec -snagging
| 242 | Decoration
| 243 | Amtico flooring /Carpets
| 244 | De snag all trades
| 245 | Sparkle clean
| 246 | Mastic
247
| 248 | Level 7Apartment fit out -cluster 2
| 249 | 1st fix electrical back boxes Edencroft | bar: August T 12 to August W 13
| 250 | 1st fix partitions/pattreses one side | bar: August W 20 to August F 22; August T 26 to August W 27
| 251 | First fix wire -ceilings/walls
| 252 | first fix plumbing
| 253 | SVP & RWP install
| 254 | Firestop to RWP & SVP
CONTROL POINT 2 (CP2)
| 255 | Wall void closure checklist sign off
| 256 | 2nd fix Partitions - insulation and board
| 257 | Install Vents/ducts | bar: July M 14 to July F 18
| 258 | CONTROL POINT 3 (CP3) | bar: July M 21 to July F 25
| 259 | Ceiling void closure checklist sign off | bar: August W 6 to August F 8
| 260 | Ceilings metal only | bar: July M 28 to August F 1
| 261 | Sprinkler 1st fix & test |  | August M 4: TECL; August T 5: TECL; August W 6: TECL
| 262 | Ceilings - board (cut holes for lights)
| 263 | Plaster spray
| 264 | Levveling screed /smoothing compound
| 265 | Drying out
| 266 | Mist coat
| 267 | Kitchen 1st fix,units tops & appliances
| 268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
| 269 | Floor and wall tiling
| 270 | Control point 4 CP 4
| 271 | service cupbaord -plywood flooring
| 272 | service cupboard decoration
| 273 | service cupboard cylinder MVHR pipework installation & ducts
| 274 | Plumbing second fix sanitaryware & pressure testing
| 275 | Electrical 2nd fix
| 276 | Builders clean
| 277 | Pre -dec -snagging
| 278 | Decoration
| 279 | Amtico flooring /Carpets
| 280 | De snag all trades
| 281 | Sparkle clean
| 282 | Mastic
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305

## Sheet2
Block 3 | W/C 10/03/25
South elevation
Craven | install access
Cara | install insulation
| commence blockwork | 1 lift
Heyrod | install drainage & backfill
Cara | 2nd lift blockwork
Craven | commence scaffold
North Elevation
Waterman Awaiting reply from RFI
Cara? | Take down existing brickwork to form level/sound structure and rebuild to 47.300 level (approx 200mm )