## Block 1
Downtown Victoria North Block 1
|  | Date 11.08.25 | Subcontractor | February |  |  |  |  | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
|  |  |  | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 |  | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | [93 empty] | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | time axis 2025-12-01 to 2026-02-28
|  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | [89 empty] | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | time axis 2025-12-01 to 2026-02-28
|  | Activity |  | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | [89 empty] | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | time axis 2025-12-01 to 2026-02-28
| 1 | L1 apartment fit out cluster 1
| 2 | kitchen 1st fix,units tops & appliances
| 3 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | PANACEA
| 4 | Wall & floor tiling JD tiling | bar: 2026-02-11 to 2026-02-15
| 5 | service cupbaord -plywood flooring | TECL
Service cupboard board ceiling &finish | bar: 2026-02-12 to 2026-02-14
| 6 | service cupboard decoration | bar: 2026-02-15
| 7 | service cupboard cylinder MVHR pipework installation & ducts | CARA | [97 empty] | 2026-02-18: GPL; 2026-02-19: GPL; 2026-02-20: GPL; 2026-02-21: GPL; 2026-02-22: GPL
Amtico flooring /Bathrooms | bar: 2026-02-13 to 2026-02-15
| 8 | Plumbing final/shower screens | [98 empty] | 2026-02-14: GPL; 2026-02-15: GPL; 2026-02-18: GPL; 2026-02-19: GPL; 2026-02-20: GPL
| 8 | Electrical 2nd fix -live testing including consumer unit | PANACEA | bar: 2026-02-20 to 2026-02-22; 2026-02-26 to 2026-02-27
Power on
Water on
| 9 | Builders clean | Edencroft | [97 empty] | 2026-02-21: MCL; 2026-02-22: MCL
| 10 | Pre -dec -snagging | CPL | bar: 2026-02-21 to 2026-02-22
| 11 | Decoration | Armstrong | [186 empty] | S |  |  | S | S | bar: 2026-02-26 to 2026-02-28
|  | Final fix/sprinkler heads /panel heaters | [192 empty] | mcl
| 12 | Amtico flooring /Carpets | [197 empty] | A | A | A | A | A
| 13 | De snag all trades -test & commision | MCL
| 14 | Sparkle clean | PANACEA
Mastic
Handover to client
| 16 | Level 1 Apartment fit out cluster 2
| 17 | kitchen 1st fix,units tops & appliances WREN | MCL | bar: 2026-02-19 to 2026-02-22; 2026-02-26
| 18 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | Armstrong | bar: 2025-12-17 to 2025-12-20; 2026-02-11 to 2026-02-14
| 19 | Wall & floor tiling JD tiling | PANACEA | bar: 2025-12-09 to 2025-12-13; 2026-02-11 to 2026-02-15
Service cupboard board ceiling &finish | bar: 2025-12-09 to 2025-12-13
Board ceilings |  | service cupbaord -plywood flooring | bar: 2025-12-23 to 2025-12-27; 2025-12-30 to 2026-01-01; 2026-02-13 to 2026-02-14
| 20 | service cupboard decoration | PANACEA | bar: 2026-01-02 to 2026-01-04; 2026-01-07 to 2026-01-11; 2026-02-15
| 21 | service cupboard cylinder MVHR pipework installation & ducts | Active flooring | bar: 2026-01-10 to 2026-01-11; 2026-01-14 to 2026-01-16
Amtico flooring /Bathrooms | bar: 2026-01-10 to 2026-01-11; 2026-01-14 to 2026-01-16; 2026-02-18 to 2026-02-22
RICKWORK | 22 | Plumbing final fix /shower screens GPL | MCL | [97 empty] | 2026-01-12: M; 2026-01-13: M; 2026-01-14: M; 2026-01-15: M; 2026-01-16: M; 2026-01-17: M; 2026-02-20: GPL; 2026-02-21: GPL; 2026-02-22: GPL; 2026-02-26: GPL; 2026-02-27: GPL
| 23 | Electrical 2nd fix live testing | Smiths | bar: 2026-01-16 to 2026-01-18; 2026-02-28
Power on | bar: 2026-01-16 to 2026-01-18
Water on | bar: 2026-01-16 to 2026-01-18
| 24 | Builders clean | MCL
| 25 | Pre -dec -snagging | Active flooring | bar: 2026-01-14 to 2026-01-16
| 26 | Decoration | Branniff | [190 empty] | S | S | S | S |  |  | S | S | bar: 2026-01-14 to 2026-01-18
|  | Amtico flooring /Carpets | Wren | [198 empty] | mcl | bar: 2026-01-23 to 2026-01-25; 2026-01-28 to 2026-01-29
De snag all trades -test & commision
Sparkle clean | bar: 2026-01-15 to 2026-01-18
Mastic | bar: 2026-01-16 to 2026-01-18
Handover to client | bar: 2026-01-16 to 2026-01-18
Level 2 Apartment fit out -cluster 1
kitchen 1st fix,units tops & appliances WREN | bar: 2026-02-19 to 2026-02-22; 2026-02-26
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: 2026-02-11 to 2026-02-15
Plumbing mid fix ,bath ,showers cisterns
Water on |  | Wall & floor tiling JD tiling | bar: 2026-02-12 to 2026-02-15; 2026-02-18
Service cupboard board ceiling &finish | bar: 2026-02-12 to 2026-02-14
service cupbaord -plywood flooring | bar: 2026-02-14 to 2026-02-15
service cupboard decoration | bar: 2026-02-15
| 28 | service cupboard cylinder MVHR pipework installation & ducts | PANACEA
Amtico flooring /Bathrooms | bar: 2026-02-21 to 2026-02-22; 2026-02-26 to 2026-02-28
| 29 | Plumbing final fix /shower screens GPL | Edencroft | [97 empty] | 2026-02-28: GPL | GPL |  |  | GPL | GPL | GPL
| 30 | Electrical 2nd fix &live testing | GPL
Power on
Water on
| 31 | Builders clean | Armstrong
| 32 | Pre -dec -snagging
| 33 | Decoration | MCL | [198 empty] | S | S | S |  |  | S | S
| 34 | Amtico flooring /Carpets | PANACEA | [205 empty] | mcl | mcl
| 35 | De snag all trades -test & commision | TECL | [97 empty] | 2025-12-16: TECL; 2025-12-17: TECL; 2025-12-18: TECL; 2025-12-19: TECL
| 36 | Sparkle clean
| 37 | Mastic | MCL
Handover to client
| 38 | Level 2 Apartment fit out cluster 2 | Armstrong | bar: 2025-12-17 to 2025-12-20
Vanity 1st fix framing | bar: 2025-12-17 to 2025-12-20
| 39 | kitchen 1st fix,units tops & appliances | PANACEA | [186 empty] | W |  |  | W | bar: 2025-12-10 to 2025-12-13; 2026-02-26 to 2026-02-28
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: 2025-12-23 to 2025-12-27; 2026-02-18 to 2026-02-22
Plumbing mid fix ,bath ,showers cisterns | bar: 2025-12-23 to 2025-12-27
| 40 | Wall & floor tiling JD tiling | PANACEA | bar: 2025-12-26 to 2025-12-27; 2025-12-30 to 2026-01-04; 2026-01-07 to 2026-01-11; 2026-02-14 to 2026-02-15; 2026-02-18 to 2026-02-20
Service cupboard board ceiling &finish | bar: 2025-12-26 to 2025-12-27; 2025-12-30 to 2026-01-04; 2026-01-07 to 2026-01-11; 2026-02-18 to 2026-02-21
| 41 | service cupbaord -plywood flooring | Active flooring | bar: 2026-01-10 to 2026-01-11; 2026-01-14 to 2026-01-16; 2026-02-14 to 2026-02-15
| 42 | service cupboard decoration | MCL | bar: 2026-01-11 to 2026-01-17
| 43 | service cupboard cylinder MVHR pipework installation & ducts | Smiths | bar: 2026-01-15 to 2026-01-17
|  | Amtico flooring /Bathrooms | [187 empty] | A |  |  | A | A | bar: 2026-01-15 to 2026-01-17; 2026-02-27 to 2026-02-28
| 44 | Plumbing final fix /shower screens GPL | MCL | [191 empty] | GPL | GPL | GPL |  |  | GPL | GPL | bar: 2025-12-16
|  | Electrical 2nd fix & live testing | Active flooring | bar: 2026-01-14 to 2026-01-16
|  | Builders clean | Branniff | bar: 2026-01-14 to 2026-01-18
|  | Pre -dec -snagging | Wren | bar: 2026-01-23 to 2026-01-25; 2026-01-28 to 2026-01-29
| 45 | Decoration | [206 empty] | S | S | S |  |  | S | S
| 46 | Amtico flooring /Carpets | [213 empty] | mcl | mcl | mcl | bar: 2026-01-21 to 2026-01-24
| 47 | De snag all trades -test & commision | bar: 2026-01-23 to 2026-01-25
| 48 | Sparkle clean | [98 empty] | 2026-02-04: GPL; 2026-02-05: GPL; 2026-02-06: GPL; 2026-02-07: GPL; 2026-02-08: GPL
| 49 | Mastic | [98 empty] | 2026-02-04: GPL; 2026-02-05: GPL; 2026-02-06: GPL; 2026-02-07: GPL; 2026-02-08: GPL
Handover to client | bar: 2026-02-04 to 2026-02-08
| 50 | Level 3 Apartment fit out -cluster 1
| 51 | Levveling screed /smoothing compound | bar: 2026-02-11 to 2026-02-15
| 52 | Drying out
| 53 | Mist coat | bar: 2026-02-14 to 2026-02-15
Vanity b |  | Vanity 1st fix framing | bar: 2026-02-12 to 2026-02-13
|  | Kitchen 1st fix,units tops & appliances | [190 empty] | W | W | W | W | W
Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: 2026-02-20 to 2026-02-22; 2026-02-26 to 2026-02-27
|  | Plumbing mid fix ,bath ,showers cisterns | [98 empty] | 2026-02-13: GPL; 2026-02-14: GPL; 2026-02-15: GPL; 2026-02-18: GPL; 2026-02-19: GPL
| 54 | Floor and wall tiling JD tiling | PANACEA | bar: 2026-02-20 to 2026-02-22; 2026-02-26 to 2026-02-27
Service cupboard board ceiling &finish | bar: 2026-02-13 to 2026-02-15
| 55 | service cupbaord -plywood flooring | Edencroft | bar: 2026-02-18 to 2026-02-19
| 56 | service cupboard decoration | GPL | bar: 2025-12-09 to 2025-12-13; 2026-02-18 to 2026-02-19
service cupboard cylinder MVHR pipework installation & ducts | bar: 2025-12-09 to 2025-12-13
|  | Amtico flooring /Bathrooms | [190 empty] | A | A | A | A | A | bar: 2025-12-09 to 2025-12-13
| 57 | Plumbing final fix /shower screens GPL | ARMSTRONG | [198 empty] | GPL | GPL | GPL |  |  | GPL | GPL
| 58 | Electrical 2nd fix & live testing
| 59 | Builders clean | MCL
| 60 | Pre -dec -snagging | PANACEA
|  | Decoration | [213 empty] | S | S | S |  |  | S | S | bar: 2025-12-09 to 2025-12-13
|  | Amtico flooring /Carpets | [98 empty] | 2025-12-23: TECL; 2025-12-24: TECL; 2025-12-25: TECL | [33 empty] | mcl | mcl | mcl
| 62 | De snag all trades - test & commision
| 63 | Sparkle clean | MCL | [97 empty] | 2025-12-17: MCL
| 65 | Mastic | PANACEA | bar: 2025-12-16 to 2025-12-20
Handover to client | bar: 2025-12-16 to 2025-12-20
Level 3 Apartment fit out -cluster 2 | bar: 2025-12-26 to 2025-12-27
Levveling screed /smoothing compound | bar: 2025-12-30 to 2026-01-04; 2026-01-07 to 2026-01-08; 2026-02-11 to 2026-02-15
| 66 | Drying out | PANACEA | bar: 2026-01-09 to 2026-01-11
| 67 | Mist coat | Active flooring | bar: 2026-01-14 to 2026-01-18; 2026-02-14 to 2026-02-15; 2026-02-18
Vanity 1st fix framing | bar: 2026-01-14 to 2026-01-18; 2026-02-13 to 2026-02-15
| 68 | Kitchen 1st fix,units tops & appliances | MCL | [189 empty] | W | W | W | W | bar: 2026-01-16 to 2026-01-22
| 69 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | Smiths | [186 empty] | B |  |  | B | B | B | bar: 2026-01-18; 2026-01-21 to 2026-01-22; 2026-02-28
|  | Plumbing mid fix ,bath ,showers cisterns | [98 empty] | 2026-02-20: GPL; 2026-02-21: GPL; 2026-02-22: GPL; 2026-02-26: GPL; 2026-02-27: GPL
| 70 | Floor and wall tiling JD tiling | MCL | [186 empty] | JD |  |  | JD | JD | JD | bar: 2026-01-08 to 2026-01-10; 2026-02-28
|  | service cupbaord -plywood flooring | [191 empty] | B | B | bar: 2026-01-24 to 2026-01-25; 2026-01-28
|  | service cupboard decoration | [193 empty] | S | S | bar: 2026-01-30 to 2026-02-01; 2026-02-04 to 2026-02-05
| 72 | service cupboard cylinder MVHR pipework installation & ducts | Branniff | bar: 2026-01-21 to 2026-01-25
|  | Amtico flooring /Bathrooms | [197 empty] | A | A | A | A | A | bar: 2026-01-21 to 2026-01-25
|  | Plumbing second fix sanitaryware & pressure testing | [206 empty] | GPL | GPL | GPL |  |  | GPL | GPL
Electrical 2nd fix & live testing | bar: 2026-01-23 to 2026-01-25; 2026-01-28 to 2026-01-29
Builders clean | bar: 2026-02-04 to 2026-02-06
Pre -dec -snagging
|  | Decoration | [220 empty] | S | S | S |  |  | S | S
|  | Amtico flooring /Carpets | [227 empty] | mcl | mcl | mcl
De snag all trades test & commision
Sparkle clean
| 73 | Mastic
Handover to client
| 74 | Level 4 Apartment fit out -cluster 1 | PANACEA
| 75 | Ceiling void closure checklist sign off | Edencroft
| 76 | Ceilings - metal | GPL | bar: 2026-02-13 to 2026-02-15
| 77 | Sprinkler 2nd fix & test Armstrong preistly | ARMSTRONG | bar: 2025-12-10 to 2025-12-11; 2026-02-18 to 2026-02-19
Ceilings board | bar: 2025-12-09 to 2025-12-13; 2026-02-18 to 2026-02-20
Plaster spray | bar: 2025-12-09 to 2025-12-13; 2026-02-19 to 2026-02-22
|  | Levveling screed /smoothing compound | [187 empty] | A |  |  | A | bar: 2026-02-26 to 2026-02-28
| 78 | Drying out
| 79 | Mist coat | MCL | [186 empty] | S | bar: 2026-02-28
Vanity 1st fix framing | bar: 2026-02-18 to 2026-02-19
| 80 | Kitchen 1st fix,units tops & appliances | PANACEA | [196 empty] | W | W | W | W | W | bar: 2025-12-10 to 2025-12-13
|  | Plumbing mid fix ,bath ,showers cisterns | [98 empty] | 2026-02-27: GPL; 2026-02-28: GPL | GPL |  |  | GPL | GPL
| 81 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | TECL | [192 empty] | B | B |  |  | B | B | B | bar: 2025-12-16 to 2025-12-20
|  | Floor and wall tiling JD tiling | [98 empty] | 2025-12-23: TECL; 2025-12-24: TECL; 2025-12-25: TECL; 2025-12-26: TECL |  |  |  |  | JD | JD | JD | JD |  |  | JD
| 82 | service cupbaord -plywood flooring | [198 empty] | B | B | bar: 2025-12-27
| 83 | service cupboard decoration | MCL | [199 empty] | S | S
| 85 | service cupboard cylinder MVHR pipework installation & ducts | PANACEA | bar: 2025-12-23 to 2025-12-27
|  | Amtico flooring /Bathrooms | [204 empty] | A | A | A | A | A | bar: 2025-12-23 to 2025-12-27
|  | Plumbing second fix sanitaryware & pressure testing | [212 empty] | GPL | GPL | GPL | GPL |  |  | GPL | bar: 2025-12-26 to 2025-12-27
Electrical 2nd fix & live testing | bar: 2025-12-30 to 2026-01-04
| 86 | Builders clean | PANACEA | bar: 2026-01-07 to 2026-01-11
| 87 | Pre -dec -snagging | Active flooring | bar: 2026-01-21 to 2026-01-25
| 88 | Decoration | MCL | [97 empty] | 2026-01-21: MCL; 2026-01-22: MCL; 2026-01-23: MCL; 2026-01-24: MCL; 2026-01-25: MCL; 2026-01-26: MCL; 2026-01-27: MCL; 2026-01-28: MCL | [40 empty] | S | S | S |  |  | S | S
| 89 | Amtico flooring /Carpets | Smiths | [233 empty] | mcl | mcl | mcl | bar: 2026-01-25; 2026-01-28 to 2026-01-29
| 90 | De snag all trades test & commision | MCL | [97 empty] | 2026-01-28: MCL; 2026-01-29: MCL
Sparkle clean
Mastic
Handover to client
Level 4 Apartment fit out -cluster 2 | bar: 2026-01-23 to 2026-01-25; 2026-01-28 to 2026-01-29
Ceiling void closure checklist sign off | bar: 2026-01-21 to 2026-01-22
Ceilings - metal | bar: 2026-02-13 to 2026-02-15
Sprinkler 2nd fix & test Armstrong preistly | bar: 2026-01-30 to 2026-02-01; 2026-02-04 to 2026-02-05; 2026-02-14 to 2026-02-15
Ceilings board | bar: 2026-02-18 to 2026-02-20
Plaster spray | bar: 2026-02-20 to 2026-02-22; 2026-02-26
|  | Levveling screed /smoothing compound | [187 empty] | A |  |  | A | A | A | bar: 2026-02-28
Drying out
|  | Mist coat | [190 empty] | S | S
Vanity 1st fix framing | bar: 2026-02-20 to 2026-02-21
|  | Kitchen 1st fix,units tops & appliances | [204 empty] | W | W | W | W | W
|  | Plumbing mid fix ,bath ,showers cisterns | [190 empty] | GPL | GPL | GPL | GPL | GPL
| 91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | [200 empty] | B | B |  |  | B | B | B
| 92 | Floor and wall tiling JD tiling | PANACEA | [196 empty] | JD | JD | JD | JD | JD
| 93 | service cupbaord -plywood flooring | Edencroft | [204 empty] | B | B
| 94 | service cupboard decoration | GPL | [206 empty] | S | S
| 95 | service cupboard cylinder MVHR pipework installation & ducts | ARMSTRONG | bar: 2025-12-12 to 2025-12-13; 2025-12-18 to 2025-12-20; 2025-12-23 to 2025-12-27
|  | Amtico flooring /Bathrooms | [211 empty] | A | A | A | A | A | bar: 2025-12-12 to 2025-12-13; 2025-12-18 to 2025-12-20; 2025-12-23 to 2025-12-27
|  | Plumbing second fix sanitaryware & pressure testing | [218 empty] | GPL | GPL | GPL | GPL | GPL | bar: 2025-12-16 to 2025-12-20
Electrical 2nd fix & live testing | bar: 2025-12-16 to 2025-12-20
|  | Builders clean | [98 empty] | 2025-12-30: TECL; 2026-01-01: TECL; 2026-01-02: TECL; 2026-01-03: TECL; 2026-01-04: TECL
| 96 | Pre -dec -snagging
| 97 | Decoration | MCL | [233 empty] | S | S | S |  |  | S | S
| 98 | Amtico flooring /Carpets | PANACEA | [240 empty] | mcl | mcl | mcl | bar: 2025-12-23 to 2025-12-27
| 99 | De snag all trades test & commision | TECL | bar: 2025-12-30 to 2026-01-04
| 100 | Sparkle clean
| 101 | Mastic | MCL
Handover to client
| 103 | Level 5 Apartment fit out -cluster 1 | PANACEA | bar: 2026-01-07 to 2026-01-11
2nd fix Partitions - insulation and board | bar: 2026-01-10 to 2026-01-11; 2026-01-14; 2026-02-11 to 2026-02-13
Ceilings board |  | Install Vents/ducts | [98 empty] | 2026-01-15: P; 2026-01-16: P; 2026-01-17: P; 2026-01-18: P; 2026-02-13: GPL; 2026-02-14: GPL; 2026-02-15: GPL; 2026-02-18: GPL; 2026-02-19: GPL
CONTROL POINT 3 CP3 | bar: 2026-01-15 to 2026-01-18
| 105 | Ceiling void closure checklist sign off | Active flooring | bar: 2026-01-28 to 2026-02-01
| 106 | Ceilings metal only | MCL | [97 empty] | 2026-01-31: MCL; 2026-02-01: MCL; 2026-02-02: MCL; 2026-02-03: MCL; 2026-02-04: MCL; 2026-02-05: MCL; 2026-02-20: P; 2026-02-21: P; 2026-02-22: P
| 107 | Sprinkler 2nd fix & test | bar: 2026-02-04 to 2026-02-06; 2026-02-26 to 2026-02-27
| 108 | Ceilings - board (cut holes for lights) | MCL | [97 empty] | 2026-02-04: MCL; 2026-02-05: MCL; 2026-02-28: P | P |  |  | P
| 109 | Plaster spray | Active flooring | [189 empty] | P | P | P | P
| 110 | Levveling screed /smoothing compound | Branniff | [193 empty] | A |  |  | A | A | A | A | bar: 2026-02-04 to 2026-02-08
|  | Drying out | Wren
|  | Mist coat | [193 empty] | S | S | bar: 2026-02-06 to 2026-02-08
|  | Vanity 1st fix framing | [191 empty] | B | B | bar: 2026-02-06 to 2026-02-08
| 111 | Kitchen 1st fix,units tops & appliances | [211 empty] | W | W | W | W | W
|  | Plumbing mid fix ,bath ,showers cisterns | [199 empty] | GPL | GPL | GPL |  |  | GPL | GPL
| 112 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | PANACEA | [206 empty] | B | B |  |  | B | B | B
| 113 | Floor and wall tiling JD tiling | Edencroft | [203 empty] | JD | JD | JD | JD | JD
Control point 4 CP 4
| 114 | service cupbaord -plywood flooring | GPL | [211 empty] | B | B | bar: 2025-12-13
| 115 | service cupboard decoration | [214 empty] | S | S | bar: 2025-12-30 to 2026-01-04
service cupboard cylinder MVHR pipework installation & ducts
|  | Amtico flooring /Bathrooms | [218 empty] | A | A | A | A | A
|  | Plumbing second fix sanitaryware & pressure testing | [225 empty] | GPL | GPL | GPL | GPL | GPL | bar: 2025-12-23 to 2025-12-27
|  | Electrical 2nd fix & live testing | [98 empty] | 2025-12-30: TECL; 2026-01-01: TECL; 2026-01-02: TECL; 2026-01-03: TECL; 2026-01-04: TECL
| 116 | Builders clean
| 117 | Pre -dec -snagging | MCL
| 118 | Decoration | PANACEA | [240 empty] | S | S | S |  |  | S | S | bar: 2025-12-26 to 2025-12-27; 2025-12-30 to 2026-01-01
| 119 | Amtico flooring /Carpets | TECL | [247 empty] | mcl | mcl | mcl | bar: 2026-01-07 to 2026-01-11
| 120 | De snag all trades test & commision
| 121 | Sparkle clean | MCL
| 122 | Mastic | ARMSTRONG | bar: 2026-01-14 to 2026-01-18
Handover to client | bar: 2026-01-14 to 2026-01-18
Level 5Apartment fit out -cluster 2 | bar: 2026-01-15 to 2026-01-18
|  | CONTROL POINT 2 (CP2) | [98 empty] | 2025-12-24: MCL; 2025-12-25: MCL; 2025-12-26: MCL
| 128 | Wall void closure checklist sign off | MCL
2nd fix Partitions - insulation and board | bar: 2026-02-14 to 2026-02-15; 2026-02-18 to 2026-02-19
|  | Install Vents/ducts | [98 empty] | 2026-02-20: GPL; 2026-02-21: GPL; 2026-02-22: GPL; 2026-02-26: GPL; 2026-02-27: GPL
CONTROL POINT 3 (CP3)
| 129 | Ceiling void closure checklist sign off
| 130 | Ceilings metal only | PANACEA | bar: 2026-02-26 to 2026-02-28
| 131 | Sprinkler 1st fix & test | CARA | bar: 2026-02-28
| 132 | Ceilings - board (cut holes for lights) | [187 empty] | P |  |  | P | P | P
| 133 | Plaster spray | GPL | [191 empty] | P | P | P |  |  | P | bar: 2026-01-02 to 2026-01-04; 2026-01-07 to 2026-01-08
|  | Levveling screed /smoothing compound | [198 empty] | A | A | A | A |  |  | A | bar: 2026-01-07 to 2026-01-11
Drying out | bar: 2025-12-30 to 2026-01-04
| 134 | Mist coat | PANACEA | [196 empty] | S | S
|  | Vanity 1st fix framing | [193 empty] | B | B | [6 empty] | B |  |  | B
| 135 | Kitchen 1st fix,units tops & appliances | CARA | [217 empty] | W | W | W | W | W
|  | Plumbing mid fix ,bath ,showers cisterns | [206 empty] | GPL | GPL | GPL |  |  | GPL | GPL
| 136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . | [214 empty] | B | B |  |  | B | B | B | B
| 137 | Floor and wall tiling JD tiling | RED | [210 empty] | JD | JD | JD | JD | JD | bar: 2026-01-14 to 2026-01-18
| 138 | Control point 4 CP 4 | PANACEA
| 139 | service cupbaord -plywood flooring | PANACEA
| 140 | service cupboard decoration | bar: 2026-01-17 to 2026-01-18; 2026-01-21 to 2026-01-24
| 141 | service cupboard cylinder MVHR pipework installation & ducts | step on safety | bar: 2026-01-23 to 2026-01-25
|  | Amtico flooring /Bathrooms | [225 empty] | A | A | A | A | A | bar: 2026-01-23 to 2026-01-25
| 142 | Plumbing second fix sanitaryware & pressure testing | PANACEA | [231 empty] | GPL | GPL | GPL | GPL | GPL | bar: 2026-01-25; 2026-01-28 to 2026-01-31
| 143 | Electrical 2nd fix & live testing | bar: 2026-02-01; 2026-02-04 to 2026-02-07
| 144 | Builders clean
| 145 | Pre -dec -snagging | RED
| 146 | Decoration | PANACEA | [247 empty] | S | S | S |  |  | S | S
| 147 | Amtico flooring /Carpets | CARA | [254 empty] | mcl | mcl | mcl
De snag all trades test & commision
| 148 | Sparkle clean
| 149 | Mastic | RED
Handover to client
| 150 | Level 6Apartment fit out -cluster 1 | PANACEA
| 152 | First fix wire -ceilings/walls | bar: 2026-02-11 to 2026-02-15
|  | first fix plumbing | [98 empty] | 2026-02-18: GPL; 2026-02-19: GPL; 2026-02-20: GPL; 2026-02-21: GPL; 2026-02-22: GPL
Wall void closure checklist sign off
2nd board walls |  | 2nd board walls | [187 empty] | P |  |  | P | bar: 2026-02-26 to 2026-02-28
Firestop to RWP/SVP wall penetrations | bar: 2026-01-14 to 2026-01-18
| 156 | Install Vents/ducts | [98 empty] | 2026-02-28: GPL | GPL |  |  | GPL | GPL | GPL
1st fix sprinkler
| 157 | CONTROL POINT 3 (CP3) | RED | bar: 2026-01-14 to 2026-01-18; 2026-01-21 to 2026-01-23
| 158 | Ceiling void closure checklist sign off | PANACEA | bar: 2026-01-21 to 2026-01-25
| 159 | Ceilings metal only | CARA | [191 empty] | P | P | P
| 160 | Sprinkler 2nd fix fix & test
| 161 | Ceilings - board (cut holes for lights) | [198 empty] | P | P | P | bar: 2026-01-28 to 2026-02-01
| 162 | Plaster spray | [200 empty] | P | P |  |  | P | P | bar: 2026-01-31 to 2026-02-01; 2026-02-04 to 2026-02-05
| 163 | Levveling screed /smoothing compound | [206 empty] | A | A | A |  |  | A | A | bar: 2026-02-04 to 2026-02-08
| 164 | Drying out | [305 empty] | PR | PR | PR | PR | PR | PR | PR
| 165 | Mist coat | [213 empty] | S | S | S
|  | Vanity 1st fix framing | [207 empty] | B | B
| 166 | Kitchen 1st fix,units tops & appliances | [225 empty] | W | W | W | W | W
|  | Joinery 1st fix -doors, frames ,skirting | [222 empty] | B |  |  | B | B | B | B
|  | Floor and wall tiling | [218 empty] | JD | JD | JD | JD | JD
Control point 4 CP 4
|  | service cupbaord -plywood flooring | [222 empty] | B |  |  | B
service cupboard decoration
service cupboard cylinder MVHR pipework installation & ducts
Amtico flooring /Bathrooms
| 167 | Plumbing second fix sanitaryware & pressure testing
| 169 | Electrical 2nd fix & live testing
| 170 | Builders clean
| 171 | Pre -dec -snagging
| 172 | Decoration | [255 empty] | S | S | S |  |  | S | S
| 173 | Amtico flooring /Carpets | [262 empty] | mcl | mcl | mcl
| 174 | De snag all trades
| 175 | Sparkle clean
| 176 | Mastic | bar: 2025-12-09 to 2025-12-13; 2025-12-16 to 2025-12-18
| 177 | Handover to client | bar: 2025-12-19 to 2025-12-20; 2025-12-23 to 2025-12-25
| 178 | Level 6Apartment fit out -cluster 2 | bar: 2025-12-26 to 2025-12-27; 2025-12-30 to 2026-01-02
| 179 | 1st fix electrical back boxes Edencroft | bar: 2026-01-16 to 2026-01-18; 2026-01-21 to 2026-01-22
1st fix partitions/pattreses one side | bar: 2026-01-21 to 2026-01-25
| 180 | First fix wire -ceilings/walls | bar: 2026-01-09 to 2026-01-11; 2026-01-14 to 2026-01-15
| 181 | first fix plumbing | [98 empty] | 2026-01-14: TECL; 2026-01-15: TECL; 2026-01-16: TECL; 2026-01-17: TECL; 2026-01-18: TECL
| 182 | SVP & RWP install
| 183 | Firestop to RWP & SVP
| 184 | CONTROL POINT 2 (CP2) | bar: 2026-01-21 to 2026-01-25
| 185 | Wall void closure checklist sign off | bar: 2026-01-28 to 2026-02-01
| 186 | 2nd fix Partitions - insulation and board
| 187 | Install Vents/ducts
| 188 | CONTROL POINT 3 (CP3) | bar: 2026-02-04 to 2026-02-07
| 189 | Ceiling void closure checklist sign off | bar: 2026-02-06 to 2026-02-08
| 190 | Ceilings metal only
| 191 | Sprinkler 1st fix & test
| 192 | Ceilings - board (cut holes for lights)
| 193 | Plaster spray
| 194 | Levveling screed /smoothing compound
| 195 | Drying out
| 196 | Mist coat
| 197 | Kitchen 1st fix,units tops & appliances
| 198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
Floor and wall tiling
| 199 | Control point 4 CP 4
| 200 | service cupbaord -plywood flooring
| 201 | service cupboard decoration | bar: 2025-12-26 to 2025-12-27; 2025-12-30 to 2026-01-02
| 202 | service cupboard cylinder MVHR pipework installation & ducts | bar: 2026-01-03 to 2026-01-04; 2026-01-07 to 2026-01-09
Amtico flooring /Bathrooms | bar: 2026-01-03 to 2026-01-04; 2026-01-07 to 2026-01-09
| 203 | Plumbing second fix sanitaryware & pressure testing | bar: 2026-01-23 to 2026-01-25; 2026-01-28 to 2026-01-29
Electrical 2nd fix & live testing | bar: 2026-01-28 to 2026-02-01
| 204 | Builders clean | bar: 2026-01-16 to 2026-01-18
| 205 | Pre -dec -snagging | [98 empty] | 2026-01-17: TECL; 2026-01-18: TECL; 2026-01-21: TECL; 2026-01-22: TECL; 2026-01-23: TECL
| 206 | Decoration | [262 empty] | S | S | S |  |  | S | S
| 207 | Amtico flooring /Carpets | [269 empty] | mcl | mcl | mcl
| 208 | De snag all trades | bar: 2026-02-01; 2026-02-04 to 2026-02-06
| 209 | Sparkle clean | bar: 2026-02-05 to 2026-02-08
| 210 | Mastic
| 211 | Handover to client
| 212 | Level 7Apartment fit out -cluster 1
| 213 | 1st fix electrical back boxes Edencroft | bar: 2026-02-11 to 2026-02-12
| 214 | 1st fix partitions/pattreses one side | bar: 2026-02-13 to 2026-02-15; 2026-02-18 to 2026-02-19
| 215 | First fix wire -ceilings/walls | bar: 2026-02-20 to 2026-02-22; 2026-02-26
| 216 | first fix plumbing
| 217 | SVP & RWP install
| 218 | Firestop to RWP & SVP
| 219 | CONTROL POINT 2 (CP2)
| 220 | Wall void closure checklist sign off
| 221 | 2nd fix Partitions - insulation and board
| 222 | Install Vents/ducts
CONTROL POINT 3 (CP3)
| 223 | Ceiling void closure checklist sign off
| 224 | Ceilings metal only
| 225 | Sprinkler 1st fix & test
| 226 | Ceilings - board (cut holes for lights)
| 227 | Plaster spray
| 228 | Levveling screed /smoothing compound
| 229 | Drying out
| 230 | Mist coat
| 231 | Kitchen 1st fix,units tops & appliances
| 232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . | bar: 2025-12-30 to 2026-01-04
| 233 | Floor and wall tiling JD tiling | bar: 2026-01-07 to 2026-01-11
| 234 | Control point 4 CP 4 | bar: 2026-01-14 to 2026-01-18
| 235 | service cupbaord -plywood flooring | bar: 2026-01-30 to 2026-02-01; 2026-02-04 to 2026-02-05
| 236 | service cupboard decoration | bar: 2026-01-28 to 2026-02-01
| 237 | service cupboard cylinder MVHR pipework installation & ducts | [98 empty] | 2026-02-04: TECL; 2026-02-05: TECL; 2026-02-06: TECL
Amtico flooring /Bathrooms | bar: 2026-02-04 to 2026-02-06
| 238 | Plumbing second fix sanitaryware & pressure testing
| 239 | Electrical 2nd fix & live testing
| 240 | Builders clean
| 241 | Pre -dec -snagging
| 242 | Decoration
| 243 | Amtico flooring /Carpets
| 244 | De snag all trades
| 245 | Sparkle clean
| 246 | Mastic
| 247 | Handover to client
| 248 | Level 7Apartment fit out -cluster 2
| 249 | 1st fix electrical back boxes Edencroft | bar: 2026-02-12 to 2026-02-13
| 250 | 1st fix partitions/pattreses one side | bar: 2026-02-20 to 2026-02-22; 2026-02-26 to 2026-02-27
| 251 | First fix wire -ceilings/walls
| 252 | first fix plumbing
| 253 | SVP & RWP install
| 254 | Firestop to RWP & SVP
CONTROL POINT 2 (CP2)
| 255 | Wall void closure checklist sign off
| 256 | 2nd fix Partitions - insulation and board
| 257 | Install Vents/ducts | bar: 2026-01-14 to 2026-01-18
| 258 | CONTROL POINT 3 (CP3) | bar: 2026-01-21 to 2026-01-25
| 259 | Ceiling void closure checklist sign off | bar: 2026-02-06 to 2026-02-08
| 260 | Ceilings metal only | bar: 2026-01-28 to 2026-02-01
| 261 | Sprinkler 1st fix & test | [98 empty] | 2026-02-04: TECL; 2026-02-05: TECL; 2026-02-06: TECL
| 262 | Ceilings - board (cut holes for lights)
| 263 | Plaster spray
| 264 | Levveling screed /smoothing compound
| 265 | Drying out
| 266 | Mist coat
| 267 | Kitchen 1st fix,units tops & appliances
| 268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths .
| 269 | Floor and wall tiling JD tiling
| 270 | Control point 4 CP 4
| 271 | service cupbaord -plywood flooring
| 272 | service cupboard decoration
| 273 | service cupboard cylinder MVHR pipework installation & ducts
Amtico flooring /Bathrooms
| 274 | Plumbing second fix sanitaryware & pressure testing
| 275 | Electrical 2nd fix & live testing
| 276 | Builders clean
| 277 | Pre -dec -snagging
| 278 | Decoration
| 279 | Amtico flooring /Carpets
| 280 | De snag all trades
| 281 | Sparkle clean
| 282 | Mastic
| 283 | Handover to client
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305

## Sheet2
Block 3 | W/C 10/03/25
South elevation
Craven | install access
Cara | install insulation
| commence blockwork | 1 lift
Heyrod | install drainage & backfill
Cara | 2nd lift blockwork
Craven | commence scaffold
North Elevation
Waterman Awaiting reply from RFI
Cara? | Take down existing brickwork to form level/sound structure and rebuild to 47.300 level (approx 200mm )