## Tasks
Section | Activity | Contractor | Start | Finish | Duration
| Activity |  | 2025-08-24 | 2026-06-30 | 222
1 | L1 apartment fit out cluster 1 |  | 2025-12-07 | 2025-12-08 | 1
1 | L1 apartment fit out cluster 1 |  | 2025-12-14 | 2025-12-15 | 1
1 | L1 apartment fit out cluster 1 |  | 2025-12-21 | 2025-12-22 | 1
1 | L1 apartment fit out cluster 1 |  | 2025-12-28 | 2025-12-29 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-01-05 | 2026-01-06 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-01-12 | 2026-01-13 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-01-19 | 2026-01-20 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-01-26 | 2026-01-27 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-02-02 | 2026-02-03 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-02-09 | 2026-02-10 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-02-16 | 2026-02-17 | 2
1 | L1 apartment fit out cluster 1 |  | 2026-02-23 | 2026-02-25 | 3
1 | L1 apartment fit out cluster 1 |  | 2026-03-06 | 2026-03-07 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-03-13 | 2026-03-14 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-03-20 | 2026-03-21 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-03-27 | 2026-03-28 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-04-04 | 2026-04-05 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-04-11 | 2026-04-12 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-04-18 | 2026-04-19 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-04-25 | 2026-04-26 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-05-01 | 2026-05-02 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-05-08 | 2026-05-09 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-05-15 | 2026-05-16 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-05-22 | 2026-05-23 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-05-29 | 2026-05-30 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-06-06 | 2026-06-07 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-06-13 | 2026-06-14 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-06-20 | 2026-06-21 | 1
1 | L1 apartment fit out cluster 1 |  | 2026-06-25 | 2026-06-28 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-08 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2025-12-14 | 2025-12-15 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2025-12-21 | 2025-12-22 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2025-12-28 | 2025-12-29 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-06 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-01-12 | 2026-01-13 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-20 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-01-26 | 2026-01-27 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-02-02 | 2026-02-03 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-02-09 | 2026-02-10 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-02-16 | 2026-02-17 | 2
2 | kitchen 1st fix,units tops & appliances |  | 2026-02-23 | 2026-02-25 | 3
2 | kitchen 1st fix,units tops & appliances |  | 2026-03-06 | 2026-03-07 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-03-13 | 2026-03-14 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-03-20 | 2026-03-21 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-03-27 | 2026-03-28 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-05 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-05-15 | 2026-05-16 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-05-22 | 2026-05-23 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-06-20 | 2026-06-21 | 1
2 | kitchen 1st fix,units tops & appliances |  | 2026-06-25 | 2026-06-28 | 2
3 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
3 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
3 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
3 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
3 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
3 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
3 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
3 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
3 | PANACEA |  | 2026-02-02 | 2026-02-03 | 2
3 | PANACEA |  | 2026-02-09 | 2026-02-10 | 2
3 | PANACEA |  | 2026-02-16 | 2026-02-17 | 2
3 | PANACEA |  | 2026-02-23 | 2026-02-25 | 3
3 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
3 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
3 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
3 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
3 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
3 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
3 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
3 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
3 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
3 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
3 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
3 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
3 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
3 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
3 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
3 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
3 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
4 | Wall & floor tiling JD tiling |  | 2025-12-07 | 2025-12-08 | 1
4 | Wall & floor tiling JD tiling |  | 2025-12-14 | 2025-12-15 | 1
4 | Wall & floor tiling JD tiling |  | 2025-12-21 | 2025-12-22 | 1
4 | Wall & floor tiling JD tiling |  | 2025-12-28 | 2025-12-29 | 1
4 | Wall & floor tiling JD tiling |  | 2026-01-05 | 2026-01-06 | 2
4 | Wall & floor tiling JD tiling |  | 2026-01-12 | 2026-01-13 | 2
4 | Wall & floor tiling JD tiling |  | 2026-01-19 | 2026-01-20 | 2
4 | Wall & floor tiling JD tiling |  | 2026-01-26 | 2026-01-27 | 2
4 | Wall & floor tiling JD tiling |  | 2026-02-02 | 2026-02-03 | 2
4 | Wall & floor tiling JD tiling |  | 2026-02-09 | 2026-02-17 | 7
4 | Wall & floor tiling JD tiling |  | 2026-02-23 | 2026-02-25 | 3
4 | Wall & floor tiling JD tiling |  | 2026-03-06 | 2026-03-07 | 1
4 | Wall & floor tiling JD tiling |  | 2026-03-13 | 2026-03-14 | 1
4 | Wall & floor tiling JD tiling |  | 2026-03-20 | 2026-03-21 | 1
4 | Wall & floor tiling JD tiling |  | 2026-03-27 | 2026-03-28 | 1
4 | Wall & floor tiling JD tiling |  | 2026-04-04 | 2026-04-05 | 1
4 | Wall & floor tiling JD tiling |  | 2026-04-11 | 2026-04-12 | 1
4 | Wall & floor tiling JD tiling |  | 2026-04-18 | 2026-04-19 | 1
4 | Wall & floor tiling JD tiling |  | 2026-04-25 | 2026-04-26 | 1
4 | Wall & floor tiling JD tiling |  | 2026-05-01 | 2026-05-02 | 1
4 | Wall & floor tiling JD tiling |  | 2026-05-08 | 2026-05-09 | 1
4 | Wall & floor tiling JD tiling |  | 2026-05-15 | 2026-05-16 | 1
4 | Wall & floor tiling JD tiling |  | 2026-05-22 | 2026-05-23 | 1
4 | Wall & floor tiling JD tiling |  | 2026-05-29 | 2026-05-30 | 1
4 | Wall & floor tiling JD tiling |  | 2026-06-06 | 2026-06-07 | 1
4 | Wall & floor tiling JD tiling |  | 2026-06-13 | 2026-06-14 | 1
4 | Wall & floor tiling JD tiling |  | 2026-06-20 | 2026-06-21 | 1
4 | Wall & floor tiling JD tiling |  | 2026-06-25 | 2026-06-28 | 2
5 | TECL |  | 2025-12-07 | 2025-12-08 | 1
5 | TECL |  | 2025-12-14 | 2025-12-15 | 1
5 | TECL |  | 2025-12-21 | 2025-12-22 | 1
5 | TECL |  | 2025-12-28 | 2025-12-29 | 1
5 | TECL |  | 2026-01-05 | 2026-01-06 | 2
5 | TECL |  | 2026-01-12 | 2026-01-13 | 2
5 | TECL |  | 2026-01-19 | 2026-01-20 | 2
5 | TECL |  | 2026-01-26 | 2026-01-27 | 2
5 | TECL |  | 2026-02-02 | 2026-02-03 | 2
5 | TECL |  | 2026-02-09 | 2026-02-10 | 2
5 | TECL |  | 2026-02-16 | 2026-02-17 | 2
5 | TECL |  | 2026-02-23 | 2026-02-25 | 3
5 | TECL |  | 2026-03-06 | 2026-03-07 | 1
5 | TECL |  | 2026-03-13 | 2026-03-14 | 1
5 | TECL |  | 2026-03-20 | 2026-03-21 | 1
5 | TECL |  | 2026-03-27 | 2026-03-28 | 1
5 | TECL |  | 2026-04-04 | 2026-04-05 | 1
5 | TECL |  | 2026-04-11 | 2026-04-12 | 1
5 | TECL |  | 2026-04-18 | 2026-04-19 | 1
5 | TECL |  | 2026-04-25 | 2026-04-26 | 1
5 | TECL |  | 2026-05-01 | 2026-05-02 | 1
5 | TECL |  | 2026-05-08 | 2026-05-09 | 1
5 | TECL |  | 2026-05-15 | 2026-05-16 | 1
5 | TECL |  | 2026-05-22 | 2026-05-23 | 1
5 | TECL |  | 2026-05-29 | 2026-05-30 | 1
5 | TECL |  | 2026-06-06 | 2026-06-07 | 1
5 | TECL |  | 2026-06-13 | 2026-06-14 | 1
5 | TECL |  | 2026-06-20 | 2026-06-21 | 1
5 | TECL |  | 2026-06-25 | 2026-06-28 | 2
| Service cupboard board ceiling &finish |  | 2025-12-07 | 2025-12-08 | 1
| Service cupboard board ceiling &finish |  | 2025-12-14 | 2025-12-15 | 1
| Service cupboard board ceiling &finish |  | 2025-12-21 | 2025-12-22 | 1
| Service cupboard board ceiling &finish |  | 2025-12-28 | 2025-12-29 | 1
| Service cupboard board ceiling &finish |  | 2026-01-05 | 2026-01-06 | 2
| Service cupboard board ceiling &finish |  | 2026-01-12 | 2026-01-13 | 2
| Service cupboard board ceiling &finish |  | 2026-01-19 | 2026-01-20 | 2
| Service cupboard board ceiling &finish |  | 2026-01-26 | 2026-01-27 | 2
| Service cupboard board ceiling &finish |  | 2026-02-02 | 2026-02-03 | 2
| Service cupboard board ceiling &finish |  | 2026-02-09 | 2026-02-10 | 2
| Service cupboard board ceiling &finish |  | 2026-02-12 | 2026-02-14 | 2
| Service cupboard board ceiling &finish |  | 2026-02-16 | 2026-02-17 | 2
| Service cupboard board ceiling &finish |  | 2026-02-23 | 2026-02-25 | 3
| Service cupboard board ceiling &finish |  | 2026-03-06 | 2026-03-07 | 1
| Service cupboard board ceiling &finish |  | 2026-03-13 | 2026-03-14 | 1
| Service cupboard board ceiling &finish |  | 2026-03-20 | 2026-03-21 | 1
| Service cupboard board ceiling &finish |  | 2026-03-27 | 2026-03-28 | 1
| Service cupboard board ceiling &finish |  | 2026-04-04 | 2026-04-05 | 1
| Service cupboard board ceiling &finish |  | 2026-04-11 | 2026-04-12 | 1
| Service cupboard board ceiling &finish |  | 2026-04-18 | 2026-04-19 | 1
| Service cupboard board ceiling &finish |  | 2026-04-25 | 2026-04-26 | 1
| Service cupboard board ceiling &finish |  | 2026-05-01 | 2026-05-02 | 1
| Service cupboard board ceiling &finish |  | 2026-05-08 | 2026-05-09 | 1
| Service cupboard board ceiling &finish |  | 2026-05-15 | 2026-05-16 | 1
| Service cupboard board ceiling &finish |  | 2026-05-22 | 2026-05-23 | 1
| Service cupboard board ceiling &finish |  | 2026-05-29 | 2026-05-30 | 1
| Service cupboard board ceiling &finish |  | 2026-06-06 | 2026-06-07 | 1
| Service cupboard board ceiling &finish |  | 2026-06-13 | 2026-06-14 | 1
| Service cupboard board ceiling &finish |  | 2026-06-20 | 2026-06-21 | 1
| Service cupboard board ceiling &finish |  | 2026-06-25 | 2026-06-28 | 2
6 | service cupboard decoration |  | 2025-12-07 | 2025-12-08 | 1
6 | service cupboard decoration |  | 2025-12-14 | 2025-12-15 | 1
6 | service cupboard decoration |  | 2025-12-21 | 2025-12-22 | 1
6 | service cupboard decoration |  | 2025-12-28 | 2025-12-29 | 1
6 | service cupboard decoration |  | 2026-01-05 | 2026-01-06 | 2
6 | service cupboard decoration |  | 2026-01-12 | 2026-01-13 | 2
6 | service cupboard decoration |  | 2026-01-19 | 2026-01-20 | 2
6 | service cupboard decoration |  | 2026-01-26 | 2026-01-27 | 2
6 | service cupboard decoration |  | 2026-02-02 | 2026-02-03 | 2
6 | service cupboard decoration |  | 2026-02-09 | 2026-02-10 | 2
6 | service cupboard decoration |  | 2026-02-15 | 2026-02-17 | 2
6 | service cupboard decoration |  | 2026-02-23 | 2026-02-25 | 3
6 | service cupboard decoration |  | 2026-03-06 | 2026-03-07 | 1
6 | service cupboard decoration |  | 2026-03-13 | 2026-03-14 | 1
6 | service cupboard decoration |  | 2026-03-20 | 2026-03-21 | 1
6 | service cupboard decoration |  | 2026-03-27 | 2026-03-28 | 1
6 | service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
6 | service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
6 | service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
6 | service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
6 | service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
6 | service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
6 | service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
6 | service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
6 | service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
6 | service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
6 | service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
6 | service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
6 | service cupboard decoration |  | 2026-06-25 | 2026-06-28 | 2
7 | CARA |  | 2025-12-07 | 2025-12-08 | 1
7 | CARA |  | 2025-12-14 | 2025-12-15 | 1
7 | CARA |  | 2025-12-21 | 2025-12-22 | 1
7 | CARA |  | 2025-12-28 | 2025-12-29 | 1
7 | CARA |  | 2026-01-05 | 2026-01-06 | 2
7 | CARA |  | 2026-01-12 | 2026-01-13 | 2
7 | CARA |  | 2026-01-19 | 2026-01-20 | 2
7 | CARA |  | 2026-01-26 | 2026-01-27 | 2
7 | CARA |  | 2026-02-02 | 2026-02-03 | 2
7 | CARA |  | 2026-02-09 | 2026-02-10 | 2
7 | CARA |  | 2026-02-16 | 2026-02-25 | 8
7 | CARA |  | 2026-03-06 | 2026-03-07 | 1
7 | CARA |  | 2026-03-13 | 2026-03-14 | 1
7 | CARA |  | 2026-03-20 | 2026-03-21 | 1
7 | CARA |  | 2026-03-27 | 2026-03-28 | 1
7 | CARA |  | 2026-04-04 | 2026-04-05 | 1
7 | CARA |  | 2026-04-11 | 2026-04-12 | 1
7 | CARA |  | 2026-04-18 | 2026-04-19 | 1
7 | CARA |  | 2026-04-25 | 2026-04-26 | 1
7 | CARA |  | 2026-05-01 | 2026-05-02 | 1
7 | CARA |  | 2026-05-08 | 2026-05-09 | 1
7 | CARA |  | 2026-05-15 | 2026-05-16 | 1
7 | CARA |  | 2026-05-22 | 2026-05-23 | 1
7 | CARA |  | 2026-05-29 | 2026-05-30 | 1
7 | CARA |  | 2026-06-06 | 2026-06-07 | 1
7 | CARA |  | 2026-06-13 | 2026-06-14 | 1
7 | CARA |  | 2026-06-20 | 2026-06-21 | 1
7 | CARA |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-20 | 2
| Amtico flooring /Bathrooms |  | 2026-01-26 | 2026-01-27 | 2
| Amtico flooring /Bathrooms |  | 2026-02-02 | 2026-02-03 | 2
| Amtico flooring /Bathrooms |  | 2026-02-09 | 2026-02-10 | 2
| Amtico flooring /Bathrooms |  | 2026-02-13 | 2026-02-17 | 3
| Amtico flooring /Bathrooms |  | 2026-02-23 | 2026-02-25 | 3
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
8 | Plumbing final/shower screens |  | 2025-12-07 | 2025-12-08 | 1
8 | Plumbing final/shower screens |  | 2025-12-14 | 2025-12-15 | 1
8 | Plumbing final/shower screens |  | 2025-12-21 | 2025-12-22 | 1
8 | Plumbing final/shower screens |  | 2025-12-28 | 2025-12-29 | 1
8 | Plumbing final/shower screens |  | 2026-01-05 | 2026-01-06 | 2
8 | Plumbing final/shower screens |  | 2026-01-12 | 2026-01-13 | 2
8 | Plumbing final/shower screens |  | 2026-01-19 | 2026-01-20 | 2
8 | Plumbing final/shower screens |  | 2026-01-26 | 2026-01-27 | 2
8 | Plumbing final/shower screens |  | 2026-02-02 | 2026-02-03 | 2
8 | Plumbing final/shower screens |  | 2026-02-09 | 2026-02-10 | 2
8 | Plumbing final/shower screens |  | 2026-02-14 | 2026-02-20 | 5
8 | Plumbing final/shower screens |  | 2026-02-23 | 2026-02-25 | 3
8 | Plumbing final/shower screens |  | 2026-03-06 | 2026-03-07 | 1
8 | Plumbing final/shower screens |  | 2026-03-13 | 2026-03-14 | 1
8 | Plumbing final/shower screens |  | 2026-03-20 | 2026-03-21 | 1
8 | Plumbing final/shower screens |  | 2026-03-27 | 2026-03-28 | 1
8 | Plumbing final/shower screens |  | 2026-04-04 | 2026-04-05 | 1
8 | Plumbing final/shower screens |  | 2026-04-11 | 2026-04-12 | 1
8 | Plumbing final/shower screens |  | 2026-04-18 | 2026-04-19 | 1
8 | Plumbing final/shower screens |  | 2026-04-25 | 2026-04-26 | 1
8 | Plumbing final/shower screens |  | 2026-05-01 | 2026-05-02 | 1
8 | Plumbing final/shower screens |  | 2026-05-08 | 2026-05-09 | 1
8 | Plumbing final/shower screens |  | 2026-05-15 | 2026-05-16 | 1
8 | Plumbing final/shower screens |  | 2026-05-22 | 2026-05-23 | 1
8 | Plumbing final/shower screens |  | 2026-05-29 | 2026-05-30 | 1
8 | Plumbing final/shower screens |  | 2026-06-06 | 2026-06-07 | 1
8 | Plumbing final/shower screens |  | 2026-06-13 | 2026-06-14 | 1
8 | Plumbing final/shower screens |  | 2026-06-20 | 2026-06-21 | 1
8 | Plumbing final/shower screens |  | 2026-06-25 | 2026-06-28 | 2
8 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
8 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
8 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
8 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
8 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
8 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
8 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
8 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
8 | PANACEA |  | 2026-02-02 | 2026-02-03 | 2
8 | PANACEA |  | 2026-02-09 | 2026-02-10 | 2
8 | PANACEA |  | 2026-02-16 | 2026-02-17 | 2
8 | PANACEA |  | 2026-02-20 | 2026-02-27 | 6
8 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
8 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
8 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
8 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
8 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
8 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
8 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
8 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
8 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
8 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
8 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
8 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
8 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
8 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
8 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
8 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
8 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Power on |  | 2025-12-07 | 2025-12-08 | 1
| Power on |  | 2025-12-14 | 2025-12-15 | 1
| Power on |  | 2025-12-21 | 2025-12-22 | 1
| Power on |  | 2025-12-28 | 2025-12-29 | 1
| Power on |  | 2026-01-05 | 2026-01-06 | 2
| Power on |  | 2026-01-12 | 2026-01-13 | 2
| Power on |  | 2026-01-19 | 2026-01-20 | 2
| Power on |  | 2026-01-26 | 2026-01-27 | 2
| Power on |  | 2026-02-02 | 2026-02-03 | 2
| Power on |  | 2026-02-09 | 2026-02-10 | 2
| Power on |  | 2026-02-16 | 2026-02-17 | 2
| Power on |  | 2026-02-23 | 2026-02-25 | 3
| Power on |  | 2026-03-06 | 2026-03-07 | 1
| Power on |  | 2026-03-13 | 2026-03-14 | 1
| Power on |  | 2026-03-20 | 2026-03-21 | 1
| Power on |  | 2026-03-27 | 2026-03-28 | 1
| Power on |  | 2026-04-04 | 2026-04-05 | 1
| Power on |  | 2026-04-11 | 2026-04-12 | 1
| Power on |  | 2026-04-18 | 2026-04-19 | 1
| Power on |  | 2026-04-25 | 2026-04-26 | 1
| Power on |  | 2026-05-01 | 2026-05-02 | 1
| Power on |  | 2026-05-08 | 2026-05-09 | 1
| Power on |  | 2026-05-15 | 2026-05-16 | 1
| Power on |  | 2026-05-22 | 2026-05-23 | 1
| Power on |  | 2026-05-29 | 2026-05-30 | 1
| Power on |  | 2026-06-06 | 2026-06-07 | 1
| Power on |  | 2026-06-13 | 2026-06-14 | 1
| Power on |  | 2026-06-20 | 2026-06-21 | 1
| Power on |  | 2026-06-25 | 2026-06-28 | 2
| Water on |  | 2025-12-07 | 2025-12-08 | 1
| Water on |  | 2025-12-14 | 2025-12-15 | 1
| Water on |  | 2025-12-21 | 2025-12-22 | 1
| Water on |  | 2025-12-28 | 2025-12-29 | 1
| Water on |  | 2026-01-05 | 2026-01-06 | 2
| Water on |  | 2026-01-12 | 2026-01-13 | 2
| Water on |  | 2026-01-19 | 2026-01-20 | 2
| Water on |  | 2026-01-26 | 2026-01-27 | 2
| Water on |  | 2026-02-02 | 2026-02-03 | 2
| Water on |  | 2026-02-09 | 2026-02-10 | 2
| Water on |  | 2026-02-16 | 2026-02-17 | 2
| Water on |  | 2026-02-23 | 2026-02-25 | 3
| Water on |  | 2026-03-06 | 2026-03-07 | 1
| Water on |  | 2026-03-13 | 2026-03-14 | 1
| Water on |  | 2026-03-20 | 2026-03-21 | 1
| Water on |  | 2026-03-27 | 2026-03-28 | 1
| Water on |  | 2026-04-04 | 2026-04-05 | 1
| Water on |  | 2026-04-11 | 2026-04-12 | 1
| Water on |  | 2026-04-18 | 2026-04-19 | 1
| Water on |  | 2026-04-25 | 2026-04-26 | 1
| Water on |  | 2026-05-01 | 2026-05-02 | 1
| Water on |  | 2026-05-08 | 2026-05-09 | 1
| Water on |  | 2026-05-15 | 2026-05-16 | 1
| Water on |  | 2026-05-22 | 2026-05-23 | 1
| Water on |  | 2026-05-29 | 2026-05-30 | 1
| Water on |  | 2026-06-06 | 2026-06-07 | 1
| Water on |  | 2026-06-13 | 2026-06-14 | 1
| Water on |  | 2026-06-20 | 2026-06-21 | 1
| Water on |  | 2026-06-25 | 2026-06-28 | 2
9 | Edencroft |  | 2025-12-07 | 2025-12-08 | 1
9 | Edencroft |  | 2025-12-14 | 2025-12-15 | 1
9 | Edencroft |  | 2025-12-21 | 2025-12-22 | 1
9 | Edencroft |  | 2025-12-28 | 2025-12-29 | 1
9 | Edencroft |  | 2026-01-05 | 2026-01-06 | 2
9 | Edencroft |  | 2026-01-12 | 2026-01-13 | 2
9 | Edencroft |  | 2026-01-19 | 2026-01-20 | 2
9 | Edencroft |  | 2026-01-26 | 2026-01-27 | 2
9 | Edencroft |  | 2026-02-02 | 2026-02-03 | 2
9 | Edencroft |  | 2026-02-09 | 2026-02-10 | 2
9 | Edencroft |  | 2026-02-16 | 2026-02-17 | 2
9 | Edencroft |  | 2026-02-21 | 2026-02-25 | 3
9 | Edencroft |  | 2026-03-06 | 2026-03-07 | 1
9 | Edencroft |  | 2026-03-13 | 2026-03-14 | 1
9 | Edencroft |  | 2026-03-20 | 2026-03-21 | 1
9 | Edencroft |  | 2026-03-27 | 2026-03-28 | 1
9 | Edencroft |  | 2026-04-04 | 2026-04-05 | 1
9 | Edencroft |  | 2026-04-11 | 2026-04-12 | 1
9 | Edencroft |  | 2026-04-18 | 2026-04-19 | 1
9 | Edencroft |  | 2026-04-25 | 2026-04-26 | 1
9 | Edencroft |  | 2026-05-01 | 2026-05-02 | 1
9 | Edencroft |  | 2026-05-08 | 2026-05-09 | 1
9 | Edencroft |  | 2026-05-15 | 2026-05-16 | 1
9 | Edencroft |  | 2026-05-22 | 2026-05-23 | 1
9 | Edencroft |  | 2026-05-29 | 2026-05-30 | 1
9 | Edencroft |  | 2026-06-06 | 2026-06-07 | 1
9 | Edencroft |  | 2026-06-13 | 2026-06-14 | 1
9 | Edencroft |  | 2026-06-20 | 2026-06-21 | 1
9 | Edencroft |  | 2026-06-25 | 2026-06-28 | 2
10 | CPL |  | 2025-12-07 | 2025-12-08 | 1
10 | CPL |  | 2025-12-14 | 2025-12-15 | 1
10 | CPL |  | 2025-12-21 | 2025-12-22 | 1
10 | CPL |  | 2025-12-28 | 2025-12-29 | 1
10 | CPL |  | 2026-01-05 | 2026-01-06 | 2
10 | CPL |  | 2026-01-12 | 2026-01-13 | 2
10 | CPL |  | 2026-01-19 | 2026-01-20 | 2
10 | CPL |  | 2026-01-26 | 2026-01-27 | 2
10 | CPL |  | 2026-02-02 | 2026-02-03 | 2
10 | CPL |  | 2026-02-09 | 2026-02-10 | 2
10 | CPL |  | 2026-02-16 | 2026-02-17 | 2
10 | CPL |  | 2026-02-21 | 2026-02-25 | 3
10 | CPL |  | 2026-03-06 | 2026-03-07 | 1
10 | CPL |  | 2026-03-13 | 2026-03-14 | 1
10 | CPL |  | 2026-03-20 | 2026-03-21 | 1
10 | CPL |  | 2026-03-27 | 2026-03-28 | 1
10 | CPL |  | 2026-04-04 | 2026-04-05 | 1
10 | CPL |  | 2026-04-11 | 2026-04-12 | 1
10 | CPL |  | 2026-04-18 | 2026-04-19 | 1
10 | CPL |  | 2026-04-25 | 2026-04-26 | 1
10 | CPL |  | 2026-05-01 | 2026-05-02 | 1
10 | CPL |  | 2026-05-08 | 2026-05-09 | 1
10 | CPL |  | 2026-05-15 | 2026-05-16 | 1
10 | CPL |  | 2026-05-22 | 2026-05-23 | 1
10 | CPL |  | 2026-05-29 | 2026-05-30 | 1
10 | CPL |  | 2026-06-06 | 2026-06-07 | 1
10 | CPL |  | 2026-06-13 | 2026-06-14 | 1
10 | CPL |  | 2026-06-20 | 2026-06-21 | 1
10 | CPL |  | 2026-06-25 | 2026-06-28 | 2
11 | Armstrong |  | 2025-12-07 | 2025-12-08 | 1
11 | Armstrong |  | 2025-12-14 | 2025-12-15 | 1
11 | Armstrong |  | 2025-12-21 | 2025-12-22 | 1
11 | Armstrong |  | 2025-12-28 | 2025-12-29 | 1
11 | Armstrong |  | 2026-01-05 | 2026-01-06 | 2
11 | Armstrong |  | 2026-01-12 | 2026-01-13 | 2
11 | Armstrong |  | 2026-01-19 | 2026-01-20 | 2
11 | Armstrong |  | 2026-01-26 | 2026-01-27 | 2
11 | Armstrong |  | 2026-02-02 | 2026-02-03 | 2
11 | Armstrong |  | 2026-02-09 | 2026-02-10 | 2
11 | Armstrong |  | 2026-02-16 | 2026-02-17 | 2
11 | Armstrong |  | 2026-02-23 | 2026-03-02 | 6
11 | Armstrong |  | 2026-03-06 | 2026-03-07 | 1
11 | Armstrong |  | 2026-03-13 | 2026-03-14 | 1
11 | Armstrong |  | 2026-03-20 | 2026-03-21 | 1
11 | Armstrong |  | 2026-03-27 | 2026-03-28 | 1
11 | Armstrong |  | 2026-04-04 | 2026-04-05 | 1
11 | Armstrong |  | 2026-04-11 | 2026-04-12 | 1
11 | Armstrong |  | 2026-04-18 | 2026-04-19 | 1
11 | Armstrong |  | 2026-04-25 | 2026-04-26 | 1
11 | Armstrong |  | 2026-05-01 | 2026-05-02 | 1
11 | Armstrong |  | 2026-05-08 | 2026-05-09 | 1
11 | Armstrong |  | 2026-05-15 | 2026-05-16 | 1
11 | Armstrong |  | 2026-05-22 | 2026-05-23 | 1
11 | Armstrong |  | 2026-05-29 | 2026-05-30 | 1
11 | Armstrong |  | 2026-06-06 | 2026-06-07 | 1
11 | Armstrong |  | 2026-06-13 | 2026-06-14 | 1
11 | Armstrong |  | 2026-06-20 | 2026-06-21 | 1
11 | Armstrong |  | 2026-06-25 | 2026-06-28 | 2
| Final fix/sprinkler heads /panel heaters |  | 2025-12-07 | 2025-12-08 | 1
| Final fix/sprinkler heads /panel heaters |  | 2025-12-14 | 2025-12-15 | 1
| Final fix/sprinkler heads /panel heaters |  | 2025-12-21 | 2025-12-22 | 1
| Final fix/sprinkler heads /panel heaters |  | 2025-12-28 | 2025-12-29 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-01-05 | 2026-01-06 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-01-12 | 2026-01-13 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-01-19 | 2026-01-20 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-01-26 | 2026-01-27 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-02-02 | 2026-02-03 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-02-09 | 2026-02-10 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-02-16 | 2026-02-17 | 2
| Final fix/sprinkler heads /panel heaters |  | 2026-02-23 | 2026-02-25 | 3
| Final fix/sprinkler heads /panel heaters |  | 2026-03-01 | 2026-03-07 | 5
| Final fix/sprinkler heads /panel heaters |  | 2026-03-13 | 2026-03-14 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-03-20 | 2026-03-21 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-03-27 | 2026-03-28 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-04-04 | 2026-04-05 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-04-11 | 2026-04-12 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-04-18 | 2026-04-19 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-04-25 | 2026-04-26 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-05-01 | 2026-05-02 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-05-08 | 2026-05-09 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-05-15 | 2026-05-16 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-05-22 | 2026-05-23 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-05-29 | 2026-05-30 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-06-06 | 2026-06-07 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-06-13 | 2026-06-14 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-06-20 | 2026-06-21 | 1
| Final fix/sprinkler heads /panel heaters |  | 2026-06-25 | 2026-06-28 | 2
12 | Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-08 | 1
12 | Amtico flooring /Carpets |  | 2025-12-14 | 2025-12-15 | 1
12 | Amtico flooring /Carpets |  | 2025-12-21 | 2025-12-22 | 1
12 | Amtico flooring /Carpets |  | 2025-12-28 | 2025-12-29 | 1
12 | Amtico flooring /Carpets |  | 2026-01-05 | 2026-01-06 | 2
12 | Amtico flooring /Carpets |  | 2026-01-12 | 2026-01-13 | 2
12 | Amtico flooring /Carpets |  | 2026-01-19 | 2026-01-20 | 2
12 | Amtico flooring /Carpets |  | 2026-01-26 | 2026-01-27 | 2
12 | Amtico flooring /Carpets |  | 2026-02-02 | 2026-02-03 | 2
12 | Amtico flooring /Carpets |  | 2026-02-09 | 2026-02-10 | 2
12 | Amtico flooring /Carpets |  | 2026-02-16 | 2026-02-17 | 2
12 | Amtico flooring /Carpets |  | 2026-02-23 | 2026-02-25 | 3
12 | Amtico flooring /Carpets |  | 2026-03-06 | 2026-03-14 | 6
12 | Amtico flooring /Carpets |  | 2026-03-20 | 2026-03-21 | 1
12 | Amtico flooring /Carpets |  | 2026-03-27 | 2026-03-28 | 1
12 | Amtico flooring /Carpets |  | 2026-04-04 | 2026-04-05 | 1
12 | Amtico flooring /Carpets |  | 2026-04-11 | 2026-04-12 | 1
12 | Amtico flooring /Carpets |  | 2026-04-18 | 2026-04-19 | 1
12 | Amtico flooring /Carpets |  | 2026-04-25 | 2026-04-26 | 1
12 | Amtico flooring /Carpets |  | 2026-05-01 | 2026-05-02 | 1
12 | Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
12 | Amtico flooring /Carpets |  | 2026-05-15 | 2026-05-16 | 1
12 | Amtico flooring /Carpets |  | 2026-05-22 | 2026-05-23 | 1
12 | Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
12 | Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
12 | Amtico flooring /Carpets |  | 2026-06-13 | 2026-06-14 | 1
12 | Amtico flooring /Carpets |  | 2026-06-20 | 2026-06-21 | 1
12 | Amtico flooring /Carpets |  | 2026-06-25 | 2026-06-28 | 2
13 | MCL |  | 2025-12-07 | 2025-12-08 | 1
13 | MCL |  | 2025-12-14 | 2025-12-15 | 1
13 | MCL |  | 2025-12-21 | 2025-12-22 | 1
13 | MCL |  | 2025-12-28 | 2025-12-29 | 1
13 | MCL |  | 2026-01-05 | 2026-01-06 | 2
13 | MCL |  | 2026-01-12 | 2026-01-13 | 2
13 | MCL |  | 2026-01-19 | 2026-01-20 | 2
13 | MCL |  | 2026-01-26 | 2026-01-27 | 2
13 | MCL |  | 2026-02-02 | 2026-02-03 | 2
13 | MCL |  | 2026-02-09 | 2026-02-10 | 2
13 | MCL |  | 2026-02-16 | 2026-02-17 | 2
13 | MCL |  | 2026-02-23 | 2026-02-25 | 3
13 | MCL |  | 2026-03-06 | 2026-03-07 | 1
13 | MCL |  | 2026-03-13 | 2026-03-24 | 8
13 | MCL |  | 2026-03-27 | 2026-03-28 | 1
13 | MCL |  | 2026-04-04 | 2026-04-05 | 1
13 | MCL |  | 2026-04-11 | 2026-04-12 | 1
13 | MCL |  | 2026-04-18 | 2026-04-19 | 1
13 | MCL |  | 2026-04-25 | 2026-04-26 | 1
13 | MCL |  | 2026-05-01 | 2026-05-02 | 1
13 | MCL |  | 2026-05-08 | 2026-05-09 | 1
13 | MCL |  | 2026-05-15 | 2026-05-16 | 1
13 | MCL |  | 2026-05-22 | 2026-05-23 | 1
13 | MCL |  | 2026-05-29 | 2026-05-30 | 1
13 | MCL |  | 2026-06-06 | 2026-06-07 | 1
13 | MCL |  | 2026-06-13 | 2026-06-14 | 1
13 | MCL |  | 2026-06-20 | 2026-06-21 | 1
13 | MCL |  | 2026-06-25 | 2026-06-28 | 2
14 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
14 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
14 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
14 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
14 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
14 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
14 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
14 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
14 | PANACEA |  | 2026-02-02 | 2026-02-03 | 2
14 | PANACEA |  | 2026-02-09 | 2026-02-10 | 2
14 | PANACEA |  | 2026-02-16 | 2026-02-17 | 2
14 | PANACEA |  | 2026-02-23 | 2026-02-25 | 3
14 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
14 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
14 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
14 | PANACEA |  | 2026-03-25 | 2026-03-28 | 3
14 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
14 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
14 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
14 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
14 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
14 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
14 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
14 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
14 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
14 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
14 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
14 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
14 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Mastic |  | 2025-12-07 | 2025-12-08 | 1
| Mastic |  | 2025-12-14 | 2025-12-15 | 1
| Mastic |  | 2025-12-21 | 2025-12-22 | 1
| Mastic |  | 2025-12-28 | 2025-12-29 | 1
| Mastic |  | 2026-01-05 | 2026-01-06 | 2
| Mastic |  | 2026-01-12 | 2026-01-13 | 2
| Mastic |  | 2026-01-19 | 2026-01-20 | 2
| Mastic |  | 2026-01-26 | 2026-01-27 | 2
| Mastic |  | 2026-02-02 | 2026-02-03 | 2
| Mastic |  | 2026-02-09 | 2026-02-10 | 2
| Mastic |  | 2026-02-16 | 2026-02-17 | 2
| Mastic |  | 2026-02-23 | 2026-02-25 | 3
| Mastic |  | 2026-03-06 | 2026-03-07 | 1
| Mastic |  | 2026-03-13 | 2026-03-14 | 1
| Mastic |  | 2026-03-20 | 2026-03-21 | 1
| Mastic |  | 2026-03-27 | 2026-03-30 | 2
| Mastic |  | 2026-04-04 | 2026-04-05 | 1
| Mastic |  | 2026-04-11 | 2026-04-12 | 1
| Mastic |  | 2026-04-18 | 2026-04-19 | 1
| Mastic |  | 2026-04-25 | 2026-04-26 | 1
| Mastic |  | 2026-05-01 | 2026-05-02 | 1
| Mastic |  | 2026-05-08 | 2026-05-09 | 1
| Mastic |  | 2026-05-15 | 2026-05-16 | 1
| Mastic |  | 2026-05-22 | 2026-05-23 | 1
| Mastic |  | 2026-05-29 | 2026-05-30 | 1
| Mastic |  | 2026-06-06 | 2026-06-07 | 1
| Mastic |  | 2026-06-13 | 2026-06-14 | 1
| Mastic |  | 2026-06-20 | 2026-06-21 | 1
| Mastic |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-15 | 1
| Handover to client |  | 2025-12-21 | 2025-12-22 | 1
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-12 | 2026-01-13 | 2
| Handover to client |  | 2026-01-19 | 2026-01-20 | 2
| Handover to client |  | 2026-01-26 | 2026-01-27 | 2
| Handover to client |  | 2026-02-02 | 2026-02-03 | 2
| Handover to client |  | 2026-02-09 | 2026-02-10 | 2
| Handover to client |  | 2026-02-16 | 2026-02-17 | 2
| Handover to client |  | 2026-02-23 | 2026-02-25 | 3
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-06 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2025-12-07 | 2025-12-08 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2025-12-14 | 2025-12-15 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2025-12-21 | 2025-12-22 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2025-12-28 | 2025-12-29 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-01-05 | 2026-01-06 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-01-12 | 2026-01-13 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-01-19 | 2026-01-20 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-01-26 | 2026-01-27 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-02-02 | 2026-02-03 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-02-09 | 2026-02-10 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-02-16 | 2026-02-17 | 2
16 | Level 1 Apartment fit out cluster 2 |  | 2026-02-23 | 2026-02-25 | 3
16 | Level 1 Apartment fit out cluster 2 |  | 2026-03-06 | 2026-03-07 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-03-13 | 2026-03-14 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-03-20 | 2026-03-21 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-03-27 | 2026-03-28 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-04-04 | 2026-04-05 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-04-11 | 2026-04-12 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-04-18 | 2026-04-19 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-04-25 | 2026-04-26 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-05-01 | 2026-05-02 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-05-08 | 2026-05-09 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-05-15 | 2026-05-16 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-05-22 | 2026-05-23 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-05-29 | 2026-05-30 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-06-06 | 2026-06-07 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-06-13 | 2026-06-14 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-06-20 | 2026-06-21 | 1
16 | Level 1 Apartment fit out cluster 2 |  | 2026-06-25 | 2026-06-28 | 2
17 | MCL |  | 2025-12-07 | 2025-12-08 | 1
17 | MCL |  | 2025-12-14 | 2025-12-15 | 1
17 | MCL |  | 2025-12-21 | 2025-12-22 | 1
17 | MCL |  | 2025-12-28 | 2025-12-29 | 1
17 | MCL |  | 2026-01-05 | 2026-01-06 | 2
17 | MCL |  | 2026-01-12 | 2026-01-13 | 2
17 | MCL |  | 2026-01-19 | 2026-01-20 | 2
17 | MCL |  | 2026-01-26 | 2026-01-27 | 2
17 | MCL |  | 2026-02-02 | 2026-02-03 | 2
17 | MCL |  | 2026-02-09 | 2026-02-10 | 2
17 | MCL |  | 2026-02-16 | 2026-02-17 | 2
17 | MCL |  | 2026-02-19 | 2026-02-26 | 6
17 | MCL |  | 2026-03-06 | 2026-03-07 | 1
17 | MCL |  | 2026-03-13 | 2026-03-14 | 1
17 | MCL |  | 2026-03-20 | 2026-03-21 | 1
17 | MCL |  | 2026-03-27 | 2026-03-28 | 1
17 | MCL |  | 2026-04-04 | 2026-04-05 | 1
17 | MCL |  | 2026-04-11 | 2026-04-12 | 1
17 | MCL |  | 2026-04-18 | 2026-04-19 | 1
17 | MCL |  | 2026-04-25 | 2026-04-26 | 1
17 | MCL |  | 2026-05-01 | 2026-05-02 | 1
17 | MCL |  | 2026-05-08 | 2026-05-09 | 1
17 | MCL |  | 2026-05-15 | 2026-05-16 | 1
17 | MCL |  | 2026-05-22 | 2026-05-23 | 1
17 | MCL |  | 2026-05-29 | 2026-05-30 | 1
17 | MCL |  | 2026-06-06 | 2026-06-07 | 1
17 | MCL |  | 2026-06-13 | 2026-06-14 | 1
17 | MCL |  | 2026-06-20 | 2026-06-21 | 1
17 | MCL |  | 2026-06-25 | 2026-06-28 | 2
18 | Armstrong |  | 2025-12-07 | 2025-12-08 | 1
18 | Armstrong |  | 2025-12-14 | 2025-12-15 | 1
18 | Armstrong |  | 2025-12-17 | 2025-12-22 | 4
18 | Armstrong |  | 2025-12-28 | 2025-12-29 | 1
18 | Armstrong |  | 2026-01-05 | 2026-01-06 | 2
18 | Armstrong |  | 2026-01-12 | 2026-01-13 | 2
18 | Armstrong |  | 2026-01-19 | 2026-01-20 | 2
18 | Armstrong |  | 2026-01-26 | 2026-01-27 | 2
18 | Armstrong |  | 2026-02-02 | 2026-02-03 | 2
18 | Armstrong |  | 2026-02-09 | 2026-02-14 | 5
18 | Armstrong |  | 2026-02-16 | 2026-02-17 | 2
18 | Armstrong |  | 2026-02-23 | 2026-02-25 | 3
18 | Armstrong |  | 2026-03-06 | 2026-03-07 | 1
18 | Armstrong |  | 2026-03-13 | 2026-03-14 | 1
18 | Armstrong |  | 2026-03-20 | 2026-03-21 | 1
18 | Armstrong |  | 2026-03-27 | 2026-03-28 | 1
18 | Armstrong |  | 2026-04-04 | 2026-04-05 | 1
18 | Armstrong |  | 2026-04-11 | 2026-04-12 | 1
18 | Armstrong |  | 2026-04-18 | 2026-04-19 | 1
18 | Armstrong |  | 2026-04-25 | 2026-04-26 | 1
18 | Armstrong |  | 2026-05-01 | 2026-05-02 | 1
18 | Armstrong |  | 2026-05-08 | 2026-05-09 | 1
18 | Armstrong |  | 2026-05-15 | 2026-05-16 | 1
18 | Armstrong |  | 2026-05-22 | 2026-05-23 | 1
18 | Armstrong |  | 2026-05-29 | 2026-05-30 | 1
18 | Armstrong |  | 2026-06-06 | 2026-06-07 | 1
18 | Armstrong |  | 2026-06-13 | 2026-06-14 | 1
18 | Armstrong |  | 2026-06-20 | 2026-06-21 | 1
18 | Armstrong |  | 2026-06-25 | 2026-06-28 | 2
19 | PANACEA |  | 2025-12-07 | 2025-12-15 | 6
19 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
19 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
19 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
19 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
19 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
19 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
19 | PANACEA |  | 2026-02-02 | 2026-02-03 | 2
19 | PANACEA |  | 2026-02-09 | 2026-02-17 | 7
19 | PANACEA |  | 2026-02-23 | 2026-02-25 | 3
19 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
19 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
19 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
19 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
19 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
19 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
19 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
19 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
19 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
19 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
19 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
19 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
19 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
19 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
19 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
19 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
19 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Service cupboard board ceiling &finish |  | 2025-12-07 | 2025-12-15 | 6
| Service cupboard board ceiling &finish |  | 2025-12-21 | 2025-12-22 | 1
| Service cupboard board ceiling &finish |  | 2025-12-28 | 2025-12-29 | 1
| Service cupboard board ceiling &finish |  | 2026-01-05 | 2026-01-06 | 2
| Service cupboard board ceiling &finish |  | 2026-01-12 | 2026-01-13 | 2
| Service cupboard board ceiling &finish |  | 2026-01-19 | 2026-01-20 | 2
| Service cupboard board ceiling &finish |  | 2026-01-26 | 2026-01-27 | 2
| Service cupboard board ceiling &finish |  | 2026-02-02 | 2026-02-03 | 2
| Service cupboard board ceiling &finish |  | 2026-02-09 | 2026-02-10 | 2
| Service cupboard board ceiling &finish |  | 2026-02-16 | 2026-02-17 | 2
| Service cupboard board ceiling &finish |  | 2026-02-23 | 2026-02-25 | 3
| Service cupboard board ceiling &finish |  | 2026-03-06 | 2026-03-07 | 1
| Service cupboard board ceiling &finish |  | 2026-03-13 | 2026-03-14 | 1
| Service cupboard board ceiling &finish |  | 2026-03-20 | 2026-03-21 | 1
| Service cupboard board ceiling &finish |  | 2026-03-27 | 2026-03-28 | 1
| Service cupboard board ceiling &finish |  | 2026-04-04 | 2026-04-05 | 1
| Service cupboard board ceiling &finish |  | 2026-04-11 | 2026-04-12 | 1
| Service cupboard board ceiling &finish |  | 2026-04-18 | 2026-04-19 | 1
| Service cupboard board ceiling &finish |  | 2026-04-25 | 2026-04-26 | 1
| Service cupboard board ceiling &finish |  | 2026-05-01 | 2026-05-02 | 1
| Service cupboard board ceiling &finish |  | 2026-05-08 | 2026-05-09 | 1
| Service cupboard board ceiling &finish |  | 2026-05-15 | 2026-05-16 | 1
| Service cupboard board ceiling &finish |  | 2026-05-22 | 2026-05-23 | 1
| Service cupboard board ceiling &finish |  | 2026-05-29 | 2026-05-30 | 1
| Service cupboard board ceiling &finish |  | 2026-06-06 | 2026-06-07 | 1
| Service cupboard board ceiling &finish |  | 2026-06-13 | 2026-06-14 | 1
| Service cupboard board ceiling &finish |  | 2026-06-20 | 2026-06-21 | 1
| Service cupboard board ceiling &finish |  | 2026-06-25 | 2026-06-28 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-08 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2025-12-14 | 2025-12-15 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2025-12-21 | 2026-01-01 | 9
Board ceilings | service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-06 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-01-12 | 2026-01-13 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-20 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-01-26 | 2026-01-27 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-02-02 | 2026-02-03 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-02-09 | 2026-02-10 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-02-13 | 2026-02-14 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-02-16 | 2026-02-17 | 2
Board ceilings | service cupbaord -plywood flooring |  | 2026-02-23 | 2026-02-25 | 3
Board ceilings | service cupbaord -plywood flooring |  | 2026-03-06 | 2026-03-07 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-03-13 | 2026-03-14 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-03-20 | 2026-03-21 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-03-27 | 2026-03-28 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-05-15 | 2026-05-16 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-05-22 | 2026-05-23 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-06-13 | 2026-06-14 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-06-20 | 2026-06-21 | 1
Board ceilings | service cupbaord -plywood flooring |  | 2026-06-25 | 2026-06-28 | 2
20 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
20 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
20 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
20 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
20 | PANACEA |  | 2026-01-02 | 2026-01-13 | 8
20 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
20 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
20 | PANACEA |  | 2026-02-02 | 2026-02-03 | 2
20 | PANACEA |  | 2026-02-09 | 2026-02-10 | 2
20 | PANACEA |  | 2026-02-15 | 2026-02-17 | 2
20 | PANACEA |  | 2026-02-23 | 2026-02-25 | 3
20 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
20 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
20 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
20 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
20 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
20 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
20 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
20 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
20 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
20 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
20 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
20 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
20 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
20 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
20 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
20 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
20 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
21 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
21 | Active flooring |  | 2025-12-14 | 2025-12-15 | 1
21 | Active flooring |  | 2025-12-21 | 2025-12-22 | 1
21 | Active flooring |  | 2025-12-28 | 2025-12-29 | 1
21 | Active flooring |  | 2026-01-05 | 2026-01-06 | 2
21 | Active flooring |  | 2026-01-10 | 2026-01-16 | 5
21 | Active flooring |  | 2026-01-19 | 2026-01-20 | 2
21 | Active flooring |  | 2026-01-26 | 2026-01-27 | 2
21 | Active flooring |  | 2026-02-02 | 2026-02-03 | 2
21 | Active flooring |  | 2026-02-09 | 2026-02-10 | 2
21 | Active flooring |  | 2026-02-16 | 2026-02-17 | 2
21 | Active flooring |  | 2026-02-23 | 2026-02-25 | 3
21 | Active flooring |  | 2026-03-06 | 2026-03-07 | 1
21 | Active flooring |  | 2026-03-13 | 2026-03-14 | 1
21 | Active flooring |  | 2026-03-20 | 2026-03-21 | 1
21 | Active flooring |  | 2026-03-27 | 2026-03-28 | 1
21 | Active flooring |  | 2026-04-04 | 2026-04-05 | 1
21 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
21 | Active flooring |  | 2026-04-18 | 2026-04-19 | 1
21 | Active flooring |  | 2026-04-25 | 2026-04-26 | 1
21 | Active flooring |  | 2026-05-01 | 2026-05-02 | 1
21 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
21 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
21 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
21 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
21 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
21 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
21 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
21 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-10 | 2026-01-16 | 5
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-20 | 2
| Amtico flooring /Bathrooms |  | 2026-01-26 | 2026-01-27 | 2
| Amtico flooring /Bathrooms |  | 2026-02-02 | 2026-02-03 | 2
| Amtico flooring /Bathrooms |  | 2026-02-09 | 2026-02-10 | 2
| Amtico flooring /Bathrooms |  | 2026-02-16 | 2026-02-25 | 8
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
RICKWORK | MCL |  | 2025-12-07 | 2025-12-08 | 1
RICKWORK | MCL |  | 2025-12-14 | 2025-12-15 | 1
RICKWORK | MCL |  | 2025-12-21 | 2025-12-22 | 1
RICKWORK | MCL |  | 2025-12-28 | 2025-12-29 | 1
RICKWORK | MCL |  | 2026-01-05 | 2026-01-06 | 2
RICKWORK | MCL |  | 2026-01-12 | 2026-01-17 | 5
RICKWORK | MCL |  | 2026-01-19 | 2026-01-20 | 2
RICKWORK | MCL |  | 2026-01-26 | 2026-01-27 | 2
RICKWORK | MCL |  | 2026-02-02 | 2026-02-03 | 2
RICKWORK | MCL |  | 2026-02-09 | 2026-02-10 | 2
RICKWORK | MCL |  | 2026-02-16 | 2026-02-17 | 2
RICKWORK | MCL |  | 2026-02-20 | 2026-02-27 | 6
RICKWORK | MCL |  | 2026-03-06 | 2026-03-07 | 1
RICKWORK | MCL |  | 2026-03-13 | 2026-03-14 | 1
RICKWORK | MCL |  | 2026-03-20 | 2026-03-21 | 1
RICKWORK | MCL |  | 2026-03-27 | 2026-03-28 | 1
RICKWORK | MCL |  | 2026-04-04 | 2026-04-05 | 1
RICKWORK | MCL |  | 2026-04-11 | 2026-04-12 | 1
RICKWORK | MCL |  | 2026-04-18 | 2026-04-19 | 1
RICKWORK | MCL |  | 2026-04-25 | 2026-04-26 | 1
RICKWORK | MCL |  | 2026-05-01 | 2026-05-02 | 1
RICKWORK | MCL |  | 2026-05-08 | 2026-05-09 | 1
RICKWORK | MCL |  | 2026-05-15 | 2026-05-16 | 1
RICKWORK | MCL |  | 2026-05-22 | 2026-05-23 | 1
RICKWORK | MCL |  | 2026-05-29 | 2026-05-30 | 1
RICKWORK | MCL |  | 2026-06-06 | 2026-06-07 | 1
RICKWORK | MCL |  | 2026-06-13 | 2026-06-14 | 1
RICKWORK | MCL |  | 2026-06-20 | 2026-06-21 | 1
RICKWORK | MCL |  | 2026-06-25 | 2026-06-28 | 2
23 | Smiths |  | 2025-12-07 | 2025-12-08 | 1
23 | Smiths |  | 2025-12-14 | 2025-12-15 | 1
23 | Smiths |  | 2025-12-21 | 2025-12-22 | 1
23 | Smiths |  | 2025-12-28 | 2025-12-29 | 1
23 | Smiths |  | 2026-01-05 | 2026-01-06 | 2
23 | Smiths |  | 2026-01-12 | 2026-01-13 | 2
23 | Smiths |  | 2026-01-16 | 2026-01-20 | 3
23 | Smiths |  | 2026-01-26 | 2026-01-27 | 2
23 | Smiths |  | 2026-02-02 | 2026-02-03 | 2
23 | Smiths |  | 2026-02-09 | 2026-02-10 | 2
23 | Smiths |  | 2026-02-16 | 2026-02-17 | 2
23 | Smiths |  | 2026-02-23 | 2026-02-25 | 3
23 | Smiths |  | 2026-02-28 | 2026-03-03 | 2
23 | Smiths |  | 2026-03-06 | 2026-03-07 | 1
23 | Smiths |  | 2026-03-13 | 2026-03-14 | 1
23 | Smiths |  | 2026-03-20 | 2026-03-21 | 1
23 | Smiths |  | 2026-03-27 | 2026-03-28 | 1
23 | Smiths |  | 2026-04-04 | 2026-04-05 | 1
23 | Smiths |  | 2026-04-11 | 2026-04-12 | 1
23 | Smiths |  | 2026-04-18 | 2026-04-19 | 1
23 | Smiths |  | 2026-04-25 | 2026-04-26 | 1
23 | Smiths |  | 2026-05-01 | 2026-05-02 | 1
23 | Smiths |  | 2026-05-08 | 2026-05-09 | 1
23 | Smiths |  | 2026-05-15 | 2026-05-16 | 1
23 | Smiths |  | 2026-05-22 | 2026-05-23 | 1
23 | Smiths |  | 2026-05-29 | 2026-05-30 | 1
23 | Smiths |  | 2026-06-06 | 2026-06-07 | 1
23 | Smiths |  | 2026-06-13 | 2026-06-14 | 1
23 | Smiths |  | 2026-06-20 | 2026-06-21 | 1
23 | Smiths |  | 2026-06-25 | 2026-06-28 | 2
| Power on |  | 2025-12-07 | 2025-12-08 | 1
| Power on |  | 2025-12-14 | 2025-12-15 | 1
| Power on |  | 2025-12-21 | 2025-12-22 | 1
| Power on |  | 2025-12-28 | 2025-12-29 | 1
| Power on |  | 2026-01-05 | 2026-01-06 | 2
| Power on |  | 2026-01-12 | 2026-01-13 | 2
| Power on |  | 2026-01-16 | 2026-01-20 | 3
| Power on |  | 2026-01-26 | 2026-01-27 | 2
| Power on |  | 2026-02-02 | 2026-02-03 | 2
| Power on |  | 2026-02-09 | 2026-02-10 | 2
| Power on |  | 2026-02-16 | 2026-02-17 | 2
| Power on |  | 2026-02-23 | 2026-02-25 | 3
| Power on |  | 2026-03-06 | 2026-03-07 | 1
| Power on |  | 2026-03-13 | 2026-03-14 | 1
| Power on |  | 2026-03-20 | 2026-03-21 | 1
| Power on |  | 2026-03-27 | 2026-03-28 | 1
| Power on |  | 2026-04-04 | 2026-04-05 | 1
| Power on |  | 2026-04-11 | 2026-04-12 | 1
| Power on |  | 2026-04-18 | 2026-04-19 | 1
| Power on |  | 2026-04-25 | 2026-04-26 | 1
| Power on |  | 2026-05-01 | 2026-05-02 | 1
| Power on |  | 2026-05-08 | 2026-05-09 | 1
| Power on |  | 2026-05-15 | 2026-05-16 | 1
| Power on |  | 2026-05-22 | 2026-05-23 | 1
| Power on |  | 2026-05-29 | 2026-05-30 | 1
| Power on |  | 2026-06-06 | 2026-06-07 | 1
| Power on |  | 2026-06-13 | 2026-06-14 | 1
| Power on |  | 2026-06-20 | 2026-06-21 | 1
| Power on |  | 2026-06-25 | 2026-06-28 | 2
| Water on |  | 2025-12-07 | 2025-12-08 | 1
| Water on |  | 2025-12-14 | 2025-12-15 | 1
| Water on |  | 2025-12-21 | 2025-12-22 | 1
| Water on |  | 2025-12-28 | 2025-12-29 | 1
| Water on |  | 2026-01-05 | 2026-01-06 | 2
| Water on |  | 2026-01-12 | 2026-01-13 | 2
| Water on |  | 2026-01-16 | 2026-01-20 | 3
| Water on |  | 2026-01-26 | 2026-01-27 | 2
| Water on |  | 2026-02-02 | 2026-02-03 | 2
| Water on |  | 2026-02-09 | 2026-02-10 | 2
| Water on |  | 2026-02-16 | 2026-02-17 | 2
| Water on |  | 2026-02-23 | 2026-02-25 | 3
| Water on |  | 2026-03-06 | 2026-03-07 | 1
| Water on |  | 2026-03-13 | 2026-03-14 | 1
| Water on |  | 2026-03-20 | 2026-03-21 | 1
| Water on |  | 2026-03-27 | 2026-03-28 | 1
| Water on |  | 2026-04-04 | 2026-04-05 | 1
| Water on |  | 2026-04-11 | 2026-04-12 | 1
| Water on |  | 2026-04-18 | 2026-04-19 | 1
| Water on |  | 2026-04-25 | 2026-04-26 | 1
| Water on |  | 2026-05-01 | 2026-05-02 | 1
| Water on |  | 2026-05-08 | 2026-05-09 | 1
| Water on |  | 2026-05-15 | 2026-05-16 | 1
| Water on |  | 2026-05-22 | 2026-05-23 | 1
| Water on |  | 2026-05-29 | 2026-05-30 | 1
| Water on |  | 2026-06-06 | 2026-06-07 | 1
| Water on |  | 2026-06-13 | 2026-06-14 | 1
| Water on |  | 2026-06-20 | 2026-06-21 | 1
| Water on |  | 2026-06-25 | 2026-06-28 | 2
24 | MCL |  | 2025-12-07 | 2025-12-08 | 1
24 | MCL |  | 2025-12-14 | 2025-12-15 | 1
24 | MCL |  | 2025-12-21 | 2025-12-22 | 1
24 | MCL |  | 2025-12-28 | 2025-12-29 | 1
24 | MCL |  | 2026-01-05 | 2026-01-06 | 2
24 | MCL |  | 2026-01-12 | 2026-01-13 | 2
24 | MCL |  | 2026-01-19 | 2026-01-20 | 2
24 | MCL |  | 2026-01-26 | 2026-01-27 | 2
24 | MCL |  | 2026-02-02 | 2026-02-03 | 2
24 | MCL |  | 2026-02-09 | 2026-02-10 | 2
24 | MCL |  | 2026-02-16 | 2026-02-17 | 2
24 | MCL |  | 2026-02-23 | 2026-02-25 | 3
24 | MCL |  | 2026-03-06 | 2026-03-07 | 1
24 | MCL |  | 2026-03-13 | 2026-03-14 | 1
24 | MCL |  | 2026-03-20 | 2026-03-21 | 1
24 | MCL |  | 2026-03-27 | 2026-03-28 | 1
24 | MCL |  | 2026-04-04 | 2026-04-05 | 1
24 | MCL |  | 2026-04-11 | 2026-04-12 | 1
24 | MCL |  | 2026-04-18 | 2026-04-19 | 1
24 | MCL |  | 2026-04-25 | 2026-04-26 | 1
24 | MCL |  | 2026-05-01 | 2026-05-02 | 1
24 | MCL |  | 2026-05-08 | 2026-05-09 | 1
24 | MCL |  | 2026-05-15 | 2026-05-16 | 1
24 | MCL |  | 2026-05-22 | 2026-05-23 | 1
24 | MCL |  | 2026-05-29 | 2026-05-30 | 1
24 | MCL |  | 2026-06-06 | 2026-06-07 | 1
24 | MCL |  | 2026-06-13 | 2026-06-14 | 1
24 | MCL |  | 2026-06-20 | 2026-06-21 | 1
24 | MCL |  | 2026-06-25 | 2026-06-28 | 2
25 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
25 | Active flooring |  | 2025-12-14 | 2025-12-15 | 1
25 | Active flooring |  | 2025-12-21 | 2025-12-22 | 1
25 | Active flooring |  | 2025-12-28 | 2025-12-29 | 1
25 | Active flooring |  | 2026-01-05 | 2026-01-06 | 2
25 | Active flooring |  | 2026-01-12 | 2026-01-16 | 5
25 | Active flooring |  | 2026-01-19 | 2026-01-20 | 2
25 | Active flooring |  | 2026-01-26 | 2026-01-27 | 2
25 | Active flooring |  | 2026-02-02 | 2026-02-03 | 2
25 | Active flooring |  | 2026-02-09 | 2026-02-10 | 2
25 | Active flooring |  | 2026-02-16 | 2026-02-17 | 2
25 | Active flooring |  | 2026-02-23 | 2026-02-25 | 3
25 | Active flooring |  | 2026-03-06 | 2026-03-07 | 1
25 | Active flooring |  | 2026-03-13 | 2026-03-14 | 1
25 | Active flooring |  | 2026-03-20 | 2026-03-21 | 1
25 | Active flooring |  | 2026-03-27 | 2026-03-28 | 1
25 | Active flooring |  | 2026-04-04 | 2026-04-05 | 1
25 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
25 | Active flooring |  | 2026-04-18 | 2026-04-19 | 1
25 | Active flooring |  | 2026-04-25 | 2026-04-26 | 1
25 | Active flooring |  | 2026-05-01 | 2026-05-02 | 1
25 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
25 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
25 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
25 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
25 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
25 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
25 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
25 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
26 | Branniff |  | 2025-12-07 | 2025-12-08 | 1
26 | Branniff |  | 2025-12-14 | 2025-12-15 | 1
26 | Branniff |  | 2025-12-21 | 2025-12-22 | 1
26 | Branniff |  | 2025-12-28 | 2025-12-29 | 1
26 | Branniff |  | 2026-01-05 | 2026-01-06 | 2
26 | Branniff |  | 2026-01-12 | 2026-01-20 | 7
26 | Branniff |  | 2026-01-26 | 2026-01-27 | 2
26 | Branniff |  | 2026-02-02 | 2026-02-03 | 2
26 | Branniff |  | 2026-02-09 | 2026-02-10 | 2
26 | Branniff |  | 2026-02-16 | 2026-02-17 | 2
26 | Branniff |  | 2026-02-23 | 2026-02-25 | 3
26 | Branniff |  | 2026-03-02 | 2026-03-09 | 6
26 | Branniff |  | 2026-03-13 | 2026-03-14 | 1
26 | Branniff |  | 2026-03-20 | 2026-03-21 | 1
26 | Branniff |  | 2026-03-27 | 2026-03-28 | 1
26 | Branniff |  | 2026-04-04 | 2026-04-05 | 1
26 | Branniff |  | 2026-04-11 | 2026-04-12 | 1
26 | Branniff |  | 2026-04-18 | 2026-04-19 | 1
26 | Branniff |  | 2026-04-25 | 2026-04-26 | 1
26 | Branniff |  | 2026-05-01 | 2026-05-02 | 1
26 | Branniff |  | 2026-05-08 | 2026-05-09 | 1
26 | Branniff |  | 2026-05-15 | 2026-05-16 | 1
26 | Branniff |  | 2026-05-22 | 2026-05-23 | 1
26 | Branniff |  | 2026-05-29 | 2026-05-30 | 1
26 | Branniff |  | 2026-06-06 | 2026-06-07 | 1
26 | Branniff |  | 2026-06-13 | 2026-06-14 | 1
26 | Branniff |  | 2026-06-20 | 2026-06-21 | 1
26 | Branniff |  | 2026-06-25 | 2026-06-28 | 2
Amtico flooring /Carpets | Wren |  | 2025-12-07 | 2025-12-08 | 1
Amtico flooring /Carpets | Wren |  | 2025-12-14 | 2025-12-15 | 1
Amtico flooring /Carpets | Wren |  | 2025-12-21 | 2025-12-22 | 1
Amtico flooring /Carpets | Wren |  | 2025-12-28 | 2025-12-29 | 1
Amtico flooring /Carpets | Wren |  | 2026-01-05 | 2026-01-06 | 2
Amtico flooring /Carpets | Wren |  | 2026-01-12 | 2026-01-13 | 2
Amtico flooring /Carpets | Wren |  | 2026-01-19 | 2026-01-20 | 2
Amtico flooring /Carpets | Wren |  | 2026-01-23 | 2026-01-29 | 5
Amtico flooring /Carpets | Wren |  | 2026-02-02 | 2026-02-03 | 2
Amtico flooring /Carpets | Wren |  | 2026-02-09 | 2026-02-10 | 2
Amtico flooring /Carpets | Wren |  | 2026-02-16 | 2026-02-17 | 2
Amtico flooring /Carpets | Wren |  | 2026-02-23 | 2026-02-25 | 3
Amtico flooring /Carpets | Wren |  | 2026-03-06 | 2026-03-14 | 6
Amtico flooring /Carpets | Wren |  | 2026-03-20 | 2026-03-21 | 1
Amtico flooring /Carpets | Wren |  | 2026-03-27 | 2026-03-28 | 1
Amtico flooring /Carpets | Wren |  | 2026-04-04 | 2026-04-05 | 1
Amtico flooring /Carpets | Wren |  | 2026-04-11 | 2026-04-12 | 1
Amtico flooring /Carpets | Wren |  | 2026-04-18 | 2026-04-19 | 1
Amtico flooring /Carpets | Wren |  | 2026-04-25 | 2026-04-26 | 1
Amtico flooring /Carpets | Wren |  | 2026-05-01 | 2026-05-02 | 1
Amtico flooring /Carpets | Wren |  | 2026-05-08 | 2026-05-09 | 1
Amtico flooring /Carpets | Wren |  | 2026-05-15 | 2026-05-16 | 1
Amtico flooring /Carpets | Wren |  | 2026-05-22 | 2026-05-23 | 1
Amtico flooring /Carpets | Wren |  | 2026-05-29 | 2026-05-30 | 1
Amtico flooring /Carpets | Wren |  | 2026-06-06 | 2026-06-07 | 1
Amtico flooring /Carpets | Wren |  | 2026-06-13 | 2026-06-14 | 1
Amtico flooring /Carpets | Wren |  | 2026-06-20 | 2026-06-21 | 1
Amtico flooring /Carpets | Wren |  | 2026-06-25 | 2026-06-28 | 2
| De snag all trades -test & commision |  | 2025-12-07 | 2025-12-08 | 1
| De snag all trades -test & commision |  | 2025-12-14 | 2025-12-15 | 1
| De snag all trades -test & commision |  | 2025-12-21 | 2025-12-22 | 1
| De snag all trades -test & commision |  | 2025-12-28 | 2025-12-29 | 1
| De snag all trades -test & commision |  | 2026-01-05 | 2026-01-06 | 2
| De snag all trades -test & commision |  | 2026-01-12 | 2026-01-13 | 2
| De snag all trades -test & commision |  | 2026-01-19 | 2026-01-20 | 2
| De snag all trades -test & commision |  | 2026-01-26 | 2026-01-27 | 2
| De snag all trades -test & commision |  | 2026-02-02 | 2026-02-03 | 2
| De snag all trades -test & commision |  | 2026-02-09 | 2026-02-10 | 2
| De snag all trades -test & commision |  | 2026-02-16 | 2026-02-17 | 2
| De snag all trades -test & commision |  | 2026-02-23 | 2026-02-25 | 3
| De snag all trades -test & commision |  | 2026-03-06 | 2026-03-07 | 1
| De snag all trades -test & commision |  | 2026-03-13 | 2026-03-21 | 6
| De snag all trades -test & commision |  | 2026-03-27 | 2026-03-28 | 1
| De snag all trades -test & commision |  | 2026-04-04 | 2026-04-05 | 1
| De snag all trades -test & commision |  | 2026-04-11 | 2026-04-12 | 1
| De snag all trades -test & commision |  | 2026-04-18 | 2026-04-19 | 1
| De snag all trades -test & commision |  | 2026-04-25 | 2026-04-26 | 1
| De snag all trades -test & commision |  | 2026-05-01 | 2026-05-02 | 1
| De snag all trades -test & commision |  | 2026-05-08 | 2026-05-09 | 1
| De snag all trades -test & commision |  | 2026-05-15 | 2026-05-16 | 1
| De snag all trades -test & commision |  | 2026-05-22 | 2026-05-23 | 1
| De snag all trades -test & commision |  | 2026-05-29 | 2026-05-30 | 1
| De snag all trades -test & commision |  | 2026-06-06 | 2026-06-07 | 1
| De snag all trades -test & commision |  | 2026-06-13 | 2026-06-14 | 1
| De snag all trades -test & commision |  | 2026-06-20 | 2026-06-21 | 1
| De snag all trades -test & commision |  | 2026-06-25 | 2026-06-28 | 2
| Sparkle clean |  | 2025-12-07 | 2025-12-08 | 1
| Sparkle clean |  | 2025-12-14 | 2025-12-15 | 1
| Sparkle clean |  | 2025-12-21 | 2025-12-22 | 1
| Sparkle clean |  | 2025-12-28 | 2025-12-29 | 1
| Sparkle clean |  | 2026-01-05 | 2026-01-06 | 2
| Sparkle clean |  | 2026-01-12 | 2026-01-13 | 2
| Sparkle clean |  | 2026-01-15 | 2026-01-20 | 4
| Sparkle clean |  | 2026-01-26 | 2026-01-27 | 2
| Sparkle clean |  | 2026-02-02 | 2026-02-03 | 2
| Sparkle clean |  | 2026-02-09 | 2026-02-10 | 2
| Sparkle clean |  | 2026-02-16 | 2026-02-17 | 2
| Sparkle clean |  | 2026-02-23 | 2026-02-25 | 3
| Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
| Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
| Sparkle clean |  | 2026-03-20 | 2026-03-28 | 6
| Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
| Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
| Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
| Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
| Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
| Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
| Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
| Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
| Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
| Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
| Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
| Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
| Sparkle clean |  | 2026-06-25 | 2026-06-28 | 2
| Mastic |  | 2025-12-07 | 2025-12-08 | 1
| Mastic |  | 2025-12-14 | 2025-12-15 | 1
| Mastic |  | 2025-12-21 | 2025-12-22 | 1
| Mastic |  | 2025-12-28 | 2025-12-29 | 1
| Mastic |  | 2026-01-05 | 2026-01-06 | 2
| Mastic |  | 2026-01-12 | 2026-01-13 | 2
| Mastic |  | 2026-01-16 | 2026-01-20 | 3
| Mastic |  | 2026-01-26 | 2026-01-27 | 2
| Mastic |  | 2026-02-02 | 2026-02-03 | 2
| Mastic |  | 2026-02-09 | 2026-02-10 | 2
| Mastic |  | 2026-02-16 | 2026-02-17 | 2
| Mastic |  | 2026-02-23 | 2026-02-25 | 3
| Mastic |  | 2026-03-06 | 2026-03-07 | 1
| Mastic |  | 2026-03-13 | 2026-03-14 | 1
| Mastic |  | 2026-03-20 | 2026-03-21 | 1
| Mastic |  | 2026-03-27 | 2026-03-30 | 2
| Mastic |  | 2026-04-04 | 2026-04-05 | 1
| Mastic |  | 2026-04-11 | 2026-04-12 | 1
| Mastic |  | 2026-04-18 | 2026-04-19 | 1
| Mastic |  | 2026-04-25 | 2026-04-26 | 1
| Mastic |  | 2026-05-01 | 2026-05-02 | 1
| Mastic |  | 2026-05-08 | 2026-05-09 | 1
| Mastic |  | 2026-05-15 | 2026-05-16 | 1
| Mastic |  | 2026-05-22 | 2026-05-23 | 1
| Mastic |  | 2026-05-29 | 2026-05-30 | 1
| Mastic |  | 2026-06-06 | 2026-06-07 | 1
| Mastic |  | 2026-06-13 | 2026-06-14 | 1
| Mastic |  | 2026-06-20 | 2026-06-21 | 1
| Mastic |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-15 | 1
| Handover to client |  | 2025-12-21 | 2025-12-22 | 1
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-12 | 2026-01-13 | 2
| Handover to client |  | 2026-01-16 | 2026-01-20 | 3
| Handover to client |  | 2026-01-26 | 2026-01-27 | 2
| Handover to client |  | 2026-02-02 | 2026-02-03 | 2
| Handover to client |  | 2026-02-09 | 2026-02-10 | 2
| Handover to client |  | 2026-02-16 | 2026-02-17 | 2
| Handover to client |  | 2026-02-23 | 2026-02-25 | 3
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-13 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2025-12-07 | 2025-12-08 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2025-12-14 | 2025-12-15 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2025-12-21 | 2025-12-22 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2025-12-28 | 2025-12-29 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-01-05 | 2026-01-06 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-01-12 | 2026-01-13 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-01-19 | 2026-01-20 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-01-26 | 2026-01-27 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-02-02 | 2026-02-03 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-02-09 | 2026-02-10 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-02-16 | 2026-02-17 | 2
| Level 2 Apartment fit out -cluster 1 |  | 2026-02-23 | 2026-02-25 | 3
| Level 2 Apartment fit out -cluster 1 |  | 2026-03-06 | 2026-03-07 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-03-13 | 2026-03-14 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-03-20 | 2026-03-21 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-03-27 | 2026-03-28 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-04-04 | 2026-04-05 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-04-11 | 2026-04-12 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-04-18 | 2026-04-19 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-04-25 | 2026-04-26 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-05-01 | 2026-05-02 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-05-08 | 2026-05-09 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-05-15 | 2026-05-16 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-05-22 | 2026-05-23 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-05-29 | 2026-05-30 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-06-06 | 2026-06-07 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-06-13 | 2026-06-14 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-06-20 | 2026-06-21 | 1
| Level 2 Apartment fit out -cluster 1 |  | 2026-06-25 | 2026-06-28 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2025-12-07 | 2025-12-08 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2025-12-14 | 2025-12-15 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2025-12-21 | 2025-12-22 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2025-12-28 | 2025-12-29 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-01-05 | 2026-01-06 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-01-12 | 2026-01-13 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-01-19 | 2026-01-20 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-01-26 | 2026-01-27 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-02-02 | 2026-02-03 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-02-09 | 2026-02-10 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-02-16 | 2026-02-17 | 2
| kitchen 1st fix,units tops & appliances WREN |  | 2026-02-19 | 2026-02-26 | 6
| kitchen 1st fix,units tops & appliances WREN |  | 2026-03-06 | 2026-03-07 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-03-13 | 2026-03-14 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-03-20 | 2026-03-21 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-03-27 | 2026-03-28 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-04-04 | 2026-04-05 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-04-11 | 2026-04-12 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-04-18 | 2026-04-19 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-04-25 | 2026-04-26 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-05-01 | 2026-05-02 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-05-08 | 2026-05-09 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-05-15 | 2026-05-16 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-05-22 | 2026-05-23 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-05-29 | 2026-05-30 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-06-06 | 2026-06-07 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-06-13 | 2026-06-14 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-06-20 | 2026-06-21 | 1
| kitchen 1st fix,units tops & appliances WREN |  | 2026-06-25 | 2026-06-28 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-08 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-14 | 2025-12-15 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-21 | 2025-12-22 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-28 | 2025-12-29 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-05 | 2026-01-06 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-12 | 2026-01-13 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-19 | 2026-01-20 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-26 | 2026-01-27 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-02 | 2026-02-03 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-09 | 2026-02-17 | 7
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-23 | 2026-02-25 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-06 | 2026-03-07 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-13 | 2026-03-14 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-20 | 2026-03-21 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-27 | 2026-03-28 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-04 | 2026-04-05 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-18 | 2026-04-19 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-25 | 2026-04-26 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-01 | 2026-05-02 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-15 | 2026-05-16 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-22 | 2026-05-23 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-29 | 2026-05-30 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-06 | 2026-06-07 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-13 | 2026-06-14 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-20 | 2026-06-21 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-19 | 2026-01-20 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-26 | 2026-01-27 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-02 | 2026-02-03 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-09 | 2026-02-10 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-16 | 2026-02-17 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-23 | 2026-02-25 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
Water on | Wall & floor tiling JD tiling |  | 2025-12-07 | 2025-12-08 | 1
Water on | Wall & floor tiling JD tiling |  | 2025-12-14 | 2025-12-15 | 1
Water on | Wall & floor tiling JD tiling |  | 2025-12-21 | 2025-12-22 | 1
Water on | Wall & floor tiling JD tiling |  | 2025-12-28 | 2025-12-29 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-01-05 | 2026-01-06 | 2
Water on | Wall & floor tiling JD tiling |  | 2026-01-12 | 2026-01-13 | 2
Water on | Wall & floor tiling JD tiling |  | 2026-01-19 | 2026-01-20 | 2
Water on | Wall & floor tiling JD tiling |  | 2026-01-26 | 2026-01-27 | 2
Water on | Wall & floor tiling JD tiling |  | 2026-02-02 | 2026-02-03 | 2
Water on | Wall & floor tiling JD tiling |  | 2026-02-09 | 2026-02-10 | 2
Water on | Wall & floor tiling JD tiling |  | 2026-02-12 | 2026-02-18 | 5
Water on | Wall & floor tiling JD tiling |  | 2026-02-23 | 2026-02-25 | 3
Water on | Wall & floor tiling JD tiling |  | 2026-03-06 | 2026-03-07 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-03-13 | 2026-03-14 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-03-20 | 2026-03-21 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-03-27 | 2026-03-28 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-04-04 | 2026-04-05 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-04-11 | 2026-04-12 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-04-18 | 2026-04-19 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-04-25 | 2026-04-26 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-05-01 | 2026-05-02 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-05-08 | 2026-05-09 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-05-15 | 2026-05-16 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-05-22 | 2026-05-23 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-05-29 | 2026-05-30 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-06-06 | 2026-06-07 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-06-13 | 2026-06-14 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-06-20 | 2026-06-21 | 1
Water on | Wall & floor tiling JD tiling |  | 2026-06-25 | 2026-06-28 | 2
| Service cupboard board ceiling &finish |  | 2025-12-07 | 2025-12-08 | 1
| Service cupboard board ceiling &finish |  | 2025-12-14 | 2025-12-15 | 1
| Service cupboard board ceiling &finish |  | 2025-12-21 | 2025-12-22 | 1
| Service cupboard board ceiling &finish |  | 2025-12-28 | 2025-12-29 | 1
| Service cupboard board ceiling &finish |  | 2026-01-05 | 2026-01-06 | 2
| Service cupboard board ceiling &finish |  | 2026-01-12 | 2026-01-13 | 2
| Service cupboard board ceiling &finish |  | 2026-01-19 | 2026-01-20 | 2
| Service cupboard board ceiling &finish |  | 2026-01-26 | 2026-01-27 | 2
| Service cupboard board ceiling &finish |  | 2026-02-02 | 2026-02-03 | 2
| Service cupboard board ceiling &finish |  | 2026-02-09 | 2026-02-10 | 2
| Service cupboard board ceiling &finish |  | 2026-02-12 | 2026-02-17 | 4
| Service cupboard board ceiling &finish |  | 2026-02-23 | 2026-02-25 | 3
| Service cupboard board ceiling &finish |  | 2026-03-06 | 2026-03-07 | 1
| Service cupboard board ceiling &finish |  | 2026-03-13 | 2026-03-14 | 1
| Service cupboard board ceiling &finish |  | 2026-03-20 | 2026-03-21 | 1
| Service cupboard board ceiling &finish |  | 2026-03-27 | 2026-03-28 | 1
| Service cupboard board ceiling &finish |  | 2026-04-04 | 2026-04-05 | 1
| Service cupboard board ceiling &finish |  | 2026-04-11 | 2026-04-12 | 1
| Service cupboard board ceiling &finish |  | 2026-04-18 | 2026-04-19 | 1
| Service cupboard board ceiling &finish |  | 2026-04-25 | 2026-04-26 | 1
| Service cupboard board ceiling &finish |  | 2026-05-01 | 2026-05-02 | 1
| Service cupboard board ceiling &finish |  | 2026-05-08 | 2026-05-09 | 1
| Service cupboard board ceiling &finish |  | 2026-05-15 | 2026-05-16 | 1
| Service cupboard board ceiling &finish |  | 2026-05-22 | 2026-05-23 | 1
| Service cupboard board ceiling &finish |  | 2026-05-29 | 2026-05-30 | 1
| Service cupboard board ceiling &finish |  | 2026-06-06 | 2026-06-07 | 1
| Service cupboard board ceiling &finish |  | 2026-06-13 | 2026-06-14 | 1
| Service cupboard board ceiling &finish |  | 2026-06-20 | 2026-06-21 | 1
| Service cupboard board ceiling &finish |  | 2026-06-25 | 2026-06-28 | 2
| service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-08 | 1
| service cupbaord -plywood flooring |  | 2025-12-14 | 2025-12-15 | 1
| service cupbaord -plywood flooring |  | 2025-12-21 | 2025-12-22 | 1
| service cupbaord -plywood flooring |  | 2025-12-28 | 2025-12-29 | 1
| service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-06 | 2
| service cupbaord -plywood flooring |  | 2026-01-12 | 2026-01-13 | 2
| service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-20 | 2
| service cupbaord -plywood flooring |  | 2026-01-26 | 2026-01-27 | 2
| service cupbaord -plywood flooring |  | 2026-02-02 | 2026-02-03 | 2
| service cupbaord -plywood flooring |  | 2026-02-09 | 2026-02-10 | 2
| service cupbaord -plywood flooring |  | 2026-02-14 | 2026-02-17 | 2
| service cupbaord -plywood flooring |  | 2026-02-23 | 2026-02-25 | 3
| service cupbaord -plywood flooring |  | 2026-03-06 | 2026-03-07 | 1
| service cupbaord -plywood flooring |  | 2026-03-13 | 2026-03-14 | 1
| service cupbaord -plywood flooring |  | 2026-03-20 | 2026-03-21 | 1
| service cupbaord -plywood flooring |  | 2026-03-27 | 2026-03-28 | 1
| service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
| service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
| service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
| service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
| service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
| service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
| service cupbaord -plywood flooring |  | 2026-05-15 | 2026-05-16 | 1
| service cupbaord -plywood flooring |  | 2026-05-22 | 2026-05-23 | 1
| service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
| service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
| service cupbaord -plywood flooring |  | 2026-06-13 | 2026-06-14 | 1
| service cupbaord -plywood flooring |  | 2026-06-20 | 2026-06-21 | 1
| service cupbaord -plywood flooring |  | 2026-06-25 | 2026-06-28 | 2
| service cupboard decoration |  | 2025-12-07 | 2025-12-08 | 1
| service cupboard decoration |  | 2025-12-14 | 2025-12-15 | 1
| service cupboard decoration |  | 2025-12-21 | 2025-12-22 | 1
| service cupboard decoration |  | 2025-12-28 | 2025-12-29 | 1
| service cupboard decoration |  | 2026-01-05 | 2026-01-06 | 2
| service cupboard decoration |  | 2026-01-12 | 2026-01-13 | 2
| service cupboard decoration |  | 2026-01-19 | 2026-01-20 | 2
| service cupboard decoration |  | 2026-01-26 | 2026-01-27 | 2
| service cupboard decoration |  | 2026-02-02 | 2026-02-03 | 2
| service cupboard decoration |  | 2026-02-09 | 2026-02-10 | 2
| service cupboard decoration |  | 2026-02-15 | 2026-02-17 | 2
| service cupboard decoration |  | 2026-02-23 | 2026-02-25 | 3
| service cupboard decoration |  | 2026-03-06 | 2026-03-07 | 1
| service cupboard decoration |  | 2026-03-13 | 2026-03-14 | 1
| service cupboard decoration |  | 2026-03-20 | 2026-03-21 | 1
| service cupboard decoration |  | 2026-03-27 | 2026-03-28 | 1
| service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
| service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
| service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
| service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
| service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
| service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
| service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
| service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
| service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
| service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
| service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
| service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
| service cupboard decoration |  | 2026-06-25 | 2026-06-28 | 2
28 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
28 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
28 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
28 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
28 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
28 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
28 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
28 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
28 | PANACEA |  | 2026-02-02 | 2026-02-03 | 2
28 | PANACEA |  | 2026-02-09 | 2026-02-10 | 2
28 | PANACEA |  | 2026-02-16 | 2026-02-17 | 2
28 | PANACEA |  | 2026-02-23 | 2026-02-25 | 3
28 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
28 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
28 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
28 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
28 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
28 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
28 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
28 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
28 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
28 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
28 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
28 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
28 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
28 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
28 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
28 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
28 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-20 | 2
| Amtico flooring /Bathrooms |  | 2026-01-26 | 2026-01-27 | 2
| Amtico flooring /Bathrooms |  | 2026-02-02 | 2026-02-03 | 2
| Amtico flooring /Bathrooms |  | 2026-02-09 | 2026-02-10 | 2
| Amtico flooring /Bathrooms |  | 2026-02-16 | 2026-02-17 | 2
| Amtico flooring /Bathrooms |  | 2026-02-21 | 2026-02-28 | 5
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
29 | Edencroft |  | 2025-12-07 | 2025-12-08 | 1
29 | Edencroft |  | 2025-12-14 | 2025-12-15 | 1
29 | Edencroft |  | 2025-12-21 | 2025-12-22 | 1
29 | Edencroft |  | 2025-12-28 | 2025-12-29 | 1
29 | Edencroft |  | 2026-01-05 | 2026-01-06 | 2
29 | Edencroft |  | 2026-01-12 | 2026-01-13 | 2
29 | Edencroft |  | 2026-01-19 | 2026-01-20 | 2
29 | Edencroft |  | 2026-01-26 | 2026-01-27 | 2
29 | Edencroft |  | 2026-02-02 | 2026-02-03 | 2
29 | Edencroft |  | 2026-02-09 | 2026-02-10 | 2
29 | Edencroft |  | 2026-02-16 | 2026-02-17 | 2
29 | Edencroft |  | 2026-02-23 | 2026-02-25 | 3
29 | Edencroft |  | 2026-02-28 | 2026-03-03 | 2
29 | Edencroft |  | 2026-03-06 | 2026-03-07 | 1
29 | Edencroft |  | 2026-03-13 | 2026-03-14 | 1
29 | Edencroft |  | 2026-03-20 | 2026-03-21 | 1
29 | Edencroft |  | 2026-03-27 | 2026-03-28 | 1
29 | Edencroft |  | 2026-04-04 | 2026-04-05 | 1
29 | Edencroft |  | 2026-04-11 | 2026-04-12 | 1
29 | Edencroft |  | 2026-04-18 | 2026-04-19 | 1
29 | Edencroft |  | 2026-04-25 | 2026-04-26 | 1
29 | Edencroft |  | 2026-05-01 | 2026-05-02 | 1
29 | Edencroft |  | 2026-05-08 | 2026-05-09 | 1
29 | Edencroft |  | 2026-05-15 | 2026-05-16 | 1
29 | Edencroft |  | 2026-05-22 | 2026-05-23 | 1
29 | Edencroft |  | 2026-05-29 | 2026-05-30 | 1
29 | Edencroft |  | 2026-06-06 | 2026-06-07 | 1
29 | Edencroft |  | 2026-06-13 | 2026-06-14 | 1
29 | Edencroft |  | 2026-06-20 | 2026-06-21 | 1
29 | Edencroft |  | 2026-06-25 | 2026-06-28 | 2
30 | GPL |  | 2025-12-07 | 2025-12-08 | 1
30 | GPL |  | 2025-12-14 | 2025-12-15 | 1
30 | GPL |  | 2025-12-21 | 2025-12-22 | 1
30 | GPL |  | 2025-12-28 | 2025-12-29 | 1
30 | GPL |  | 2026-01-05 | 2026-01-06 | 2
30 | GPL |  | 2026-01-12 | 2026-01-13 | 2
30 | GPL |  | 2026-01-19 | 2026-01-20 | 2
30 | GPL |  | 2026-01-26 | 2026-01-27 | 2
30 | GPL |  | 2026-02-02 | 2026-02-03 | 2
30 | GPL |  | 2026-02-09 | 2026-02-10 | 2
30 | GPL |  | 2026-02-16 | 2026-02-17 | 2
30 | GPL |  | 2026-02-23 | 2026-02-25 | 3
30 | GPL |  | 2026-03-04 | 2026-03-10 | 5
30 | GPL |  | 2026-03-13 | 2026-03-14 | 1
30 | GPL |  | 2026-03-20 | 2026-03-21 | 1
30 | GPL |  | 2026-03-27 | 2026-03-28 | 1
30 | GPL |  | 2026-04-04 | 2026-04-05 | 1
30 | GPL |  | 2026-04-11 | 2026-04-12 | 1
30 | GPL |  | 2026-04-18 | 2026-04-19 | 1
30 | GPL |  | 2026-04-25 | 2026-04-26 | 1
30 | GPL |  | 2026-05-01 | 2026-05-02 | 1
30 | GPL |  | 2026-05-08 | 2026-05-09 | 1
30 | GPL |  | 2026-05-15 | 2026-05-16 | 1
30 | GPL |  | 2026-05-22 | 2026-05-23 | 1
30 | GPL |  | 2026-05-29 | 2026-05-30 | 1
30 | GPL |  | 2026-06-06 | 2026-06-07 | 1
30 | GPL |  | 2026-06-13 | 2026-06-14 | 1
30 | GPL |  | 2026-06-20 | 2026-06-21 | 1
30 | GPL |  | 2026-06-25 | 2026-06-28 | 2
| Power on |  | 2025-12-07 | 2025-12-08 | 1
| Power on |  | 2025-12-14 | 2025-12-15 | 1
| Power on |  | 2025-12-21 | 2025-12-22 | 1
| Power on |  | 2025-12-28 | 2025-12-29 | 1
| Power on |  | 2026-01-05 | 2026-01-06 | 2
| Power on |  | 2026-01-12 | 2026-01-13 | 2
| Power on |  | 2026-01-19 | 2026-01-20 | 2
| Power on |  | 2026-01-26 | 2026-01-27 | 2
| Power on |  | 2026-02-02 | 2026-02-03 | 2
| Power on |  | 2026-02-09 | 2026-02-10 | 2
| Power on |  | 2026-02-16 | 2026-02-17 | 2
| Power on |  | 2026-02-23 | 2026-02-25 | 3
| Power on |  | 2026-03-06 | 2026-03-07 | 1
| Power on |  | 2026-03-13 | 2026-03-14 | 1
| Power on |  | 2026-03-20 | 2026-03-21 | 1
| Power on |  | 2026-03-27 | 2026-03-28 | 1
| Power on |  | 2026-04-04 | 2026-04-05 | 1
| Power on |  | 2026-04-11 | 2026-04-12 | 1
| Power on |  | 2026-04-18 | 2026-04-19 | 1
| Power on |  | 2026-04-25 | 2026-04-26 | 1
| Power on |  | 2026-05-01 | 2026-05-02 | 1
| Power on |  | 2026-05-08 | 2026-05-09 | 1
| Power on |  | 2026-05-15 | 2026-05-16 | 1
| Power on |  | 2026-05-22 | 2026-05-23 | 1
| Power on |  | 2026-05-29 | 2026-05-30 | 1
| Power on |  | 2026-06-06 | 2026-06-07 | 1
| Power on |  | 2026-06-13 | 2026-06-14 | 1
| Power on |  | 2026-06-20 | 2026-06-21 | 1
| Power on |  | 2026-06-25 | 2026-06-28 | 2
| Water on |  | 2025-12-07 | 2025-12-08 | 1
| Water on |  | 2025-12-14 | 2025-12-15 | 1
| Water on |  | 2025-12-21 | 2025-12-22 | 1
| Water on |  | 2025-12-28 | 2025-12-29 | 1
| Water on |  | 2026-01-05 | 2026-01-06 | 2
| Water on |  | 2026-01-12 | 2026-01-13 | 2
| Water on |  | 2026-01-19 | 2026-01-20 | 2
| Water on |  | 2026-01-26 | 2026-01-27 | 2
| Water on |  | 2026-02-02 | 2026-02-03 | 2
| Water on |  | 2026-02-09 | 2026-02-10 | 2
| Water on |  | 2026-02-16 | 2026-02-17 | 2
| Water on |  | 2026-02-23 | 2026-02-25 | 3
| Water on |  | 2026-03-06 | 2026-03-07 | 1
| Water on |  | 2026-03-13 | 2026-03-14 | 1
| Water on |  | 2026-03-20 | 2026-03-21 | 1
| Water on |  | 2026-03-27 | 2026-03-28 | 1
| Water on |  | 2026-04-04 | 2026-04-05 | 1
| Water on |  | 2026-04-11 | 2026-04-12 | 1
| Water on |  | 2026-04-18 | 2026-04-19 | 1
| Water on |  | 2026-04-25 | 2026-04-26 | 1
| Water on |  | 2026-05-01 | 2026-05-02 | 1
| Water on |  | 2026-05-08 | 2026-05-09 | 1
| Water on |  | 2026-05-15 | 2026-05-16 | 1
| Water on |  | 2026-05-22 | 2026-05-23 | 1
| Water on |  | 2026-05-29 | 2026-05-30 | 1
| Water on |  | 2026-06-06 | 2026-06-07 | 1
| Water on |  | 2026-06-13 | 2026-06-14 | 1
| Water on |  | 2026-06-20 | 2026-06-21 | 1
| Water on |  | 2026-06-25 | 2026-06-28 | 2
31 | Armstrong |  | 2025-12-07 | 2025-12-08 | 1
31 | Armstrong |  | 2025-12-14 | 2025-12-15 | 1
31 | Armstrong |  | 2025-12-21 | 2025-12-22 | 1
31 | Armstrong |  | 2025-12-28 | 2025-12-29 | 1
31 | Armstrong |  | 2026-01-05 | 2026-01-06 | 2
31 | Armstrong |  | 2026-01-12 | 2026-01-13 | 2
31 | Armstrong |  | 2026-01-19 | 2026-01-20 | 2
31 | Armstrong |  | 2026-01-26 | 2026-01-27 | 2
31 | Armstrong |  | 2026-02-02 | 2026-02-03 | 2
31 | Armstrong |  | 2026-02-09 | 2026-02-10 | 2
31 | Armstrong |  | 2026-02-16 | 2026-02-17 | 2
31 | Armstrong |  | 2026-02-23 | 2026-02-25 | 3
31 | Armstrong |  | 2026-03-06 | 2026-03-07 | 1
31 | Armstrong |  | 2026-03-13 | 2026-03-14 | 1
31 | Armstrong |  | 2026-03-20 | 2026-03-21 | 1
31 | Armstrong |  | 2026-03-27 | 2026-03-28 | 1
31 | Armstrong |  | 2026-04-04 | 2026-04-05 | 1
31 | Armstrong |  | 2026-04-11 | 2026-04-12 | 1
31 | Armstrong |  | 2026-04-18 | 2026-04-19 | 1
31 | Armstrong |  | 2026-04-25 | 2026-04-26 | 1
31 | Armstrong |  | 2026-05-01 | 2026-05-02 | 1
31 | Armstrong |  | 2026-05-08 | 2026-05-09 | 1
31 | Armstrong |  | 2026-05-15 | 2026-05-16 | 1
31 | Armstrong |  | 2026-05-22 | 2026-05-23 | 1
31 | Armstrong |  | 2026-05-29 | 2026-05-30 | 1
31 | Armstrong |  | 2026-06-06 | 2026-06-07 | 1
31 | Armstrong |  | 2026-06-13 | 2026-06-14 | 1
31 | Armstrong |  | 2026-06-20 | 2026-06-21 | 1
31 | Armstrong |  | 2026-06-25 | 2026-06-28 | 2
32 | Pre -dec -snagging |  | 2025-12-07 | 2025-12-08 | 1
32 | Pre -dec -snagging |  | 2025-12-14 | 2025-12-15 | 1
32 | Pre -dec -snagging |  | 2025-12-21 | 2025-12-22 | 1
32 | Pre -dec -snagging |  | 2025-12-28 | 2025-12-29 | 1
32 | Pre -dec -snagging |  | 2026-01-05 | 2026-01-06 | 2
32 | Pre -dec -snagging |  | 2026-01-12 | 2026-01-13 | 2
32 | Pre -dec -snagging |  | 2026-01-19 | 2026-01-20 | 2
32 | Pre -dec -snagging |  | 2026-01-26 | 2026-01-27 | 2
32 | Pre -dec -snagging |  | 2026-02-02 | 2026-02-03 | 2
32 | Pre -dec -snagging |  | 2026-02-09 | 2026-02-10 | 2
32 | Pre -dec -snagging |  | 2026-02-16 | 2026-02-17 | 2
32 | Pre -dec -snagging |  | 2026-02-23 | 2026-02-25 | 3
32 | Pre -dec -snagging |  | 2026-03-06 | 2026-03-07 | 1
32 | Pre -dec -snagging |  | 2026-03-13 | 2026-03-14 | 1
32 | Pre -dec -snagging |  | 2026-03-20 | 2026-03-21 | 1
32 | Pre -dec -snagging |  | 2026-03-27 | 2026-03-28 | 1
32 | Pre -dec -snagging |  | 2026-04-04 | 2026-04-05 | 1
32 | Pre -dec -snagging |  | 2026-04-11 | 2026-04-12 | 1
32 | Pre -dec -snagging |  | 2026-04-18 | 2026-04-19 | 1
32 | Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
32 | Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
32 | Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
32 | Pre -dec -snagging |  | 2026-05-15 | 2026-05-16 | 1
32 | Pre -dec -snagging |  | 2026-05-22 | 2026-05-23 | 1
32 | Pre -dec -snagging |  | 2026-05-29 | 2026-05-30 | 1
32 | Pre -dec -snagging |  | 2026-06-06 | 2026-06-07 | 1
32 | Pre -dec -snagging |  | 2026-06-13 | 2026-06-14 | 1
32 | Pre -dec -snagging |  | 2026-06-20 | 2026-06-21 | 1
32 | Pre -dec -snagging |  | 2026-06-25 | 2026-06-28 | 2
33 | MCL |  | 2025-12-07 | 2025-12-08 | 1
33 | MCL |  | 2025-12-14 | 2025-12-15 | 1
33 | MCL |  | 2025-12-21 | 2025-12-22 | 1
33 | MCL |  | 2025-12-28 | 2025-12-29 | 1
33 | MCL |  | 2026-01-05 | 2026-01-06 | 2
33 | MCL |  | 2026-01-12 | 2026-01-13 | 2
33 | MCL |  | 2026-01-19 | 2026-01-20 | 2
33 | MCL |  | 2026-01-26 | 2026-01-27 | 2
33 | MCL |  | 2026-02-02 | 2026-02-03 | 2
33 | MCL |  | 2026-02-09 | 2026-02-10 | 2
33 | MCL |  | 2026-02-16 | 2026-02-17 | 2
33 | MCL |  | 2026-02-23 | 2026-02-25 | 3
33 | MCL |  | 2026-03-06 | 2026-03-07 | 1
33 | MCL |  | 2026-03-10 | 2026-03-16 | 5
33 | MCL |  | 2026-03-20 | 2026-03-21 | 1
33 | MCL |  | 2026-03-27 | 2026-03-28 | 1
33 | MCL |  | 2026-04-04 | 2026-04-05 | 1
33 | MCL |  | 2026-04-11 | 2026-04-12 | 1
33 | MCL |  | 2026-04-18 | 2026-04-19 | 1
33 | MCL |  | 2026-04-25 | 2026-04-26 | 1
33 | MCL |  | 2026-05-01 | 2026-05-02 | 1
33 | MCL |  | 2026-05-08 | 2026-05-09 | 1
33 | MCL |  | 2026-05-15 | 2026-05-16 | 1
33 | MCL |  | 2026-05-22 | 2026-05-23 | 1
33 | MCL |  | 2026-05-29 | 2026-05-30 | 1
33 | MCL |  | 2026-06-06 | 2026-06-07 | 1
33 | MCL |  | 2026-06-13 | 2026-06-14 | 1
33 | MCL |  | 2026-06-20 | 2026-06-21 | 1
33 | MCL |  | 2026-06-25 | 2026-06-28 | 2
34 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
34 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
34 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
34 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
34 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
34 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
34 | PANACEA |  | 2026-01-17 | 2026-01-23 | 5
34 | PANACEA |  | 2026-01-26 | 2026-01-27 | 2
34 | PANACEA |  | 2026-02-02 | 2026-02-04 | 3
34 | PANACEA |  | 2026-02-09 | 2026-02-10 | 2
34 | PANACEA |  | 2026-02-16 | 2026-02-17 | 2
34 | PANACEA |  | 2026-02-23 | 2026-02-25 | 3
34 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
34 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
34 | PANACEA |  | 2026-03-16 | 2026-03-21 | 5
34 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
34 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
34 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
34 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
34 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
34 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
34 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
34 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
34 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
34 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
34 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
34 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
34 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
34 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
35 | TECL |  | 2025-12-07 | 2025-12-08 | 1
35 | TECL |  | 2025-12-14 | 2025-12-19 | 5
35 | TECL |  | 2025-12-21 | 2025-12-22 | 1
35 | TECL |  | 2025-12-28 | 2025-12-29 | 1
35 | TECL |  | 2026-01-05 | 2026-01-06 | 2
35 | TECL |  | 2026-01-12 | 2026-01-13 | 2
35 | TECL |  | 2026-01-17 | 2026-01-23 | 5
35 | TECL |  | 2026-01-26 | 2026-01-27 | 2
35 | TECL |  | 2026-02-02 | 2026-02-04 | 3
35 | TECL |  | 2026-02-09 | 2026-02-10 | 2
35 | TECL |  | 2026-02-16 | 2026-02-17 | 2
35 | TECL |  | 2026-02-23 | 2026-02-25 | 3
35 | TECL |  | 2026-03-06 | 2026-03-07 | 1
35 | TECL |  | 2026-03-13 | 2026-03-14 | 1
35 | TECL |  | 2026-03-20 | 2026-03-28 | 6
35 | TECL |  | 2026-04-04 | 2026-04-05 | 1
35 | TECL |  | 2026-04-11 | 2026-04-12 | 1
35 | TECL |  | 2026-04-18 | 2026-04-19 | 1
35 | TECL |  | 2026-04-25 | 2026-04-26 | 1
35 | TECL |  | 2026-05-01 | 2026-05-02 | 1
35 | TECL |  | 2026-05-08 | 2026-05-09 | 1
35 | TECL |  | 2026-05-15 | 2026-05-16 | 1
35 | TECL |  | 2026-05-22 | 2026-05-23 | 1
35 | TECL |  | 2026-05-29 | 2026-05-30 | 1
35 | TECL |  | 2026-06-06 | 2026-06-07 | 1
35 | TECL |  | 2026-06-13 | 2026-06-14 | 1
35 | TECL |  | 2026-06-20 | 2026-06-21 | 1
35 | TECL |  | 2026-06-25 | 2026-06-28 | 2
36 | Sparkle clean |  | 2025-12-07 | 2025-12-08 | 1
36 | Sparkle clean |  | 2025-12-13 | 2025-12-15 | 1
36 | Sparkle clean |  | 2025-12-20 | 2025-12-22 | 1
36 | Sparkle clean |  | 2025-12-26 | 2025-12-29 | 2
36 | Sparkle clean |  | 2026-01-03 | 2026-01-06 | 2
36 | Sparkle clean |  | 2026-01-10 | 2026-01-13 | 2
36 | Sparkle clean |  | 2026-01-16 | 2026-01-22 | 5
36 | Sparkle clean |  | 2026-01-24 | 2026-01-27 | 2
36 | Sparkle clean |  | 2026-01-30 | 2026-02-04 | 4
36 | Sparkle clean |  | 2026-02-06 | 2026-02-10 | 3
36 | Sparkle clean |  | 2026-02-15 | 2026-02-17 | 2
36 | Sparkle clean |  | 2026-02-23 | 2026-02-25 | 3
36 | Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
36 | Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
36 | Sparkle clean |  | 2026-03-20 | 2026-03-21 | 1
36 | Sparkle clean |  | 2026-03-27 | 2026-04-05 | 6
36 | Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
36 | Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
36 | Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
36 | Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
36 | Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
36 | Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
36 | Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
36 | Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
36 | Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
36 | Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
36 | Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
36 | Sparkle clean |  | 2026-06-25 | 2026-06-28 | 2
37 | MCL |  | 2025-12-07 | 2025-12-08 | 1
37 | MCL |  | 2025-12-13 | 2025-12-15 | 1
37 | MCL |  | 2025-12-20 | 2025-12-22 | 1
37 | MCL |  | 2025-12-26 | 2025-12-29 | 2
37 | MCL |  | 2026-01-03 | 2026-01-06 | 2
37 | MCL |  | 2026-01-10 | 2026-01-13 | 2
37 | MCL |  | 2026-01-16 | 2026-01-22 | 5
37 | MCL |  | 2026-01-24 | 2026-01-27 | 2
37 | MCL |  | 2026-01-30 | 2026-02-04 | 4
37 | MCL |  | 2026-02-06 | 2026-02-10 | 3
37 | MCL |  | 2026-02-15 | 2026-02-17 | 2
37 | MCL |  | 2026-02-23 | 2026-02-25 | 3
37 | MCL |  | 2026-03-06 | 2026-03-07 | 1
37 | MCL |  | 2026-03-13 | 2026-03-14 | 1
37 | MCL |  | 2026-03-20 | 2026-03-21 | 1
37 | MCL |  | 2026-03-27 | 2026-03-28 | 1
37 | MCL |  | 2026-04-04 | 2026-04-07 | 2
37 | MCL |  | 2026-04-11 | 2026-04-12 | 1
37 | MCL |  | 2026-04-18 | 2026-04-19 | 1
37 | MCL |  | 2026-04-25 | 2026-04-26 | 1
37 | MCL |  | 2026-05-01 | 2026-05-02 | 1
37 | MCL |  | 2026-05-08 | 2026-05-09 | 1
37 | MCL |  | 2026-05-15 | 2026-05-16 | 1
37 | MCL |  | 2026-05-22 | 2026-05-23 | 1
37 | MCL |  | 2026-05-29 | 2026-05-30 | 1
37 | MCL |  | 2026-06-06 | 2026-06-07 | 1
37 | MCL |  | 2026-06-13 | 2026-06-14 | 1
37 | MCL |  | 2026-06-20 | 2026-06-21 | 1
37 | MCL |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-13 | 2025-12-15 | 1
| Handover to client |  | 2025-12-20 | 2025-12-22 | 1
| Handover to client |  | 2025-12-26 | 2025-12-29 | 2
| Handover to client |  | 2026-01-03 | 2026-01-06 | 2
| Handover to client |  | 2026-01-10 | 2026-01-13 | 2
| Handover to client |  | 2026-01-16 | 2026-01-22 | 5
| Handover to client |  | 2026-01-24 | 2026-01-27 | 2
| Handover to client |  | 2026-01-30 | 2026-02-04 | 4
| Handover to client |  | 2026-02-06 | 2026-02-10 | 3
| Handover to client |  | 2026-02-15 | 2026-02-17 | 2
| Handover to client |  | 2026-02-23 | 2026-02-25 | 3
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
38 | Armstrong |  | 2025-12-07 | 2025-12-08 | 1
38 | Armstrong |  | 2025-12-13 | 2025-12-15 | 1
38 | Armstrong |  | 2025-12-17 | 2025-12-22 | 4
38 | Armstrong |  | 2025-12-26 | 2025-12-29 | 2
38 | Armstrong |  | 2026-01-03 | 2026-01-06 | 2
38 | Armstrong |  | 2026-01-10 | 2026-01-13 | 2
38 | Armstrong |  | 2026-01-16 | 2026-01-22 | 5
38 | Armstrong |  | 2026-01-24 | 2026-01-27 | 2
38 | Armstrong |  | 2026-01-30 | 2026-02-04 | 4
38 | Armstrong |  | 2026-02-06 | 2026-02-10 | 3
38 | Armstrong |  | 2026-02-15 | 2026-02-17 | 2
38 | Armstrong |  | 2026-02-23 | 2026-02-25 | 3
38 | Armstrong |  | 2026-03-06 | 2026-03-07 | 1
38 | Armstrong |  | 2026-03-13 | 2026-03-14 | 1
38 | Armstrong |  | 2026-03-20 | 2026-03-21 | 1
38 | Armstrong |  | 2026-03-27 | 2026-03-28 | 1
38 | Armstrong |  | 2026-04-04 | 2026-04-05 | 1
38 | Armstrong |  | 2026-04-11 | 2026-04-12 | 1
38 | Armstrong |  | 2026-04-18 | 2026-04-20 | 1
38 | Armstrong |  | 2026-04-25 | 2026-04-26 | 1
38 | Armstrong |  | 2026-05-01 | 2026-05-02 | 1
38 | Armstrong |  | 2026-05-08 | 2026-05-09 | 1
38 | Armstrong |  | 2026-05-15 | 2026-05-16 | 1
38 | Armstrong |  | 2026-05-22 | 2026-05-23 | 1
38 | Armstrong |  | 2026-05-29 | 2026-05-30 | 1
38 | Armstrong |  | 2026-06-06 | 2026-06-07 | 1
38 | Armstrong |  | 2026-06-13 | 2026-06-14 | 1
38 | Armstrong |  | 2026-06-20 | 2026-06-21 | 1
38 | Armstrong |  | 2026-06-25 | 2026-06-28 | 2
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-08 | 1
| Vanity 1st fix framing |  | 2025-12-13 | 2025-12-15 | 1
| Vanity 1st fix framing |  | 2025-12-17 | 2025-12-22 | 4
| Vanity 1st fix framing |  | 2025-12-26 | 2025-12-29 | 2
| Vanity 1st fix framing |  | 2026-01-03 | 2026-01-06 | 2
| Vanity 1st fix framing |  | 2026-01-10 | 2026-01-13 | 2
| Vanity 1st fix framing |  | 2026-01-16 | 2026-01-22 | 5
| Vanity 1st fix framing |  | 2026-01-24 | 2026-01-27 | 2
| Vanity 1st fix framing |  | 2026-01-30 | 2026-02-04 | 4
| Vanity 1st fix framing |  | 2026-02-06 | 2026-02-10 | 3
| Vanity 1st fix framing |  | 2026-02-15 | 2026-02-17 | 2
| Vanity 1st fix framing |  | 2026-02-23 | 2026-02-25 | 3
| Vanity 1st fix framing |  | 2026-03-06 | 2026-03-07 | 1
| Vanity 1st fix framing |  | 2026-03-13 | 2026-03-14 | 1
| Vanity 1st fix framing |  | 2026-03-20 | 2026-03-21 | 1
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2026-06-25 | 2026-06-28 | 2
39 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
39 | PANACEA |  | 2025-12-10 | 2025-12-15 | 4
39 | PANACEA |  | 2025-12-20 | 2025-12-22 | 1
39 | PANACEA |  | 2025-12-26 | 2025-12-29 | 2
39 | PANACEA |  | 2026-01-03 | 2026-01-06 | 2
39 | PANACEA |  | 2026-01-10 | 2026-01-13 | 2
39 | PANACEA |  | 2026-01-16 | 2026-01-22 | 5
39 | PANACEA |  | 2026-01-24 | 2026-01-27 | 2
39 | PANACEA |  | 2026-01-30 | 2026-02-04 | 4
39 | PANACEA |  | 2026-02-06 | 2026-02-10 | 3
39 | PANACEA |  | 2026-02-15 | 2026-02-17 | 2
39 | PANACEA |  | 2026-02-22 | 2026-03-01 | 5
39 | PANACEA |  | 2026-03-05 | 2026-03-07 | 2
39 | PANACEA |  | 2026-03-12 | 2026-03-14 | 2
39 | PANACEA |  | 2026-03-18 | 2026-03-21 | 3
39 | PANACEA |  | 2026-03-25 | 2026-03-28 | 3
39 | PANACEA |  | 2026-04-02 | 2026-04-05 | 2
39 | PANACEA |  | 2026-04-08 | 2026-04-09 | 2
39 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
39 | PANACEA |  | 2026-04-14 | 2026-04-14 | 1
39 | PANACEA |  | 2026-04-16 | 2026-04-19 | 2
39 | PANACEA |  | 2026-04-22 | 2026-04-26 | 3
39 | PANACEA |  | 2026-04-29 | 2026-05-02 | 3
39 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
39 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
39 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
39 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
39 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
39 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
39 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
39 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-08 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-10 | 2025-12-15 | 4
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-20 | 2025-12-29 | 6
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-03 | 2026-01-06 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-10 | 2026-01-13 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-16 | 2026-01-22 | 5
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-24 | 2026-01-27 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-30 | 2026-02-04 | 4
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-06 | 2026-02-10 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-15 | 2026-02-25 | 8
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-05 | 2026-03-07 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-12 | 2026-03-14 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-18 | 2026-03-21 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-25 | 2026-03-28 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-02 | 2026-04-05 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-08 | 2026-04-09 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-14 | 2026-04-14 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-16 | 2026-04-19 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-22 | 2026-04-26 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-29 | 2026-05-02 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-15 | 2026-05-16 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-22 | 2026-05-23 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-29 | 2026-05-30 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-06 | 2026-06-07 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-13 | 2026-06-14 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-20 | 2026-06-21 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-10 | 2025-12-15 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-20 | 2025-12-29 | 6
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-03 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-10 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-16 | 2026-01-22 | 5
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-24 | 2026-01-27 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-30 | 2026-02-04 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-06 | 2026-02-10 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-15 | 2026-02-25 | 8
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-05 | 2026-03-07 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-12 | 2026-03-14 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-18 | 2026-03-21 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-25 | 2026-03-28 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-02 | 2026-04-05 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-08 | 2026-04-09 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-14 | 2026-04-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-16 | 2026-04-19 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-22 | 2026-04-26 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-29 | 2026-05-02 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
40 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
40 | PANACEA |  | 2025-12-10 | 2025-12-15 | 4
40 | PANACEA |  | 2025-12-20 | 2025-12-22 | 1
40 | PANACEA |  | 2025-12-26 | 2026-01-13 | 13
40 | PANACEA |  | 2026-01-16 | 2026-01-22 | 5
40 | PANACEA |  | 2026-01-24 | 2026-01-27 | 2
40 | PANACEA |  | 2026-01-30 | 2026-02-04 | 4
40 | PANACEA |  | 2026-02-06 | 2026-02-10 | 3
40 | PANACEA |  | 2026-02-14 | 2026-02-25 | 8
40 | PANACEA |  | 2026-03-05 | 2026-03-07 | 2
40 | PANACEA |  | 2026-03-12 | 2026-03-14 | 2
40 | PANACEA |  | 2026-03-18 | 2026-03-21 | 3
40 | PANACEA |  | 2026-03-25 | 2026-03-28 | 3
40 | PANACEA |  | 2026-04-02 | 2026-04-05 | 2
40 | PANACEA |  | 2026-04-08 | 2026-04-09 | 2
40 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
40 | PANACEA |  | 2026-04-14 | 2026-04-14 | 1
40 | PANACEA |  | 2026-04-16 | 2026-04-19 | 2
40 | PANACEA |  | 2026-04-22 | 2026-04-26 | 3
40 | PANACEA |  | 2026-04-29 | 2026-05-02 | 3
40 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
40 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
40 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
40 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
40 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
40 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
40 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
40 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Service cupboard board ceiling &finish |  | 2025-12-07 | 2025-12-08 | 1
| Service cupboard board ceiling &finish |  | 2025-12-10 | 2025-12-15 | 4
| Service cupboard board ceiling &finish |  | 2025-12-20 | 2025-12-22 | 1
| Service cupboard board ceiling &finish |  | 2025-12-26 | 2026-01-13 | 13
| Service cupboard board ceiling &finish |  | 2026-01-16 | 2026-01-22 | 5
| Service cupboard board ceiling &finish |  | 2026-01-24 | 2026-01-27 | 2
| Service cupboard board ceiling &finish |  | 2026-01-30 | 2026-02-04 | 4
| Service cupboard board ceiling &finish |  | 2026-02-06 | 2026-02-10 | 3
| Service cupboard board ceiling &finish |  | 2026-02-15 | 2026-02-25 | 8
| Service cupboard board ceiling &finish |  | 2026-03-05 | 2026-03-07 | 2
| Service cupboard board ceiling &finish |  | 2026-03-12 | 2026-03-14 | 2
| Service cupboard board ceiling &finish |  | 2026-03-18 | 2026-03-21 | 3
| Service cupboard board ceiling &finish |  | 2026-03-25 | 2026-03-28 | 3
| Service cupboard board ceiling &finish |  | 2026-04-02 | 2026-04-05 | 2
| Service cupboard board ceiling &finish |  | 2026-04-08 | 2026-04-09 | 2
| Service cupboard board ceiling &finish |  | 2026-04-11 | 2026-04-12 | 1
| Service cupboard board ceiling &finish |  | 2026-04-14 | 2026-04-14 | 1
| Service cupboard board ceiling &finish |  | 2026-04-16 | 2026-04-19 | 2
| Service cupboard board ceiling &finish |  | 2026-04-22 | 2026-04-26 | 3
| Service cupboard board ceiling &finish |  | 2026-04-29 | 2026-05-02 | 3
| Service cupboard board ceiling &finish |  | 2026-05-08 | 2026-05-09 | 1
| Service cupboard board ceiling &finish |  | 2026-05-15 | 2026-05-16 | 1
| Service cupboard board ceiling &finish |  | 2026-05-22 | 2026-05-23 | 1
| Service cupboard board ceiling &finish |  | 2026-05-29 | 2026-05-30 | 1
| Service cupboard board ceiling &finish |  | 2026-06-06 | 2026-06-07 | 1
| Service cupboard board ceiling &finish |  | 2026-06-13 | 2026-06-14 | 1
| Service cupboard board ceiling &finish |  | 2026-06-20 | 2026-06-21 | 1
| Service cupboard board ceiling &finish |  | 2026-06-25 | 2026-06-28 | 2
41 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
41 | Active flooring |  | 2025-12-10 | 2025-12-15 | 4
41 | Active flooring |  | 2025-12-20 | 2025-12-22 | 1
41 | Active flooring |  | 2025-12-26 | 2025-12-29 | 2
41 | Active flooring |  | 2026-01-03 | 2026-01-06 | 2
41 | Active flooring |  | 2026-01-10 | 2026-01-22 | 9
41 | Active flooring |  | 2026-01-24 | 2026-01-27 | 2
41 | Active flooring |  | 2026-01-30 | 2026-02-04 | 4
41 | Active flooring |  | 2026-02-06 | 2026-02-10 | 3
41 | Active flooring |  | 2026-02-14 | 2026-02-25 | 8
41 | Active flooring |  | 2026-03-05 | 2026-03-07 | 2
41 | Active flooring |  | 2026-03-12 | 2026-03-14 | 2
41 | Active flooring |  | 2026-03-18 | 2026-03-21 | 3
41 | Active flooring |  | 2026-03-25 | 2026-03-28 | 3
41 | Active flooring |  | 2026-04-02 | 2026-04-05 | 2
41 | Active flooring |  | 2026-04-08 | 2026-04-09 | 2
41 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
41 | Active flooring |  | 2026-04-14 | 2026-04-14 | 1
41 | Active flooring |  | 2026-04-16 | 2026-04-19 | 2
41 | Active flooring |  | 2026-04-22 | 2026-04-26 | 3
41 | Active flooring |  | 2026-04-29 | 2026-05-02 | 3
41 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
41 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
41 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
41 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
41 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
41 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
41 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
41 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
42 | MCL |  | 2025-12-07 | 2025-12-08 | 1
42 | MCL |  | 2025-12-13 | 2025-12-15 | 1
42 | MCL |  | 2025-12-20 | 2025-12-22 | 1
42 | MCL |  | 2025-12-26 | 2025-12-29 | 2
42 | MCL |  | 2026-01-03 | 2026-01-06 | 2
42 | MCL |  | 2026-01-11 | 2026-01-22 | 9
42 | MCL |  | 2026-01-24 | 2026-01-27 | 2
42 | MCL |  | 2026-01-30 | 2026-02-04 | 4
42 | MCL |  | 2026-02-06 | 2026-02-10 | 3
42 | MCL |  | 2026-02-15 | 2026-02-17 | 2
42 | MCL |  | 2026-02-22 | 2026-02-25 | 3
42 | MCL |  | 2026-03-05 | 2026-03-07 | 2
42 | MCL |  | 2026-03-12 | 2026-03-14 | 2
42 | MCL |  | 2026-03-18 | 2026-03-21 | 3
42 | MCL |  | 2026-03-25 | 2026-03-28 | 3
42 | MCL |  | 2026-04-02 | 2026-04-05 | 2
42 | MCL |  | 2026-04-08 | 2026-04-09 | 2
42 | MCL |  | 2026-04-11 | 2026-04-12 | 1
42 | MCL |  | 2026-04-14 | 2026-04-14 | 1
42 | MCL |  | 2026-04-16 | 2026-04-19 | 2
42 | MCL |  | 2026-04-22 | 2026-04-26 | 3
42 | MCL |  | 2026-04-29 | 2026-05-02 | 3
42 | MCL |  | 2026-05-08 | 2026-05-09 | 1
42 | MCL |  | 2026-05-15 | 2026-05-16 | 1
42 | MCL |  | 2026-05-22 | 2026-05-23 | 1
42 | MCL |  | 2026-05-29 | 2026-05-30 | 1
42 | MCL |  | 2026-06-06 | 2026-06-07 | 1
42 | MCL |  | 2026-06-13 | 2026-06-14 | 1
42 | MCL |  | 2026-06-20 | 2026-06-21 | 1
42 | MCL |  | 2026-06-25 | 2026-06-28 | 2
43 | Smiths |  | 2025-12-07 | 2025-12-08 | 1
43 | Smiths |  | 2025-12-12 | 2025-12-15 | 2
43 | Smiths |  | 2025-12-20 | 2025-12-22 | 1
43 | Smiths |  | 2025-12-28 | 2025-12-29 | 1
43 | Smiths |  | 2026-01-03 | 2026-01-06 | 2
43 | Smiths |  | 2026-01-11 | 2026-01-13 | 2
43 | Smiths |  | 2026-01-15 | 2026-01-22 | 6
43 | Smiths |  | 2026-01-24 | 2026-01-27 | 2
43 | Smiths |  | 2026-01-30 | 2026-02-04 | 4
43 | Smiths |  | 2026-02-06 | 2026-02-10 | 3
43 | Smiths |  | 2026-02-15 | 2026-02-17 | 2
43 | Smiths |  | 2026-02-22 | 2026-02-25 | 3
43 | Smiths |  | 2026-03-05 | 2026-03-07 | 2
43 | Smiths |  | 2026-03-12 | 2026-03-14 | 2
43 | Smiths |  | 2026-03-18 | 2026-03-21 | 3
43 | Smiths |  | 2026-03-25 | 2026-03-28 | 3
43 | Smiths |  | 2026-04-02 | 2026-04-05 | 2
43 | Smiths |  | 2026-04-08 | 2026-04-09 | 2
43 | Smiths |  | 2026-04-11 | 2026-04-12 | 1
43 | Smiths |  | 2026-04-14 | 2026-04-14 | 1
43 | Smiths |  | 2026-04-16 | 2026-04-19 | 2
43 | Smiths |  | 2026-04-22 | 2026-04-26 | 3
43 | Smiths |  | 2026-04-29 | 2026-05-02 | 3
43 | Smiths |  | 2026-05-08 | 2026-05-09 | 1
43 | Smiths |  | 2026-05-15 | 2026-05-16 | 1
43 | Smiths |  | 2026-05-22 | 2026-05-23 | 1
43 | Smiths |  | 2026-05-29 | 2026-05-30 | 1
43 | Smiths |  | 2026-06-06 | 2026-06-07 | 1
43 | Smiths |  | 2026-06-13 | 2026-06-14 | 1
43 | Smiths |  | 2026-06-20 | 2026-06-21 | 1
43 | Smiths |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-12 | 2025-12-15 | 2
| Amtico flooring /Bathrooms |  | 2025-12-20 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-03 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-11 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-15 | 2026-01-22 | 6
| Amtico flooring /Bathrooms |  | 2026-01-24 | 2026-01-27 | 2
| Amtico flooring /Bathrooms |  | 2026-01-30 | 2026-02-04 | 4
| Amtico flooring /Bathrooms |  | 2026-02-06 | 2026-02-10 | 3
| Amtico flooring /Bathrooms |  | 2026-02-15 | 2026-02-17 | 2
| Amtico flooring /Bathrooms |  | 2026-02-22 | 2026-02-25 | 3
| Amtico flooring /Bathrooms |  | 2026-02-27 | 2026-03-02 | 2
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-12 | 2026-03-14 | 2
| Amtico flooring /Bathrooms |  | 2026-03-18 | 2026-03-21 | 3
| Amtico flooring /Bathrooms |  | 2026-03-25 | 2026-03-28 | 3
| Amtico flooring /Bathrooms |  | 2026-04-02 | 2026-04-05 | 2
| Amtico flooring /Bathrooms |  | 2026-04-08 | 2026-04-09 | 2
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-14 | 2026-04-14 | 1
| Amtico flooring /Bathrooms |  | 2026-04-16 | 2026-04-19 | 2
| Amtico flooring /Bathrooms |  | 2026-04-22 | 2026-04-26 | 3
| Amtico flooring /Bathrooms |  | 2026-04-29 | 2026-05-02 | 3
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
44 | MCL |  | 2025-12-07 | 2025-12-08 | 1
44 | MCL |  | 2025-12-12 | 2025-12-16 | 3
44 | MCL |  | 2025-12-20 | 2025-12-22 | 1
44 | MCL |  | 2025-12-26 | 2025-12-29 | 2
44 | MCL |  | 2026-01-03 | 2026-01-06 | 2
44 | MCL |  | 2026-01-10 | 2026-01-13 | 2
44 | MCL |  | 2026-01-16 | 2026-01-22 | 5
44 | MCL |  | 2026-01-24 | 2026-01-27 | 2
44 | MCL |  | 2026-01-30 | 2026-02-04 | 4
44 | MCL |  | 2026-02-06 | 2026-02-10 | 3
44 | MCL |  | 2026-02-15 | 2026-02-17 | 2
44 | MCL |  | 2026-02-22 | 2026-02-25 | 3
44 | MCL |  | 2026-03-03 | 2026-03-09 | 5
44 | MCL |  | 2026-03-12 | 2026-03-14 | 2
44 | MCL |  | 2026-03-18 | 2026-03-21 | 3
44 | MCL |  | 2026-03-25 | 2026-03-28 | 3
44 | MCL |  | 2026-04-02 | 2026-04-05 | 2
44 | MCL |  | 2026-04-08 | 2026-04-09 | 2
44 | MCL |  | 2026-04-11 | 2026-04-12 | 1
44 | MCL |  | 2026-04-14 | 2026-04-14 | 1
44 | MCL |  | 2026-04-16 | 2026-04-19 | 2
44 | MCL |  | 2026-04-22 | 2026-04-26 | 3
44 | MCL |  | 2026-04-29 | 2026-05-02 | 3
44 | MCL |  | 2026-05-08 | 2026-05-09 | 1
44 | MCL |  | 2026-05-15 | 2026-05-16 | 1
44 | MCL |  | 2026-05-22 | 2026-05-23 | 1
44 | MCL |  | 2026-05-29 | 2026-05-30 | 1
44 | MCL |  | 2026-06-06 | 2026-06-07 | 1
44 | MCL |  | 2026-06-13 | 2026-06-14 | 1
44 | MCL |  | 2026-06-20 | 2026-06-21 | 1
44 | MCL |  | 2026-06-25 | 2026-06-28 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2025-12-10 | 2026-01-06 | 20
Electrical 2nd fix & live testing | Active flooring |  | 2026-01-12 | 2026-01-22 | 9
Electrical 2nd fix & live testing | Active flooring |  | 2026-01-24 | 2026-01-27 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2026-01-30 | 2026-02-04 | 4
Electrical 2nd fix & live testing | Active flooring |  | 2026-02-06 | 2026-02-10 | 3
Electrical 2nd fix & live testing | Active flooring |  | 2026-02-15 | 2026-02-17 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2026-02-22 | 2026-02-25 | 3
Electrical 2nd fix & live testing | Active flooring |  | 2026-03-05 | 2026-03-07 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2026-03-10 | 2026-03-16 | 5
Electrical 2nd fix & live testing | Active flooring |  | 2026-03-18 | 2026-03-21 | 3
Electrical 2nd fix & live testing | Active flooring |  | 2026-03-25 | 2026-03-28 | 3
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-02 | 2026-04-05 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-08 | 2026-04-09 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-14 | 2026-04-14 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-16 | 2026-04-19 | 2
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-22 | 2026-04-26 | 3
Electrical 2nd fix & live testing | Active flooring |  | 2026-04-29 | 2026-05-02 | 3
Electrical 2nd fix & live testing | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
Electrical 2nd fix & live testing | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
Builders clean | Branniff |  | 2025-12-07 | 2025-12-08 | 1
Builders clean | Branniff |  | 2025-12-10 | 2026-01-06 | 20
Builders clean | Branniff |  | 2026-01-12 | 2026-01-22 | 9
Builders clean | Branniff |  | 2026-01-24 | 2026-01-27 | 2
Builders clean | Branniff |  | 2026-01-30 | 2026-02-04 | 4
Builders clean | Branniff |  | 2026-02-06 | 2026-02-10 | 3
Builders clean | Branniff |  | 2026-02-15 | 2026-02-17 | 2
Builders clean | Branniff |  | 2026-02-22 | 2026-02-25 | 3
Builders clean | Branniff |  | 2026-03-05 | 2026-03-07 | 2
Builders clean | Branniff |  | 2026-03-12 | 2026-03-14 | 2
Builders clean | Branniff |  | 2026-03-18 | 2026-03-21 | 3
Builders clean | Branniff |  | 2026-03-25 | 2026-03-28 | 3
Builders clean | Branniff |  | 2026-04-02 | 2026-04-05 | 2
Builders clean | Branniff |  | 2026-04-08 | 2026-04-09 | 2
Builders clean | Branniff |  | 2026-04-11 | 2026-04-12 | 1
Builders clean | Branniff |  | 2026-04-14 | 2026-04-14 | 1
Builders clean | Branniff |  | 2026-04-16 | 2026-04-19 | 2
Builders clean | Branniff |  | 2026-04-22 | 2026-04-26 | 3
Builders clean | Branniff |  | 2026-04-29 | 2026-05-02 | 3
Builders clean | Branniff |  | 2026-05-08 | 2026-05-09 | 1
Builders clean | Branniff |  | 2026-05-15 | 2026-05-16 | 1
Builders clean | Branniff |  | 2026-05-22 | 2026-05-23 | 1
Builders clean | Branniff |  | 2026-05-29 | 2026-05-30 | 1
Builders clean | Branniff |  | 2026-06-06 | 2026-06-07 | 1
Builders clean | Branniff |  | 2026-06-13 | 2026-06-14 | 1
Builders clean | Branniff |  | 2026-06-20 | 2026-06-21 | 1
Builders clean | Branniff |  | 2026-06-25 | 2026-06-28 | 2
Pre -dec -snagging | Wren |  | 2025-12-07 | 2025-12-08 | 1
Pre -dec -snagging | Wren |  | 2025-12-10 | 2025-12-22 | 9
Pre -dec -snagging | Wren |  | 2025-12-26 | 2025-12-29 | 2
Pre -dec -snagging | Wren |  | 2026-01-01 | 2026-01-06 | 4
Pre -dec -snagging | Wren |  | 2026-01-12 | 2026-01-13 | 2
Pre -dec -snagging | Wren |  | 2026-01-16 | 2026-02-04 | 14
Pre -dec -snagging | Wren |  | 2026-02-06 | 2026-02-10 | 3
Pre -dec -snagging | Wren |  | 2026-02-15 | 2026-02-17 | 2
Pre -dec -snagging | Wren |  | 2026-02-22 | 2026-02-25 | 3
Pre -dec -snagging | Wren |  | 2026-03-05 | 2026-03-07 | 2
Pre -dec -snagging | Wren |  | 2026-03-12 | 2026-03-14 | 2
Pre -dec -snagging | Wren |  | 2026-03-18 | 2026-03-21 | 3
Pre -dec -snagging | Wren |  | 2026-03-25 | 2026-03-28 | 3
Pre -dec -snagging | Wren |  | 2026-04-02 | 2026-04-05 | 2
Pre -dec -snagging | Wren |  | 2026-04-08 | 2026-04-09 | 2
Pre -dec -snagging | Wren |  | 2026-04-11 | 2026-04-12 | 1
Pre -dec -snagging | Wren |  | 2026-04-14 | 2026-04-14 | 1
Pre -dec -snagging | Wren |  | 2026-04-16 | 2026-04-19 | 2
Pre -dec -snagging | Wren |  | 2026-04-22 | 2026-04-26 | 3
Pre -dec -snagging | Wren |  | 2026-04-29 | 2026-05-02 | 3
Pre -dec -snagging | Wren |  | 2026-05-08 | 2026-05-09 | 1
Pre -dec -snagging | Wren |  | 2026-05-15 | 2026-05-16 | 1
Pre -dec -snagging | Wren |  | 2026-05-22 | 2026-05-23 | 1
Pre -dec -snagging | Wren |  | 2026-05-29 | 2026-05-30 | 1
Pre -dec -snagging | Wren |  | 2026-06-06 | 2026-06-07 | 1
Pre -dec -snagging | Wren |  | 2026-06-13 | 2026-06-14 | 1
Pre -dec -snagging | Wren |  | 2026-06-20 | 2026-06-21 | 1
Pre -dec -snagging | Wren |  | 2026-06-25 | 2026-06-28 | 2
45 | Decoration |  | 2025-12-07 | 2025-12-08 | 1
45 | Decoration |  | 2025-12-13 | 2025-12-22 | 6
45 | Decoration |  | 2025-12-26 | 2025-12-29 | 2
45 | Decoration |  | 2026-01-01 | 2026-01-06 | 4
45 | Decoration |  | 2026-01-12 | 2026-01-13 | 2
45 | Decoration |  | 2026-01-16 | 2026-01-22 | 5
45 | Decoration |  | 2026-01-24 | 2026-01-27 | 2
45 | Decoration |  | 2026-01-30 | 2026-02-04 | 4
45 | Decoration |  | 2026-02-06 | 2026-02-10 | 3
45 | Decoration |  | 2026-02-15 | 2026-02-17 | 2
45 | Decoration |  | 2026-02-22 | 2026-02-25 | 3
45 | Decoration |  | 2026-03-05 | 2026-03-07 | 2
45 | Decoration |  | 2026-03-12 | 2026-03-14 | 2
45 | Decoration |  | 2026-03-17 | 2026-03-23 | 5
45 | Decoration |  | 2026-03-25 | 2026-03-28 | 3
45 | Decoration |  | 2026-04-02 | 2026-04-05 | 2
45 | Decoration |  | 2026-04-08 | 2026-04-09 | 2
45 | Decoration |  | 2026-04-11 | 2026-04-12 | 1
45 | Decoration |  | 2026-04-14 | 2026-04-14 | 1
45 | Decoration |  | 2026-04-16 | 2026-04-19 | 2
45 | Decoration |  | 2026-04-22 | 2026-04-26 | 3
45 | Decoration |  | 2026-04-29 | 2026-05-02 | 3
45 | Decoration |  | 2026-05-08 | 2026-05-09 | 1
45 | Decoration |  | 2026-05-15 | 2026-05-16 | 1
45 | Decoration |  | 2026-05-22 | 2026-05-23 | 1
45 | Decoration |  | 2026-05-29 | 2026-05-30 | 1
45 | Decoration |  | 2026-06-06 | 2026-06-07 | 1
45 | Decoration |  | 2026-06-13 | 2026-06-14 | 1
45 | Decoration |  | 2026-06-20 | 2026-06-21 | 1
45 | Decoration |  | 2026-06-25 | 2026-06-28 | 2
46 | Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-08 | 1
46 | Amtico flooring /Carpets |  | 2025-12-13 | 2025-12-15 | 1
46 | Amtico flooring /Carpets |  | 2025-12-19 | 2025-12-22 | 2
46 | Amtico flooring /Carpets |  | 2025-12-26 | 2025-12-29 | 2
46 | Amtico flooring /Carpets |  | 2026-01-03 | 2026-01-06 | 2
46 | Amtico flooring /Carpets |  | 2026-01-12 | 2026-01-13 | 2
46 | Amtico flooring /Carpets |  | 2026-01-16 | 2026-01-27 | 8
46 | Amtico flooring /Carpets |  | 2026-02-01 | 2026-02-04 | 3
46 | Amtico flooring /Carpets |  | 2026-02-06 | 2026-02-10 | 3
46 | Amtico flooring /Carpets |  | 2026-02-15 | 2026-02-17 | 2
46 | Amtico flooring /Carpets |  | 2026-02-22 | 2026-02-25 | 3
46 | Amtico flooring /Carpets |  | 2026-03-05 | 2026-03-07 | 2
46 | Amtico flooring /Carpets |  | 2026-03-12 | 2026-03-14 | 2
46 | Amtico flooring /Carpets |  | 2026-03-18 | 2026-03-21 | 3
46 | Amtico flooring /Carpets |  | 2026-03-24 | 2026-03-28 | 4
46 | Amtico flooring /Carpets |  | 2026-04-02 | 2026-04-05 | 2
46 | Amtico flooring /Carpets |  | 2026-04-08 | 2026-04-09 | 2
46 | Amtico flooring /Carpets |  | 2026-04-11 | 2026-04-12 | 1
46 | Amtico flooring /Carpets |  | 2026-04-14 | 2026-04-14 | 1
46 | Amtico flooring /Carpets |  | 2026-04-16 | 2026-04-19 | 2
46 | Amtico flooring /Carpets |  | 2026-04-22 | 2026-04-26 | 3
46 | Amtico flooring /Carpets |  | 2026-04-29 | 2026-05-02 | 3
46 | Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
46 | Amtico flooring /Carpets |  | 2026-05-15 | 2026-05-16 | 1
46 | Amtico flooring /Carpets |  | 2026-05-22 | 2026-05-23 | 1
46 | Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
46 | Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
46 | Amtico flooring /Carpets |  | 2026-06-13 | 2026-06-14 | 1
46 | Amtico flooring /Carpets |  | 2026-06-20 | 2026-06-21 | 1
46 | Amtico flooring /Carpets |  | 2026-06-25 | 2026-06-28 | 2
47 | De snag all trades -test & commision |  | 2025-12-07 | 2025-12-08 | 1
47 | De snag all trades -test & commision |  | 2025-12-13 | 2025-12-15 | 1
47 | De snag all trades -test & commision |  | 2025-12-19 | 2025-12-22 | 2
47 | De snag all trades -test & commision |  | 2025-12-26 | 2025-12-29 | 2
47 | De snag all trades -test & commision |  | 2026-01-03 | 2026-01-06 | 2
47 | De snag all trades -test & commision |  | 2026-01-12 | 2026-01-13 | 2
47 | De snag all trades -test & commision |  | 2026-01-16 | 2026-01-27 | 8
47 | De snag all trades -test & commision |  | 2026-02-01 | 2026-02-04 | 3
47 | De snag all trades -test & commision |  | 2026-02-06 | 2026-02-10 | 3
47 | De snag all trades -test & commision |  | 2026-02-15 | 2026-02-17 | 2
47 | De snag all trades -test & commision |  | 2026-02-22 | 2026-02-25 | 3
47 | De snag all trades -test & commision |  | 2026-03-05 | 2026-03-07 | 2
47 | De snag all trades -test & commision |  | 2026-03-12 | 2026-03-14 | 2
47 | De snag all trades -test & commision |  | 2026-03-18 | 2026-03-21 | 3
47 | De snag all trades -test & commision |  | 2026-03-25 | 2026-04-05 | 8
47 | De snag all trades -test & commision |  | 2026-04-08 | 2026-04-09 | 2
47 | De snag all trades -test & commision |  | 2026-04-11 | 2026-04-12 | 1
47 | De snag all trades -test & commision |  | 2026-04-14 | 2026-04-14 | 1
47 | De snag all trades -test & commision |  | 2026-04-16 | 2026-04-19 | 2
47 | De snag all trades -test & commision |  | 2026-04-22 | 2026-04-26 | 3
47 | De snag all trades -test & commision |  | 2026-04-29 | 2026-05-02 | 3
47 | De snag all trades -test & commision |  | 2026-05-08 | 2026-05-09 | 1
47 | De snag all trades -test & commision |  | 2026-05-15 | 2026-05-16 | 1
47 | De snag all trades -test & commision |  | 2026-05-22 | 2026-05-23 | 1
47 | De snag all trades -test & commision |  | 2026-05-29 | 2026-05-30 | 1
47 | De snag all trades -test & commision |  | 2026-06-06 | 2026-06-07 | 1
47 | De snag all trades -test & commision |  | 2026-06-13 | 2026-06-14 | 1
47 | De snag all trades -test & commision |  | 2026-06-20 | 2026-06-21 | 1
47 | De snag all trades -test & commision |  | 2026-06-25 | 2026-06-28 | 2
48 | Sparkle clean |  | 2025-12-07 | 2025-12-08 | 1
48 | Sparkle clean |  | 2025-12-13 | 2025-12-15 | 1
48 | Sparkle clean |  | 2025-12-20 | 2025-12-22 | 1
48 | Sparkle clean |  | 2025-12-26 | 2025-12-29 | 2
48 | Sparkle clean |  | 2026-01-03 | 2026-01-06 | 2
48 | Sparkle clean |  | 2026-01-10 | 2026-01-13 | 2
48 | Sparkle clean |  | 2026-01-16 | 2026-01-22 | 5
48 | Sparkle clean |  | 2026-01-24 | 2026-01-27 | 2
48 | Sparkle clean |  | 2026-01-30 | 2026-02-10 | 8
48 | Sparkle clean |  | 2026-02-15 | 2026-02-17 | 2
48 | Sparkle clean |  | 2026-02-22 | 2026-02-25 | 3
48 | Sparkle clean |  | 2026-03-05 | 2026-03-07 | 2
48 | Sparkle clean |  | 2026-03-12 | 2026-03-14 | 2
48 | Sparkle clean |  | 2026-03-18 | 2026-03-21 | 3
48 | Sparkle clean |  | 2026-03-25 | 2026-03-28 | 3
48 | Sparkle clean |  | 2026-04-02 | 2026-04-12 | 7
48 | Sparkle clean |  | 2026-04-14 | 2026-04-14 | 1
48 | Sparkle clean |  | 2026-04-16 | 2026-04-19 | 2
48 | Sparkle clean |  | 2026-04-22 | 2026-04-26 | 3
48 | Sparkle clean |  | 2026-04-29 | 2026-05-02 | 3
48 | Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
48 | Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
48 | Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
48 | Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
48 | Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
48 | Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
48 | Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
48 | Sparkle clean |  | 2026-06-25 | 2026-06-28 | 2
49 | Mastic |  | 2025-12-07 | 2025-12-08 | 1
49 | Mastic |  | 2025-12-13 | 2025-12-15 | 1
49 | Mastic |  | 2025-12-20 | 2025-12-22 | 1
49 | Mastic |  | 2025-12-26 | 2025-12-29 | 2
49 | Mastic |  | 2026-01-03 | 2026-01-06 | 2
49 | Mastic |  | 2026-01-10 | 2026-01-13 | 2
49 | Mastic |  | 2026-01-16 | 2026-01-22 | 5
49 | Mastic |  | 2026-01-24 | 2026-01-27 | 2
49 | Mastic |  | 2026-01-30 | 2026-02-10 | 8
49 | Mastic |  | 2026-02-16 | 2026-02-17 | 2
49 | Mastic |  | 2026-02-22 | 2026-02-25 | 3
49 | Mastic |  | 2026-03-05 | 2026-03-07 | 2
49 | Mastic |  | 2026-03-12 | 2026-03-14 | 2
49 | Mastic |  | 2026-03-18 | 2026-03-21 | 3
49 | Mastic |  | 2026-03-25 | 2026-03-28 | 3
49 | Mastic |  | 2026-04-02 | 2026-04-05 | 2
49 | Mastic |  | 2026-04-08 | 2026-04-09 | 2
49 | Mastic |  | 2026-04-11 | 2026-04-14 | 2
49 | Mastic |  | 2026-04-16 | 2026-04-19 | 2
49 | Mastic |  | 2026-04-22 | 2026-04-26 | 3
49 | Mastic |  | 2026-04-29 | 2026-05-02 | 3
49 | Mastic |  | 2026-05-08 | 2026-05-09 | 1
49 | Mastic |  | 2026-05-15 | 2026-05-16 | 1
49 | Mastic |  | 2026-05-22 | 2026-05-23 | 1
49 | Mastic |  | 2026-05-29 | 2026-05-30 | 1
49 | Mastic |  | 2026-06-06 | 2026-06-07 | 1
49 | Mastic |  | 2026-06-13 | 2026-06-14 | 1
49 | Mastic |  | 2026-06-20 | 2026-06-21 | 1
49 | Mastic |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-13 | 2025-12-15 | 1
| Handover to client |  | 2025-12-20 | 2025-12-22 | 1
| Handover to client |  | 2025-12-26 | 2025-12-29 | 2
| Handover to client |  | 2026-01-03 | 2026-01-06 | 2
| Handover to client |  | 2026-01-10 | 2026-01-13 | 2
| Handover to client |  | 2026-01-16 | 2026-01-22 | 5
| Handover to client |  | 2026-01-24 | 2026-01-27 | 2
| Handover to client |  | 2026-01-30 | 2026-02-10 | 8
| Handover to client |  | 2026-02-16 | 2026-02-17 | 2
| Handover to client |  | 2026-02-22 | 2026-02-25 | 3
| Handover to client |  | 2026-03-05 | 2026-03-07 | 2
| Handover to client |  | 2026-03-12 | 2026-03-14 | 2
| Handover to client |  | 2026-03-18 | 2026-03-21 | 3
| Handover to client |  | 2026-03-25 | 2026-03-28 | 3
| Handover to client |  | 2026-04-02 | 2026-04-05 | 2
| Handover to client |  | 2026-04-08 | 2026-04-09 | 2
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-14 | 2026-04-14 | 1
| Handover to client |  | 2026-04-16 | 2026-04-19 | 2
| Handover to client |  | 2026-04-22 | 2026-04-27 | 4
| Handover to client |  | 2026-04-29 | 2026-05-02 | 3
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2025-12-07 | 2025-12-08 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2025-12-13 | 2025-12-15 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2025-12-20 | 2025-12-22 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2025-12-26 | 2025-12-29 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-01-03 | 2026-01-06 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-01-10 | 2026-01-13 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-01-16 | 2026-01-22 | 5
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-01-24 | 2026-01-27 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-01-30 | 2026-02-04 | 4
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-02-06 | 2026-02-10 | 3
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-02-16 | 2026-02-17 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-02-22 | 2026-02-25 | 3
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-03-05 | 2026-03-07 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-03-12 | 2026-03-14 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-03-18 | 2026-03-21 | 3
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-03-25 | 2026-03-28 | 3
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-02 | 2026-04-05 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-08 | 2026-04-09 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-11 | 2026-04-12 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-14 | 2026-04-14 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-16 | 2026-04-19 | 2
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-22 | 2026-04-26 | 3
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-04-29 | 2026-05-02 | 3
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-05-08 | 2026-05-09 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-05-15 | 2026-05-16 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-05-22 | 2026-05-23 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-05-29 | 2026-05-30 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-06-06 | 2026-06-07 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-06-13 | 2026-06-14 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-06-20 | 2026-06-21 | 1
50 | Level 3 Apartment fit out -cluster 1 |  | 2026-06-25 | 2026-06-28 | 2
51 | Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-08 | 1
51 | Levveling screed /smoothing compound |  | 2025-12-13 | 2025-12-15 | 1
51 | Levveling screed /smoothing compound |  | 2025-12-20 | 2025-12-22 | 1
51 | Levveling screed /smoothing compound |  | 2025-12-26 | 2025-12-29 | 2
51 | Levveling screed /smoothing compound |  | 2026-01-03 | 2026-01-06 | 2
51 | Levveling screed /smoothing compound |  | 2026-01-10 | 2026-01-13 | 2
51 | Levveling screed /smoothing compound |  | 2026-01-16 | 2026-01-22 | 5
51 | Levveling screed /smoothing compound |  | 2026-01-24 | 2026-01-27 | 2
51 | Levveling screed /smoothing compound |  | 2026-01-30 | 2026-02-04 | 4
51 | Levveling screed /smoothing compound |  | 2026-02-06 | 2026-02-17 | 8
51 | Levveling screed /smoothing compound |  | 2026-02-22 | 2026-02-25 | 3
51 | Levveling screed /smoothing compound |  | 2026-03-05 | 2026-03-07 | 2
51 | Levveling screed /smoothing compound |  | 2026-03-12 | 2026-03-14 | 2
51 | Levveling screed /smoothing compound |  | 2026-03-18 | 2026-03-21 | 3
51 | Levveling screed /smoothing compound |  | 2026-03-25 | 2026-03-28 | 3
51 | Levveling screed /smoothing compound |  | 2026-04-02 | 2026-04-05 | 2
51 | Levveling screed /smoothing compound |  | 2026-04-08 | 2026-04-09 | 2
51 | Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
51 | Levveling screed /smoothing compound |  | 2026-04-14 | 2026-04-14 | 1
51 | Levveling screed /smoothing compound |  | 2026-04-16 | 2026-04-19 | 2
51 | Levveling screed /smoothing compound |  | 2026-04-22 | 2026-04-26 | 3
51 | Levveling screed /smoothing compound |  | 2026-04-29 | 2026-05-02 | 3
51 | Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
51 | Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
51 | Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
51 | Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
51 | Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
51 | Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
51 | Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
51 | Levveling screed /smoothing compound |  | 2026-06-25 | 2026-06-28 | 2
52 | Drying out |  | 2025-12-07 | 2025-12-08 | 1
52 | Drying out |  | 2025-12-13 | 2025-12-15 | 1
52 | Drying out |  | 2025-12-20 | 2025-12-22 | 1
52 | Drying out |  | 2025-12-26 | 2025-12-29 | 2
52 | Drying out |  | 2026-01-03 | 2026-01-06 | 2
52 | Drying out |  | 2026-01-10 | 2026-01-13 | 2
52 | Drying out |  | 2026-01-16 | 2026-01-22 | 5
52 | Drying out |  | 2026-01-24 | 2026-01-27 | 2
52 | Drying out |  | 2026-01-30 | 2026-02-04 | 4
52 | Drying out |  | 2026-02-06 | 2026-02-10 | 3
52 | Drying out |  | 2026-02-15 | 2026-02-17 | 2
52 | Drying out |  | 2026-02-22 | 2026-02-25 | 3
52 | Drying out |  | 2026-03-05 | 2026-03-07 | 2
52 | Drying out |  | 2026-03-12 | 2026-03-14 | 2
52 | Drying out |  | 2026-03-18 | 2026-03-21 | 3
52 | Drying out |  | 2026-03-25 | 2026-03-28 | 3
52 | Drying out |  | 2026-04-02 | 2026-04-05 | 2
52 | Drying out |  | 2026-04-08 | 2026-04-09 | 2
52 | Drying out |  | 2026-04-11 | 2026-04-12 | 1
52 | Drying out |  | 2026-04-14 | 2026-04-14 | 1
52 | Drying out |  | 2026-04-16 | 2026-04-19 | 2
52 | Drying out |  | 2026-04-22 | 2026-04-26 | 3
52 | Drying out |  | 2026-04-29 | 2026-05-02 | 3
52 | Drying out |  | 2026-05-08 | 2026-05-09 | 1
52 | Drying out |  | 2026-05-15 | 2026-05-16 | 1
52 | Drying out |  | 2026-05-22 | 2026-05-23 | 1
52 | Drying out |  | 2026-05-29 | 2026-05-30 | 1
52 | Drying out |  | 2026-06-06 | 2026-06-07 | 1
52 | Drying out |  | 2026-06-13 | 2026-06-14 | 1
52 | Drying out |  | 2026-06-20 | 2026-06-21 | 1
52 | Drying out |  | 2026-06-25 | 2026-06-28 | 2
53 | Mist coat |  | 2025-12-07 | 2025-12-08 | 1
53 | Mist coat |  | 2025-12-13 | 2025-12-15 | 1
53 | Mist coat |  | 2025-12-20 | 2025-12-22 | 1
53 | Mist coat |  | 2025-12-26 | 2025-12-29 | 2
53 | Mist coat |  | 2026-01-03 | 2026-01-06 | 2
53 | Mist coat |  | 2026-01-10 | 2026-01-13 | 2
53 | Mist coat |  | 2026-01-16 | 2026-01-22 | 5
53 | Mist coat |  | 2026-01-24 | 2026-01-27 | 2
53 | Mist coat |  | 2026-01-30 | 2026-02-04 | 4
53 | Mist coat |  | 2026-02-06 | 2026-02-10 | 3
53 | Mist coat |  | 2026-02-14 | 2026-02-17 | 2
53 | Mist coat |  | 2026-02-22 | 2026-02-25 | 3
53 | Mist coat |  | 2026-03-05 | 2026-03-07 | 2
53 | Mist coat |  | 2026-03-12 | 2026-03-14 | 2
53 | Mist coat |  | 2026-03-18 | 2026-03-21 | 3
53 | Mist coat |  | 2026-03-25 | 2026-03-28 | 3
53 | Mist coat |  | 2026-04-02 | 2026-04-05 | 2
53 | Mist coat |  | 2026-04-08 | 2026-04-09 | 2
53 | Mist coat |  | 2026-04-11 | 2026-04-12 | 1
53 | Mist coat |  | 2026-04-14 | 2026-04-14 | 1
53 | Mist coat |  | 2026-04-16 | 2026-04-19 | 2
53 | Mist coat |  | 2026-04-22 | 2026-04-26 | 3
53 | Mist coat |  | 2026-04-29 | 2026-05-02 | 3
53 | Mist coat |  | 2026-05-08 | 2026-05-09 | 1
53 | Mist coat |  | 2026-05-15 | 2026-05-16 | 1
53 | Mist coat |  | 2026-05-22 | 2026-05-23 | 1
53 | Mist coat |  | 2026-05-29 | 2026-05-30 | 1
53 | Mist coat |  | 2026-06-06 | 2026-06-07 | 1
53 | Mist coat |  | 2026-06-13 | 2026-06-14 | 1
53 | Mist coat |  | 2026-06-20 | 2026-06-21 | 1
53 | Mist coat |  | 2026-06-25 | 2026-06-28 | 2
Vanity b | Vanity 1st fix framing |  | 2025-12-07 | 2025-12-08 | 1
Vanity b | Vanity 1st fix framing |  | 2025-12-13 | 2025-12-15 | 1
Vanity b | Vanity 1st fix framing |  | 2025-12-20 | 2025-12-22 | 1
Vanity b | Vanity 1st fix framing |  | 2025-12-26 | 2025-12-29 | 2
Vanity b | Vanity 1st fix framing |  | 2026-01-03 | 2026-01-06 | 2
Vanity b | Vanity 1st fix framing |  | 2026-01-10 | 2026-01-13 | 2
Vanity b | Vanity 1st fix framing |  | 2026-01-16 | 2026-01-22 | 5
Vanity b | Vanity 1st fix framing |  | 2026-01-24 | 2026-01-27 | 2
Vanity b | Vanity 1st fix framing |  | 2026-01-30 | 2026-02-04 | 4
Vanity b | Vanity 1st fix framing |  | 2026-02-06 | 2026-02-10 | 3
Vanity b | Vanity 1st fix framing |  | 2026-02-12 | 2026-02-13 | 2
Vanity b | Vanity 1st fix framing |  | 2026-02-15 | 2026-02-17 | 2
Vanity b | Vanity 1st fix framing |  | 2026-02-22 | 2026-02-25 | 3
Vanity b | Vanity 1st fix framing |  | 2026-03-05 | 2026-03-07 | 2
Vanity b | Vanity 1st fix framing |  | 2026-03-12 | 2026-03-14 | 2
Vanity b | Vanity 1st fix framing |  | 2026-03-18 | 2026-03-21 | 3
Vanity b | Vanity 1st fix framing |  | 2026-03-25 | 2026-03-28 | 3
Vanity b | Vanity 1st fix framing |  | 2026-04-02 | 2026-04-05 | 2
Vanity b | Vanity 1st fix framing |  | 2026-04-08 | 2026-04-09 | 2
Vanity b | Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
Vanity b | Vanity 1st fix framing |  | 2026-04-14 | 2026-04-14 | 1
Vanity b | Vanity 1st fix framing |  | 2026-04-16 | 2026-04-19 | 2
Vanity b | Vanity 1st fix framing |  | 2026-04-22 | 2026-04-26 | 3
Vanity b | Vanity 1st fix framing |  | 2026-04-29 | 2026-05-02 | 3
Vanity b | Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
Vanity b | Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
Vanity b | Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
Vanity b | Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
Vanity b | Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
Vanity b | Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
Vanity b | Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
Vanity b | Vanity 1st fix framing |  | 2026-06-25 | 2026-06-28 | 2
| Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-08 | 1
| Kitchen 1st fix,units tops & appliances |  | 2025-12-13 | 2025-12-15 | 1
| Kitchen 1st fix,units tops & appliances |  | 2025-12-20 | 2025-12-22 | 1
| Kitchen 1st fix,units tops & appliances |  | 2025-12-26 | 2025-12-29 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-01-03 | 2026-01-06 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-01-10 | 2026-01-13 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-01-16 | 2026-01-22 | 5
| Kitchen 1st fix,units tops & appliances |  | 2026-01-24 | 2026-01-27 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-01-30 | 2026-02-04 | 4
| Kitchen 1st fix,units tops & appliances |  | 2026-02-06 | 2026-02-10 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-02-15 | 2026-02-17 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-02-22 | 2026-02-25 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-03-01 | 2026-03-07 | 5
| Kitchen 1st fix,units tops & appliances |  | 2026-03-12 | 2026-03-14 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-03-18 | 2026-03-21 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-03-25 | 2026-03-28 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-04-02 | 2026-04-05 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-04-08 | 2026-04-09 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-04-14 | 2026-04-14 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-04-16 | 2026-04-19 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-04-22 | 2026-04-26 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-04-29 | 2026-05-02 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-15 | 2026-05-16 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-22 | 2026-05-23 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-20 | 2026-06-21 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-25 | 2026-06-28 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-08 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-13 | 2025-12-15 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-20 | 2025-12-22 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-26 | 2025-12-29 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-03 | 2026-01-06 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-10 | 2026-01-13 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-16 | 2026-01-22 | 5
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-24 | 2026-01-27 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-30 | 2026-02-04 | 4
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-06 | 2026-02-10 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-15 | 2026-02-17 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-02-20 | 2026-02-28 | 6
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-05 | 2026-03-07 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-12 | 2026-03-14 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-18 | 2026-03-21 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-25 | 2026-03-28 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-02 | 2026-04-05 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-08 | 2026-04-09 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-14 | 2026-04-14 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-16 | 2026-04-19 | 2
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-22 | 2026-04-26 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-29 | 2026-05-02 | 3
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-15 | 2026-05-16 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-22 | 2026-05-23 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-29 | 2026-05-30 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-06 | 2026-06-07 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-13 | 2026-06-14 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-20 | 2026-06-21 | 1
| Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-13 | 2025-12-15 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-20 | 2025-12-22 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-26 | 2025-12-29 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-03 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-10 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-16 | 2026-01-22 | 5
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-24 | 2026-01-27 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-30 | 2026-02-04 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-06 | 2026-02-10 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-13 | 2026-02-19 | 5
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-23 | 2026-02-28 | 5
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-05 | 2026-03-07 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-12 | 2026-03-14 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-18 | 2026-03-21 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-25 | 2026-03-28 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-02 | 2026-04-05 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-08 | 2026-04-09 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-14 | 2026-04-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-16 | 2026-04-19 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-22 | 2026-04-26 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-29 | 2026-05-02 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
54 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
54 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
54 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
54 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
54 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
54 | PANACEA |  | 2026-01-10 | 2026-01-13 | 2
54 | PANACEA |  | 2026-01-16 | 2026-01-22 | 5
54 | PANACEA |  | 2026-01-24 | 2026-01-27 | 2
54 | PANACEA |  | 2026-01-30 | 2026-02-04 | 4
54 | PANACEA |  | 2026-02-06 | 2026-02-10 | 3
54 | PANACEA |  | 2026-02-15 | 2026-02-17 | 2
54 | PANACEA |  | 2026-02-20 | 2026-02-27 | 6
54 | PANACEA |  | 2026-03-05 | 2026-03-07 | 2
54 | PANACEA |  | 2026-03-12 | 2026-03-14 | 2
54 | PANACEA |  | 2026-03-18 | 2026-03-21 | 3
54 | PANACEA |  | 2026-03-25 | 2026-03-28 | 3
54 | PANACEA |  | 2026-04-02 | 2026-04-05 | 2
54 | PANACEA |  | 2026-04-08 | 2026-04-09 | 2
54 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
54 | PANACEA |  | 2026-04-14 | 2026-04-14 | 1
54 | PANACEA |  | 2026-04-16 | 2026-04-19 | 2
54 | PANACEA |  | 2026-04-22 | 2026-04-26 | 3
54 | PANACEA |  | 2026-04-29 | 2026-05-02 | 3
54 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
54 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
54 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
54 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
54 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
54 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
54 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
54 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Service cupboard board ceiling &finish |  | 2025-12-07 | 2025-12-08 | 1
| Service cupboard board ceiling &finish |  | 2025-12-14 | 2025-12-15 | 1
| Service cupboard board ceiling &finish |  | 2025-12-21 | 2025-12-22 | 1
| Service cupboard board ceiling &finish |  | 2025-12-28 | 2025-12-29 | 1
| Service cupboard board ceiling &finish |  | 2026-01-05 | 2026-01-06 | 2
| Service cupboard board ceiling &finish |  | 2026-01-10 | 2026-01-13 | 2
| Service cupboard board ceiling &finish |  | 2026-01-16 | 2026-01-22 | 5
| Service cupboard board ceiling &finish |  | 2026-01-24 | 2026-01-27 | 2
| Service cupboard board ceiling &finish |  | 2026-01-30 | 2026-02-04 | 4
| Service cupboard board ceiling &finish |  | 2026-02-06 | 2026-02-10 | 3
| Service cupboard board ceiling &finish |  | 2026-02-13 | 2026-02-17 | 3
| Service cupboard board ceiling &finish |  | 2026-02-22 | 2026-02-25 | 3
| Service cupboard board ceiling &finish |  | 2026-03-05 | 2026-03-07 | 2
| Service cupboard board ceiling &finish |  | 2026-03-12 | 2026-03-14 | 2
| Service cupboard board ceiling &finish |  | 2026-03-18 | 2026-03-21 | 3
| Service cupboard board ceiling &finish |  | 2026-03-25 | 2026-03-28 | 3
| Service cupboard board ceiling &finish |  | 2026-04-02 | 2026-04-05 | 2
| Service cupboard board ceiling &finish |  | 2026-04-08 | 2026-04-09 | 2
| Service cupboard board ceiling &finish |  | 2026-04-11 | 2026-04-12 | 1
| Service cupboard board ceiling &finish |  | 2026-04-14 | 2026-04-14 | 1
| Service cupboard board ceiling &finish |  | 2026-04-16 | 2026-04-19 | 2
| Service cupboard board ceiling &finish |  | 2026-04-22 | 2026-04-26 | 3
| Service cupboard board ceiling &finish |  | 2026-04-29 | 2026-05-02 | 3
| Service cupboard board ceiling &finish |  | 2026-05-08 | 2026-05-09 | 1
| Service cupboard board ceiling &finish |  | 2026-05-15 | 2026-05-16 | 1
| Service cupboard board ceiling &finish |  | 2026-05-22 | 2026-05-23 | 1
| Service cupboard board ceiling &finish |  | 2026-05-29 | 2026-05-30 | 1
| Service cupboard board ceiling &finish |  | 2026-06-06 | 2026-06-07 | 1
| Service cupboard board ceiling &finish |  | 2026-06-13 | 2026-06-14 | 1
| Service cupboard board ceiling &finish |  | 2026-06-20 | 2026-06-21 | 1
| Service cupboard board ceiling &finish |  | 2026-06-25 | 2026-06-28 | 2
55 | Edencroft |  | 2025-12-07 | 2025-12-08 | 1
55 | Edencroft |  | 2025-12-14 | 2025-12-15 | 1
55 | Edencroft |  | 2025-12-21 | 2025-12-22 | 1
55 | Edencroft |  | 2025-12-28 | 2025-12-29 | 1
55 | Edencroft |  | 2026-01-05 | 2026-01-06 | 2
55 | Edencroft |  | 2026-01-10 | 2026-01-13 | 2
55 | Edencroft |  | 2026-01-16 | 2026-01-22 | 5
55 | Edencroft |  | 2026-01-24 | 2026-01-27 | 2
55 | Edencroft |  | 2026-01-30 | 2026-02-04 | 4
55 | Edencroft |  | 2026-02-06 | 2026-02-10 | 3
55 | Edencroft |  | 2026-02-15 | 2026-02-19 | 4
55 | Edencroft |  | 2026-02-22 | 2026-02-25 | 3
55 | Edencroft |  | 2026-03-05 | 2026-03-07 | 2
55 | Edencroft |  | 2026-03-12 | 2026-03-14 | 2
55 | Edencroft |  | 2026-03-18 | 2026-03-21 | 3
55 | Edencroft |  | 2026-03-25 | 2026-03-28 | 3
55 | Edencroft |  | 2026-04-02 | 2026-04-05 | 2
55 | Edencroft |  | 2026-04-08 | 2026-04-09 | 2
55 | Edencroft |  | 2026-04-11 | 2026-04-12 | 1
55 | Edencroft |  | 2026-04-14 | 2026-04-14 | 1
55 | Edencroft |  | 2026-04-16 | 2026-04-19 | 2
55 | Edencroft |  | 2026-04-22 | 2026-04-26 | 3
55 | Edencroft |  | 2026-04-29 | 2026-05-02 | 3
55 | Edencroft |  | 2026-05-08 | 2026-05-09 | 1
55 | Edencroft |  | 2026-05-15 | 2026-05-16 | 1
55 | Edencroft |  | 2026-05-22 | 2026-05-23 | 1
55 | Edencroft |  | 2026-05-29 | 2026-05-30 | 1
55 | Edencroft |  | 2026-06-06 | 2026-06-07 | 1
55 | Edencroft |  | 2026-06-13 | 2026-06-14 | 1
55 | Edencroft |  | 2026-06-20 | 2026-06-21 | 1
55 | Edencroft |  | 2026-06-25 | 2026-06-28 | 2
56 | GPL |  | 2025-12-07 | 2025-12-15 | 6
56 | GPL |  | 2025-12-21 | 2025-12-22 | 1
56 | GPL |  | 2025-12-28 | 2025-12-29 | 1
56 | GPL |  | 2026-01-05 | 2026-01-06 | 2
56 | GPL |  | 2026-01-10 | 2026-01-13 | 2
56 | GPL |  | 2026-01-16 | 2026-01-22 | 5
56 | GPL |  | 2026-01-24 | 2026-01-27 | 2
56 | GPL |  | 2026-01-30 | 2026-02-04 | 4
56 | GPL |  | 2026-02-06 | 2026-02-10 | 3
56 | GPL |  | 2026-02-15 | 2026-02-19 | 4
56 | GPL |  | 2026-02-22 | 2026-02-25 | 3
56 | GPL |  | 2026-03-05 | 2026-03-07 | 2
56 | GPL |  | 2026-03-12 | 2026-03-14 | 2
56 | GPL |  | 2026-03-18 | 2026-03-21 | 3
56 | GPL |  | 2026-03-25 | 2026-03-28 | 3
56 | GPL |  | 2026-04-02 | 2026-04-05 | 2
56 | GPL |  | 2026-04-08 | 2026-04-09 | 2
56 | GPL |  | 2026-04-11 | 2026-04-12 | 1
56 | GPL |  | 2026-04-14 | 2026-04-14 | 1
56 | GPL |  | 2026-04-16 | 2026-04-19 | 2
56 | GPL |  | 2026-04-22 | 2026-04-26 | 3
56 | GPL |  | 2026-04-29 | 2026-05-02 | 3
56 | GPL |  | 2026-05-08 | 2026-05-09 | 1
56 | GPL |  | 2026-05-15 | 2026-05-16 | 1
56 | GPL |  | 2026-05-22 | 2026-05-23 | 1
56 | GPL |  | 2026-05-29 | 2026-05-30 | 1
56 | GPL |  | 2026-06-06 | 2026-06-07 | 1
56 | GPL |  | 2026-06-13 | 2026-06-14 | 1
56 | GPL |  | 2026-06-20 | 2026-06-21 | 1
56 | GPL |  | 2026-06-25 | 2026-06-28 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-07 | 2025-12-15 | 6
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-21 | 2025-12-22 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-28 | 2025-12-29 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-05 | 2026-01-06 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-10 | 2026-01-13 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-16 | 2026-01-22 | 5
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-24 | 2026-01-27 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-30 | 2026-02-04 | 4
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-02-06 | 2026-02-10 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-02-15 | 2026-02-17 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-02-22 | 2026-02-25 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-05 | 2026-03-07 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-12 | 2026-03-14 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-18 | 2026-03-21 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-25 | 2026-03-28 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-02 | 2026-04-05 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-08 | 2026-04-09 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-11 | 2026-04-12 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-14 | 2026-04-14 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-16 | 2026-04-19 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-22 | 2026-04-26 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-01 | 2026-05-02 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-08 | 2026-05-09 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-15 | 2026-05-16 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-22 | 2026-05-23 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-29 | 2026-05-30 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-06 | 2026-06-07 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-13 | 2026-06-14 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-20 | 2026-06-21 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-15 | 6
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-10 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-16 | 2026-01-22 | 5
| Amtico flooring /Bathrooms |  | 2026-01-24 | 2026-01-27 | 2
| Amtico flooring /Bathrooms |  | 2026-01-30 | 2026-02-04 | 4
| Amtico flooring /Bathrooms |  | 2026-02-06 | 2026-02-10 | 3
| Amtico flooring /Bathrooms |  | 2026-02-15 | 2026-02-17 | 2
| Amtico flooring /Bathrooms |  | 2026-02-22 | 2026-02-25 | 3
| Amtico flooring /Bathrooms |  | 2026-03-01 | 2026-03-07 | 5
| Amtico flooring /Bathrooms |  | 2026-03-12 | 2026-03-14 | 2
| Amtico flooring /Bathrooms |  | 2026-03-18 | 2026-03-21 | 3
| Amtico flooring /Bathrooms |  | 2026-03-25 | 2026-03-28 | 3
| Amtico flooring /Bathrooms |  | 2026-04-02 | 2026-04-05 | 2
| Amtico flooring /Bathrooms |  | 2026-04-08 | 2026-04-09 | 2
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-14 | 2026-04-14 | 1
| Amtico flooring /Bathrooms |  | 2026-04-16 | 2026-04-19 | 2
| Amtico flooring /Bathrooms |  | 2026-04-22 | 2026-04-26 | 3
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
57 | ARMSTRONG |  | 2025-12-07 | 2025-12-08 | 1
57 | ARMSTRONG |  | 2025-12-14 | 2025-12-15 | 1
57 | ARMSTRONG |  | 2025-12-21 | 2025-12-22 | 1
57 | ARMSTRONG |  | 2025-12-28 | 2025-12-29 | 1
57 | ARMSTRONG |  | 2026-01-05 | 2026-01-06 | 2
57 | ARMSTRONG |  | 2026-01-10 | 2026-01-13 | 2
57 | ARMSTRONG |  | 2026-01-16 | 2026-01-22 | 5
57 | ARMSTRONG |  | 2026-01-24 | 2026-01-27 | 2
57 | ARMSTRONG |  | 2026-01-30 | 2026-02-04 | 4
57 | ARMSTRONG |  | 2026-02-06 | 2026-02-10 | 3
57 | ARMSTRONG |  | 2026-02-15 | 2026-02-17 | 2
57 | ARMSTRONG |  | 2026-02-22 | 2026-02-25 | 3
57 | ARMSTRONG |  | 2026-03-06 | 2026-03-07 | 1
57 | ARMSTRONG |  | 2026-03-10 | 2026-03-16 | 5
57 | ARMSTRONG |  | 2026-03-20 | 2026-03-21 | 1
57 | ARMSTRONG |  | 2026-03-27 | 2026-03-28 | 1
57 | ARMSTRONG |  | 2026-04-04 | 2026-04-05 | 1
57 | ARMSTRONG |  | 2026-04-11 | 2026-04-12 | 1
57 | ARMSTRONG |  | 2026-04-18 | 2026-04-19 | 1
57 | ARMSTRONG |  | 2026-04-25 | 2026-04-26 | 1
57 | ARMSTRONG |  | 2026-05-01 | 2026-05-02 | 1
57 | ARMSTRONG |  | 2026-05-08 | 2026-05-09 | 1
57 | ARMSTRONG |  | 2026-05-15 | 2026-05-16 | 1
57 | ARMSTRONG |  | 2026-05-22 | 2026-05-23 | 1
57 | ARMSTRONG |  | 2026-05-29 | 2026-05-30 | 1
57 | ARMSTRONG |  | 2026-06-06 | 2026-06-07 | 1
57 | ARMSTRONG |  | 2026-06-13 | 2026-06-14 | 1
57 | ARMSTRONG |  | 2026-06-20 | 2026-06-21 | 1
57 | ARMSTRONG |  | 2026-06-25 | 2026-06-28 | 2
58 | Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-08 | 1
58 | Electrical 2nd fix & live testing |  | 2025-12-14 | 2025-12-15 | 1
58 | Electrical 2nd fix & live testing |  | 2025-12-21 | 2025-12-22 | 1
58 | Electrical 2nd fix & live testing |  | 2025-12-28 | 2025-12-29 | 1
58 | Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-06 | 2
58 | Electrical 2nd fix & live testing |  | 2026-01-10 | 2026-01-13 | 2
58 | Electrical 2nd fix & live testing |  | 2026-01-16 | 2026-01-22 | 5
58 | Electrical 2nd fix & live testing |  | 2026-01-24 | 2026-01-27 | 2
58 | Electrical 2nd fix & live testing |  | 2026-01-30 | 2026-02-04 | 4
58 | Electrical 2nd fix & live testing |  | 2026-02-06 | 2026-02-10 | 3
58 | Electrical 2nd fix & live testing |  | 2026-02-15 | 2026-02-17 | 2
58 | Electrical 2nd fix & live testing |  | 2026-02-22 | 2026-02-25 | 3
58 | Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
58 | Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
58 | Electrical 2nd fix & live testing |  | 2026-03-17 | 2026-03-23 | 5
58 | Electrical 2nd fix & live testing |  | 2026-03-27 | 2026-03-28 | 1
58 | Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
58 | Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
58 | Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
58 | Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
58 | Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
58 | Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
58 | Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
58 | Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
58 | Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
58 | Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
58 | Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
58 | Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
58 | Electrical 2nd fix & live testing |  | 2026-06-25 | 2026-06-28 | 2
59 | MCL |  | 2025-12-07 | 2025-12-08 | 1
59 | MCL |  | 2025-12-14 | 2025-12-15 | 1
59 | MCL |  | 2025-12-21 | 2025-12-22 | 1
59 | MCL |  | 2025-12-28 | 2025-12-29 | 1
59 | MCL |  | 2026-01-05 | 2026-01-06 | 2
59 | MCL |  | 2026-01-10 | 2026-01-13 | 2
59 | MCL |  | 2026-01-16 | 2026-01-22 | 5
59 | MCL |  | 2026-01-24 | 2026-01-27 | 2
59 | MCL |  | 2026-01-30 | 2026-02-04 | 4
59 | MCL |  | 2026-02-06 | 2026-02-10 | 3
59 | MCL |  | 2026-02-15 | 2026-02-17 | 2
59 | MCL |  | 2026-02-22 | 2026-02-25 | 3
59 | MCL |  | 2026-03-06 | 2026-03-07 | 1
59 | MCL |  | 2026-03-13 | 2026-03-14 | 1
59 | MCL |  | 2026-03-20 | 2026-03-21 | 1
59 | MCL |  | 2026-03-27 | 2026-03-28 | 1
59 | MCL |  | 2026-04-04 | 2026-04-05 | 1
59 | MCL |  | 2026-04-11 | 2026-04-12 | 1
59 | MCL |  | 2026-04-18 | 2026-04-19 | 1
59 | MCL |  | 2026-04-25 | 2026-04-26 | 1
59 | MCL |  | 2026-05-01 | 2026-05-02 | 1
59 | MCL |  | 2026-05-08 | 2026-05-09 | 1
59 | MCL |  | 2026-05-15 | 2026-05-16 | 1
59 | MCL |  | 2026-05-22 | 2026-05-23 | 1
59 | MCL |  | 2026-05-29 | 2026-05-30 | 1
59 | MCL |  | 2026-06-06 | 2026-06-07 | 1
59 | MCL |  | 2026-06-13 | 2026-06-14 | 1
59 | MCL |  | 2026-06-20 | 2026-06-21 | 1
59 | MCL |  | 2026-06-25 | 2026-06-28 | 2
60 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
60 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
60 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
60 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
60 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
60 | PANACEA |  | 2026-01-10 | 2026-01-13 | 2
60 | PANACEA |  | 2026-01-16 | 2026-01-22 | 5
60 | PANACEA |  | 2026-01-24 | 2026-01-27 | 2
60 | PANACEA |  | 2026-01-30 | 2026-02-04 | 4
60 | PANACEA |  | 2026-02-06 | 2026-02-10 | 3
60 | PANACEA |  | 2026-02-15 | 2026-02-17 | 2
60 | PANACEA |  | 2026-02-22 | 2026-02-25 | 3
60 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
60 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
60 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
60 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
60 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
60 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
60 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
60 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
60 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
60 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
60 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
60 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
60 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
60 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
60 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
60 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
60 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Decoration |  | 2025-12-07 | 2025-12-15 | 6
| Decoration |  | 2025-12-21 | 2025-12-22 | 1
| Decoration |  | 2025-12-28 | 2025-12-29 | 1
| Decoration |  | 2026-01-05 | 2026-01-06 | 2
| Decoration |  | 2026-01-10 | 2026-01-13 | 2
| Decoration |  | 2026-01-16 | 2026-01-22 | 5
| Decoration |  | 2026-01-24 | 2026-01-27 | 2
| Decoration |  | 2026-01-30 | 2026-02-04 | 4
| Decoration |  | 2026-02-06 | 2026-02-10 | 3
| Decoration |  | 2026-02-15 | 2026-02-17 | 2
| Decoration |  | 2026-02-22 | 2026-02-25 | 3
| Decoration |  | 2026-03-06 | 2026-03-07 | 1
| Decoration |  | 2026-03-13 | 2026-03-14 | 1
| Decoration |  | 2026-03-20 | 2026-03-21 | 1
| Decoration |  | 2026-03-24 | 2026-03-30 | 5
| Decoration |  | 2026-04-04 | 2026-04-05 | 1
| Decoration |  | 2026-04-11 | 2026-04-12 | 1
| Decoration |  | 2026-04-18 | 2026-04-19 | 1
| Decoration |  | 2026-04-25 | 2026-04-26 | 1
| Decoration |  | 2026-05-01 | 2026-05-02 | 1
| Decoration |  | 2026-05-08 | 2026-05-09 | 1
| Decoration |  | 2026-05-15 | 2026-05-16 | 1
| Decoration |  | 2026-05-22 | 2026-05-23 | 1
| Decoration |  | 2026-05-29 | 2026-05-30 | 1
| Decoration |  | 2026-06-06 | 2026-06-07 | 1
| Decoration |  | 2026-06-13 | 2026-06-14 | 1
| Decoration |  | 2026-06-20 | 2026-06-21 | 1
| Decoration |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Carpets |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Carpets |  | 2025-12-21 | 2025-12-25 | 4
| Amtico flooring /Carpets |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Carpets |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Carpets |  | 2026-01-10 | 2026-01-13 | 2
| Amtico flooring /Carpets |  | 2026-01-16 | 2026-01-22 | 5
| Amtico flooring /Carpets |  | 2026-01-24 | 2026-01-27 | 2
| Amtico flooring /Carpets |  | 2026-01-30 | 2026-02-04 | 4
| Amtico flooring /Carpets |  | 2026-02-06 | 2026-02-10 | 3
| Amtico flooring /Carpets |  | 2026-02-15 | 2026-02-17 | 2
| Amtico flooring /Carpets |  | 2026-02-22 | 2026-02-25 | 3
| Amtico flooring /Carpets |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Carpets |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Carpets |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Carpets |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Carpets |  | 2026-04-01 | 2026-04-05 | 3
| Amtico flooring /Carpets |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Carpets |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Carpets |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Carpets |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Carpets |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Carpets |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Carpets |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Carpets |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Carpets |  | 2026-06-25 | 2026-06-28 | 2
62 | De snag all trades - test & commision |  | 2025-12-07 | 2025-12-08 | 1
62 | De snag all trades - test & commision |  | 2025-12-14 | 2025-12-15 | 1
62 | De snag all trades - test & commision |  | 2025-12-21 | 2025-12-22 | 1
62 | De snag all trades - test & commision |  | 2025-12-28 | 2025-12-29 | 1
62 | De snag all trades - test & commision |  | 2026-01-05 | 2026-01-06 | 2
62 | De snag all trades - test & commision |  | 2026-01-10 | 2026-01-13 | 2
62 | De snag all trades - test & commision |  | 2026-01-16 | 2026-01-22 | 5
62 | De snag all trades - test & commision |  | 2026-01-24 | 2026-01-27 | 2
62 | De snag all trades - test & commision |  | 2026-01-30 | 2026-02-04 | 4
62 | De snag all trades - test & commision |  | 2026-02-06 | 2026-02-10 | 3
62 | De snag all trades - test & commision |  | 2026-02-15 | 2026-02-17 | 2
62 | De snag all trades - test & commision |  | 2026-02-22 | 2026-02-25 | 3
62 | De snag all trades - test & commision |  | 2026-03-06 | 2026-03-07 | 1
62 | De snag all trades - test & commision |  | 2026-03-13 | 2026-03-14 | 1
62 | De snag all trades - test & commision |  | 2026-03-20 | 2026-03-21 | 1
62 | De snag all trades - test & commision |  | 2026-03-27 | 2026-03-28 | 1
62 | De snag all trades - test & commision |  | 2026-04-04 | 2026-04-12 | 5
62 | De snag all trades - test & commision |  | 2026-04-18 | 2026-04-19 | 1
62 | De snag all trades - test & commision |  | 2026-04-25 | 2026-04-26 | 1
62 | De snag all trades - test & commision |  | 2026-05-01 | 2026-05-02 | 1
62 | De snag all trades - test & commision |  | 2026-05-08 | 2026-05-09 | 1
62 | De snag all trades - test & commision |  | 2026-05-15 | 2026-05-16 | 1
62 | De snag all trades - test & commision |  | 2026-05-22 | 2026-05-23 | 1
62 | De snag all trades - test & commision |  | 2026-05-29 | 2026-05-30 | 1
62 | De snag all trades - test & commision |  | 2026-06-06 | 2026-06-07 | 1
62 | De snag all trades - test & commision |  | 2026-06-13 | 2026-06-14 | 1
62 | De snag all trades - test & commision |  | 2026-06-20 | 2026-06-21 | 1
62 | De snag all trades - test & commision |  | 2026-06-25 | 2026-06-28 | 2
63 | MCL |  | 2025-12-07 | 2025-12-08 | 1
63 | MCL |  | 2025-12-14 | 2025-12-15 | 1
63 | MCL |  | 2025-12-17 | 2025-12-17 | 1
63 | MCL |  | 2025-12-21 | 2025-12-22 | 1
63 | MCL |  | 2025-12-28 | 2025-12-29 | 1
63 | MCL |  | 2026-01-05 | 2026-01-06 | 2
63 | MCL |  | 2026-01-10 | 2026-01-13 | 2
63 | MCL |  | 2026-01-16 | 2026-01-22 | 5
63 | MCL |  | 2026-01-24 | 2026-01-27 | 2
63 | MCL |  | 2026-01-30 | 2026-02-04 | 4
63 | MCL |  | 2026-02-06 | 2026-02-10 | 3
63 | MCL |  | 2026-02-15 | 2026-02-17 | 2
63 | MCL |  | 2026-02-22 | 2026-02-25 | 3
63 | MCL |  | 2026-03-06 | 2026-03-07 | 1
63 | MCL |  | 2026-03-13 | 2026-03-14 | 1
63 | MCL |  | 2026-03-20 | 2026-03-21 | 1
63 | MCL |  | 2026-03-27 | 2026-03-28 | 1
63 | MCL |  | 2026-04-04 | 2026-04-05 | 1
63 | MCL |  | 2026-04-11 | 2026-04-19 | 5
63 | MCL |  | 2026-04-25 | 2026-04-26 | 1
63 | MCL |  | 2026-05-01 | 2026-05-02 | 1
63 | MCL |  | 2026-05-08 | 2026-05-09 | 1
63 | MCL |  | 2026-05-15 | 2026-05-16 | 1
63 | MCL |  | 2026-05-22 | 2026-05-23 | 1
63 | MCL |  | 2026-05-29 | 2026-05-30 | 1
63 | MCL |  | 2026-06-06 | 2026-06-07 | 1
63 | MCL |  | 2026-06-13 | 2026-06-14 | 1
63 | MCL |  | 2026-06-20 | 2026-06-21 | 1
63 | MCL |  | 2026-06-25 | 2026-06-28 | 2
65 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
65 | PANACEA |  | 2025-12-14 | 2025-12-22 | 6
65 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
65 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
65 | PANACEA |  | 2026-01-10 | 2026-01-13 | 2
65 | PANACEA |  | 2026-01-16 | 2026-01-22 | 5
65 | PANACEA |  | 2026-01-24 | 2026-01-27 | 2
65 | PANACEA |  | 2026-01-30 | 2026-02-04 | 4
65 | PANACEA |  | 2026-02-06 | 2026-02-10 | 3
65 | PANACEA |  | 2026-02-15 | 2026-02-17 | 2
65 | PANACEA |  | 2026-02-22 | 2026-02-25 | 3
65 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
65 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
65 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
65 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
65 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
65 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
65 | PANACEA |  | 2026-04-18 | 2026-04-21 | 2
65 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
65 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
65 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
65 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
65 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
65 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
65 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
65 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
65 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
65 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-22 | 6
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-10 | 2026-01-13 | 2
| Handover to client |  | 2026-01-16 | 2026-01-22 | 5
| Handover to client |  | 2026-01-24 | 2026-01-27 | 2
| Handover to client |  | 2026-01-30 | 2026-02-04 | 4
| Handover to client |  | 2026-02-06 | 2026-02-10 | 3
| Handover to client |  | 2026-02-15 | 2026-02-17 | 2
| Handover to client |  | 2026-02-22 | 2026-02-25 | 3
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-03 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
| Level 3 Apartment fit out -cluster 2 |  | 2025-12-07 | 2025-12-08 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2025-12-14 | 2025-12-15 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2025-12-21 | 2025-12-22 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2025-12-26 | 2025-12-29 | 2
| Level 3 Apartment fit out -cluster 2 |  | 2026-01-05 | 2026-01-06 | 2
| Level 3 Apartment fit out -cluster 2 |  | 2026-01-10 | 2026-01-13 | 2
| Level 3 Apartment fit out -cluster 2 |  | 2026-01-16 | 2026-01-22 | 5
| Level 3 Apartment fit out -cluster 2 |  | 2026-01-24 | 2026-01-27 | 2
| Level 3 Apartment fit out -cluster 2 |  | 2026-01-30 | 2026-02-04 | 4
| Level 3 Apartment fit out -cluster 2 |  | 2026-02-06 | 2026-02-10 | 3
| Level 3 Apartment fit out -cluster 2 |  | 2026-02-15 | 2026-02-17 | 2
| Level 3 Apartment fit out -cluster 2 |  | 2026-02-22 | 2026-02-25 | 3
| Level 3 Apartment fit out -cluster 2 |  | 2026-03-06 | 2026-03-07 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-03-13 | 2026-03-14 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-03-20 | 2026-03-21 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-03-27 | 2026-03-28 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-04-04 | 2026-04-05 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-04-11 | 2026-04-12 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-04-18 | 2026-04-19 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-04-25 | 2026-04-26 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-05-01 | 2026-05-02 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-05-08 | 2026-05-09 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-05-15 | 2026-05-16 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-05-22 | 2026-05-23 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-05-29 | 2026-05-30 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-06-06 | 2026-06-07 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-06-13 | 2026-06-14 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-06-20 | 2026-06-21 | 1
| Level 3 Apartment fit out -cluster 2 |  | 2026-06-25 | 2026-06-28 | 2
| Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-08 | 1
| Levveling screed /smoothing compound |  | 2025-12-14 | 2025-12-15 | 1
| Levveling screed /smoothing compound |  | 2025-12-21 | 2025-12-22 | 1
| Levveling screed /smoothing compound |  | 2025-12-28 | 2026-01-08 | 9
| Levveling screed /smoothing compound |  | 2026-01-10 | 2026-01-13 | 2
| Levveling screed /smoothing compound |  | 2026-01-16 | 2026-01-22 | 5
| Levveling screed /smoothing compound |  | 2026-01-24 | 2026-01-27 | 2
| Levveling screed /smoothing compound |  | 2026-01-30 | 2026-02-04 | 4
| Levveling screed /smoothing compound |  | 2026-02-06 | 2026-02-17 | 8
| Levveling screed /smoothing compound |  | 2026-02-22 | 2026-02-25 | 3
| Levveling screed /smoothing compound |  | 2026-03-06 | 2026-03-07 | 1
| Levveling screed /smoothing compound |  | 2026-03-13 | 2026-03-14 | 1
| Levveling screed /smoothing compound |  | 2026-03-20 | 2026-03-21 | 1
| Levveling screed /smoothing compound |  | 2026-03-27 | 2026-03-28 | 1
| Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
| Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
| Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
| Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
| Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
| Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
| Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
| Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
| Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
| Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
| Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
| Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
| Levveling screed /smoothing compound |  | 2026-06-25 | 2026-06-28 | 2
66 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
66 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
66 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
66 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
66 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
66 | PANACEA |  | 2026-01-09 | 2026-01-13 | 3
66 | PANACEA |  | 2026-01-16 | 2026-01-22 | 5
66 | PANACEA |  | 2026-01-24 | 2026-01-27 | 2
66 | PANACEA |  | 2026-01-30 | 2026-02-04 | 4
66 | PANACEA |  | 2026-02-06 | 2026-02-10 | 3
66 | PANACEA |  | 2026-02-15 | 2026-02-17 | 2
66 | PANACEA |  | 2026-02-22 | 2026-02-25 | 3
66 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
66 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
66 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
66 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
66 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
66 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
66 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
66 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
66 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
66 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
66 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
66 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
66 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
66 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
66 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
66 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
66 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
67 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
67 | Active flooring |  | 2025-12-14 | 2025-12-15 | 1
67 | Active flooring |  | 2025-12-21 | 2025-12-22 | 1
67 | Active flooring |  | 2025-12-28 | 2025-12-29 | 1
67 | Active flooring |  | 2026-01-05 | 2026-01-22 | 14
67 | Active flooring |  | 2026-01-24 | 2026-01-27 | 2
67 | Active flooring |  | 2026-01-30 | 2026-02-04 | 4
67 | Active flooring |  | 2026-02-06 | 2026-02-10 | 3
67 | Active flooring |  | 2026-02-14 | 2026-02-18 | 3
67 | Active flooring |  | 2026-02-22 | 2026-02-25 | 3
67 | Active flooring |  | 2026-03-06 | 2026-03-07 | 1
67 | Active flooring |  | 2026-03-13 | 2026-03-14 | 1
67 | Active flooring |  | 2026-03-20 | 2026-03-21 | 1
67 | Active flooring |  | 2026-03-27 | 2026-03-28 | 1
67 | Active flooring |  | 2026-04-04 | 2026-04-05 | 1
67 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
67 | Active flooring |  | 2026-04-18 | 2026-04-19 | 1
67 | Active flooring |  | 2026-04-25 | 2026-04-26 | 1
67 | Active flooring |  | 2026-05-01 | 2026-05-02 | 1
67 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
67 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
67 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
67 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
67 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
67 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
67 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
67 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-08 | 1
| Vanity 1st fix framing |  | 2025-12-14 | 2025-12-15 | 1
| Vanity 1st fix framing |  | 2025-12-21 | 2025-12-22 | 1
| Vanity 1st fix framing |  | 2025-12-28 | 2025-12-29 | 1
| Vanity 1st fix framing |  | 2026-01-05 | 2026-01-22 | 14
| Vanity 1st fix framing |  | 2026-01-24 | 2026-01-27 | 2
| Vanity 1st fix framing |  | 2026-01-30 | 2026-02-04 | 4
| Vanity 1st fix framing |  | 2026-02-06 | 2026-02-10 | 3
| Vanity 1st fix framing |  | 2026-02-13 | 2026-02-17 | 3
| Vanity 1st fix framing |  | 2026-02-22 | 2026-02-25 | 3
| Vanity 1st fix framing |  | 2026-03-06 | 2026-03-07 | 1
| Vanity 1st fix framing |  | 2026-03-13 | 2026-03-14 | 1
| Vanity 1st fix framing |  | 2026-03-20 | 2026-03-21 | 1
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2026-06-25 | 2026-06-28 | 2
68 | MCL |  | 2025-12-07 | 2025-12-08 | 1
68 | MCL |  | 2025-12-14 | 2025-12-15 | 1
68 | MCL |  | 2025-12-21 | 2025-12-22 | 1
68 | MCL |  | 2025-12-28 | 2025-12-29 | 1
68 | MCL |  | 2026-01-05 | 2026-01-06 | 2
68 | MCL |  | 2026-01-12 | 2026-01-13 | 2
68 | MCL |  | 2026-01-16 | 2026-01-22 | 5
68 | MCL |  | 2026-01-24 | 2026-01-27 | 2
68 | MCL |  | 2026-01-30 | 2026-02-04 | 4
68 | MCL |  | 2026-02-06 | 2026-02-10 | 3
68 | MCL |  | 2026-02-15 | 2026-02-17 | 2
68 | MCL |  | 2026-02-22 | 2026-02-25 | 3
68 | MCL |  | 2026-03-01 | 2026-03-04 | 3
68 | MCL |  | 2026-03-06 | 2026-03-07 | 1
68 | MCL |  | 2026-03-13 | 2026-03-14 | 1
68 | MCL |  | 2026-03-20 | 2026-03-21 | 1
68 | MCL |  | 2026-03-27 | 2026-03-28 | 1
68 | MCL |  | 2026-04-04 | 2026-04-05 | 1
68 | MCL |  | 2026-04-11 | 2026-04-12 | 1
68 | MCL |  | 2026-04-18 | 2026-04-19 | 1
68 | MCL |  | 2026-04-25 | 2026-04-26 | 1
68 | MCL |  | 2026-05-01 | 2026-05-02 | 1
68 | MCL |  | 2026-05-08 | 2026-05-09 | 1
68 | MCL |  | 2026-05-15 | 2026-05-16 | 1
68 | MCL |  | 2026-05-22 | 2026-05-23 | 1
68 | MCL |  | 2026-05-29 | 2026-05-30 | 1
68 | MCL |  | 2026-06-06 | 2026-06-07 | 1
68 | MCL |  | 2026-06-13 | 2026-06-14 | 1
68 | MCL |  | 2026-06-20 | 2026-06-21 | 1
68 | MCL |  | 2026-06-25 | 2026-06-28 | 2
69 | Smiths |  | 2025-12-07 | 2025-12-08 | 1
69 | Smiths |  | 2025-12-14 | 2025-12-15 | 1
69 | Smiths |  | 2025-12-21 | 2025-12-22 | 1
69 | Smiths |  | 2025-12-28 | 2025-12-29 | 1
69 | Smiths |  | 2026-01-05 | 2026-01-13 | 7
69 | Smiths |  | 2026-01-18 | 2026-01-22 | 4
69 | Smiths |  | 2026-01-24 | 2026-01-27 | 2
69 | Smiths |  | 2026-01-30 | 2026-02-04 | 4
69 | Smiths |  | 2026-02-06 | 2026-02-10 | 3
69 | Smiths |  | 2026-02-15 | 2026-02-17 | 2
69 | Smiths |  | 2026-02-22 | 2026-02-25 | 3
69 | Smiths |  | 2026-02-28 | 2026-03-03 | 2
69 | Smiths |  | 2026-03-06 | 2026-03-07 | 1
69 | Smiths |  | 2026-03-13 | 2026-03-14 | 1
69 | Smiths |  | 2026-03-20 | 2026-03-21 | 1
69 | Smiths |  | 2026-03-27 | 2026-03-28 | 1
69 | Smiths |  | 2026-04-04 | 2026-04-05 | 1
69 | Smiths |  | 2026-04-11 | 2026-04-12 | 1
69 | Smiths |  | 2026-04-18 | 2026-04-19 | 1
69 | Smiths |  | 2026-04-25 | 2026-04-26 | 1
69 | Smiths |  | 2026-05-01 | 2026-05-02 | 1
69 | Smiths |  | 2026-05-08 | 2026-05-09 | 1
69 | Smiths |  | 2026-05-15 | 2026-05-16 | 1
69 | Smiths |  | 2026-05-22 | 2026-05-23 | 1
69 | Smiths |  | 2026-05-29 | 2026-05-30 | 1
69 | Smiths |  | 2026-06-06 | 2026-06-07 | 1
69 | Smiths |  | 2026-06-13 | 2026-06-14 | 1
69 | Smiths |  | 2026-06-20 | 2026-06-21 | 1
69 | Smiths |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-05 | 2026-01-13 | 7
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-18 | 2026-01-22 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-24 | 2026-01-27 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-30 | 2026-02-04 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-06 | 2026-02-10 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-15 | 2026-02-17 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-02-20 | 2026-02-27 | 6
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
70 | MCL |  | 2025-12-07 | 2025-12-08 | 1
70 | MCL |  | 2025-12-14 | 2025-12-15 | 1
70 | MCL |  | 2025-12-21 | 2025-12-22 | 1
70 | MCL |  | 2025-12-28 | 2025-12-29 | 1
70 | MCL |  | 2026-01-05 | 2026-01-06 | 2
70 | MCL |  | 2026-01-08 | 2026-01-13 | 4
70 | MCL |  | 2026-01-16 | 2026-01-22 | 5
70 | MCL |  | 2026-01-24 | 2026-01-29 | 4
70 | MCL |  | 2026-02-02 | 2026-02-03 | 2
70 | MCL |  | 2026-02-06 | 2026-02-10 | 3
70 | MCL |  | 2026-02-15 | 2026-02-17 | 2
70 | MCL |  | 2026-02-22 | 2026-02-25 | 3
70 | MCL |  | 2026-02-28 | 2026-03-03 | 2
70 | MCL |  | 2026-03-06 | 2026-03-07 | 1
70 | MCL |  | 2026-03-13 | 2026-03-14 | 1
70 | MCL |  | 2026-03-20 | 2026-03-21 | 1
70 | MCL |  | 2026-03-27 | 2026-03-28 | 1
70 | MCL |  | 2026-04-04 | 2026-04-05 | 1
70 | MCL |  | 2026-04-11 | 2026-04-12 | 1
70 | MCL |  | 2026-04-18 | 2026-04-19 | 1
70 | MCL |  | 2026-04-25 | 2026-04-26 | 1
70 | MCL |  | 2026-05-01 | 2026-05-02 | 1
70 | MCL |  | 2026-05-08 | 2026-05-09 | 1
70 | MCL |  | 2026-05-15 | 2026-05-16 | 1
70 | MCL |  | 2026-05-22 | 2026-05-23 | 1
70 | MCL |  | 2026-05-29 | 2026-05-30 | 1
70 | MCL |  | 2026-06-06 | 2026-06-07 | 1
70 | MCL |  | 2026-06-13 | 2026-06-14 | 1
70 | MCL |  | 2026-06-20 | 2026-06-21 | 1
70 | MCL |  | 2026-06-25 | 2026-06-28 | 2
| service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-08 | 1
| service cupbaord -plywood flooring |  | 2025-12-14 | 2025-12-15 | 1
| service cupbaord -plywood flooring |  | 2025-12-21 | 2025-12-22 | 1
| service cupbaord -plywood flooring |  | 2025-12-28 | 2025-12-29 | 1
| service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-06 | 2
| service cupbaord -plywood flooring |  | 2026-01-12 | 2026-01-13 | 2
| service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-21 | 3
| service cupbaord -plywood flooring |  | 2026-01-24 | 2026-02-10 | 12
| service cupbaord -plywood flooring |  | 2026-02-15 | 2026-02-17 | 2
| service cupbaord -plywood flooring |  | 2026-02-22 | 2026-02-25 | 3
| service cupbaord -plywood flooring |  | 2026-03-02 | 2026-03-03 | 2
| service cupbaord -plywood flooring |  | 2026-03-06 | 2026-03-07 | 1
| service cupbaord -plywood flooring |  | 2026-03-13 | 2026-03-14 | 1
| service cupbaord -plywood flooring |  | 2026-03-20 | 2026-03-21 | 1
| service cupbaord -plywood flooring |  | 2026-03-27 | 2026-03-28 | 1
| service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
| service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
| service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
| service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
| service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
| service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
| service cupbaord -plywood flooring |  | 2026-05-15 | 2026-05-16 | 1
| service cupbaord -plywood flooring |  | 2026-05-22 | 2026-05-23 | 1
| service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
| service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
| service cupbaord -plywood flooring |  | 2026-06-13 | 2026-06-14 | 1
| service cupbaord -plywood flooring |  | 2026-06-20 | 2026-06-21 | 1
| service cupbaord -plywood flooring |  | 2026-06-25 | 2026-06-28 | 2
| service cupboard decoration |  | 2025-12-07 | 2025-12-08 | 1
| service cupboard decoration |  | 2025-12-14 | 2025-12-15 | 1
| service cupboard decoration |  | 2025-12-21 | 2025-12-22 | 1
| service cupboard decoration |  | 2025-12-28 | 2025-12-29 | 1
| service cupboard decoration |  | 2026-01-05 | 2026-01-06 | 2
| service cupboard decoration |  | 2026-01-12 | 2026-01-13 | 2
| service cupboard decoration |  | 2026-01-19 | 2026-01-21 | 3
| service cupboard decoration |  | 2026-01-23 | 2026-02-10 | 13
| service cupboard decoration |  | 2026-02-15 | 2026-02-17 | 2
| service cupboard decoration |  | 2026-02-22 | 2026-02-25 | 3
| service cupboard decoration |  | 2026-03-04 | 2026-03-07 | 3
| service cupboard decoration |  | 2026-03-13 | 2026-03-14 | 1
| service cupboard decoration |  | 2026-03-20 | 2026-03-21 | 1
| service cupboard decoration |  | 2026-03-27 | 2026-03-28 | 1
| service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
| service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
| service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
| service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
| service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
| service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
| service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
| service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
| service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
| service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
| service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
| service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
| service cupboard decoration |  | 2026-06-25 | 2026-06-28 | 2
72 | Branniff |  | 2025-12-07 | 2025-12-08 | 1
72 | Branniff |  | 2025-12-14 | 2025-12-15 | 1
72 | Branniff |  | 2025-12-21 | 2025-12-22 | 1
72 | Branniff |  | 2025-12-28 | 2025-12-29 | 1
72 | Branniff |  | 2026-01-05 | 2026-01-06 | 2
72 | Branniff |  | 2026-01-12 | 2026-01-13 | 2
72 | Branniff |  | 2026-01-19 | 2026-02-03 | 12
72 | Branniff |  | 2026-02-06 | 2026-02-10 | 3
72 | Branniff |  | 2026-02-15 | 2026-02-17 | 2
72 | Branniff |  | 2026-02-22 | 2026-02-25 | 3
72 | Branniff |  | 2026-03-06 | 2026-03-07 | 1
72 | Branniff |  | 2026-03-13 | 2026-03-14 | 1
72 | Branniff |  | 2026-03-20 | 2026-03-21 | 1
72 | Branniff |  | 2026-03-27 | 2026-03-28 | 1
72 | Branniff |  | 2026-04-04 | 2026-04-05 | 1
72 | Branniff |  | 2026-04-11 | 2026-04-12 | 1
72 | Branniff |  | 2026-04-18 | 2026-04-19 | 1
72 | Branniff |  | 2026-04-25 | 2026-04-26 | 1
72 | Branniff |  | 2026-05-01 | 2026-05-02 | 1
72 | Branniff |  | 2026-05-08 | 2026-05-09 | 1
72 | Branniff |  | 2026-05-15 | 2026-05-16 | 1
72 | Branniff |  | 2026-05-22 | 2026-05-23 | 1
72 | Branniff |  | 2026-05-29 | 2026-05-30 | 1
72 | Branniff |  | 2026-06-06 | 2026-06-07 | 1
72 | Branniff |  | 2026-06-13 | 2026-06-14 | 1
72 | Branniff |  | 2026-06-20 | 2026-06-21 | 1
72 | Branniff |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-02-03 | 12
| Amtico flooring /Bathrooms |  | 2026-02-06 | 2026-02-10 | 3
| Amtico flooring /Bathrooms |  | 2026-02-15 | 2026-02-17 | 2
| Amtico flooring /Bathrooms |  | 2026-02-22 | 2026-02-25 | 3
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-14 | 6
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-23 | 2026-02-03 | 8
| Plumbing second fix sanitaryware & pressure testing |  | 2026-02-06 | 2026-02-10 | 3
| Plumbing second fix sanitaryware & pressure testing |  | 2026-02-15 | 2026-02-17 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-02-22 | 2026-02-25 | 3
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-17 | 2026-03-23 | 5
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-25 | 2026-06-28 | 2
| Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-08 | 1
| Electrical 2nd fix & live testing |  | 2025-12-14 | 2025-12-15 | 1
| Electrical 2nd fix & live testing |  | 2025-12-21 | 2025-12-22 | 1
| Electrical 2nd fix & live testing |  | 2025-12-28 | 2025-12-29 | 1
| Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-06 | 2
| Electrical 2nd fix & live testing |  | 2026-01-12 | 2026-01-13 | 2
| Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
| Electrical 2nd fix & live testing |  | 2026-01-23 | 2026-02-03 | 8
| Electrical 2nd fix & live testing |  | 2026-02-06 | 2026-02-10 | 3
| Electrical 2nd fix & live testing |  | 2026-02-15 | 2026-02-17 | 2
| Electrical 2nd fix & live testing |  | 2026-02-22 | 2026-02-25 | 3
| Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
| Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
| Electrical 2nd fix & live testing |  | 2026-03-20 | 2026-03-21 | 1
| Electrical 2nd fix & live testing |  | 2026-03-24 | 2026-03-30 | 5
| Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
| Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
| Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
| Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
| Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
| Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
| Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
| Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
| Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
| Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
| Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
| Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
| Electrical 2nd fix & live testing |  | 2026-06-25 | 2026-06-28 | 2
| Builders clean |  | 2025-12-07 | 2025-12-08 | 1
| Builders clean |  | 2025-12-14 | 2025-12-15 | 1
| Builders clean |  | 2025-12-21 | 2025-12-22 | 1
| Builders clean |  | 2025-12-28 | 2025-12-29 | 1
| Builders clean |  | 2026-01-05 | 2026-01-06 | 2
| Builders clean |  | 2026-01-12 | 2026-01-13 | 2
| Builders clean |  | 2026-01-19 | 2026-01-21 | 3
| Builders clean |  | 2026-01-23 | 2026-02-10 | 13
| Builders clean |  | 2026-02-16 | 2026-02-17 | 2
| Builders clean |  | 2026-02-22 | 2026-02-25 | 3
| Builders clean |  | 2026-03-06 | 2026-03-07 | 1
| Builders clean |  | 2026-03-13 | 2026-03-14 | 1
| Builders clean |  | 2026-03-20 | 2026-03-21 | 1
| Builders clean |  | 2026-03-27 | 2026-03-28 | 1
| Builders clean |  | 2026-04-04 | 2026-04-05 | 1
| Builders clean |  | 2026-04-11 | 2026-04-12 | 1
| Builders clean |  | 2026-04-18 | 2026-04-19 | 1
| Builders clean |  | 2026-04-25 | 2026-04-26 | 1
| Builders clean |  | 2026-05-01 | 2026-05-02 | 1
| Builders clean |  | 2026-05-08 | 2026-05-09 | 1
| Builders clean |  | 2026-05-15 | 2026-05-16 | 1
| Builders clean |  | 2026-05-22 | 2026-05-23 | 1
| Builders clean |  | 2026-05-29 | 2026-05-30 | 1
| Builders clean |  | 2026-06-06 | 2026-06-07 | 1
| Builders clean |  | 2026-06-13 | 2026-06-14 | 1
| Builders clean |  | 2026-06-20 | 2026-06-21 | 1
| Builders clean |  | 2026-06-25 | 2026-06-28 | 2
| Pre -dec -snagging |  | 2025-12-07 | 2025-12-08 | 1
| Pre -dec -snagging |  | 2025-12-14 | 2025-12-15 | 1
| Pre -dec -snagging |  | 2025-12-21 | 2025-12-22 | 1
| Pre -dec -snagging |  | 2025-12-28 | 2025-12-29 | 1
| Pre -dec -snagging |  | 2026-01-05 | 2026-01-06 | 2
| Pre -dec -snagging |  | 2026-01-12 | 2026-01-13 | 2
| Pre -dec -snagging |  | 2026-01-19 | 2026-01-21 | 3
| Pre -dec -snagging |  | 2026-01-23 | 2026-02-04 | 9
| Pre -dec -snagging |  | 2026-02-06 | 2026-02-10 | 3
| Pre -dec -snagging |  | 2026-02-16 | 2026-02-17 | 2
| Pre -dec -snagging |  | 2026-02-22 | 2026-02-25 | 3
| Pre -dec -snagging |  | 2026-03-06 | 2026-03-07 | 1
| Pre -dec -snagging |  | 2026-03-13 | 2026-03-14 | 1
| Pre -dec -snagging |  | 2026-03-20 | 2026-03-21 | 1
| Pre -dec -snagging |  | 2026-03-27 | 2026-03-28 | 1
| Pre -dec -snagging |  | 2026-04-04 | 2026-04-05 | 1
| Pre -dec -snagging |  | 2026-04-11 | 2026-04-12 | 1
| Pre -dec -snagging |  | 2026-04-18 | 2026-04-19 | 1
| Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
| Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
| Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
| Pre -dec -snagging |  | 2026-05-15 | 2026-05-16 | 1
| Pre -dec -snagging |  | 2026-05-22 | 2026-05-23 | 1
| Pre -dec -snagging |  | 2026-05-29 | 2026-05-30 | 1
| Pre -dec -snagging |  | 2026-06-06 | 2026-06-07 | 1
| Pre -dec -snagging |  | 2026-06-13 | 2026-06-14 | 1
| Pre -dec -snagging |  | 2026-06-20 | 2026-06-21 | 1
| Pre -dec -snagging |  | 2026-06-25 | 2026-06-28 | 2
| Decoration |  | 2025-12-07 | 2025-12-08 | 1
| Decoration |  | 2025-12-14 | 2025-12-15 | 1
| Decoration |  | 2025-12-21 | 2025-12-22 | 1
| Decoration |  | 2025-12-28 | 2025-12-29 | 1
| Decoration |  | 2026-01-05 | 2026-01-06 | 2
| Decoration |  | 2026-01-12 | 2026-01-13 | 2
| Decoration |  | 2026-01-19 | 2026-01-21 | 3
| Decoration |  | 2026-01-23 | 2026-02-04 | 9
| Decoration |  | 2026-02-06 | 2026-02-10 | 3
| Decoration |  | 2026-02-16 | 2026-02-17 | 2
| Decoration |  | 2026-02-22 | 2026-02-25 | 3
| Decoration |  | 2026-03-06 | 2026-03-07 | 1
| Decoration |  | 2026-03-13 | 2026-03-14 | 1
| Decoration |  | 2026-03-20 | 2026-03-21 | 1
| Decoration |  | 2026-03-27 | 2026-03-28 | 1
| Decoration |  | 2026-04-01 | 2026-04-07 | 5
| Decoration |  | 2026-04-11 | 2026-04-12 | 1
| Decoration |  | 2026-04-18 | 2026-04-19 | 1
| Decoration |  | 2026-04-25 | 2026-04-26 | 1
| Decoration |  | 2026-05-01 | 2026-05-02 | 1
| Decoration |  | 2026-05-08 | 2026-05-09 | 1
| Decoration |  | 2026-05-15 | 2026-05-16 | 1
| Decoration |  | 2026-05-22 | 2026-05-23 | 1
| Decoration |  | 2026-05-29 | 2026-05-30 | 1
| Decoration |  | 2026-06-06 | 2026-06-07 | 1
| Decoration |  | 2026-06-13 | 2026-06-14 | 1
| Decoration |  | 2026-06-20 | 2026-06-21 | 1
| Decoration |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Carpets |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Carpets |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Carpets |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Carpets |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Carpets |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Carpets |  | 2026-01-19 | 2026-01-21 | 3
| Amtico flooring /Carpets |  | 2026-01-23 | 2026-02-04 | 9
| Amtico flooring /Carpets |  | 2026-02-06 | 2026-02-10 | 3
| Amtico flooring /Carpets |  | 2026-02-15 | 2026-02-17 | 2
| Amtico flooring /Carpets |  | 2026-02-22 | 2026-02-25 | 3
| Amtico flooring /Carpets |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Carpets |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Carpets |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Carpets |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Carpets |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Carpets |  | 2026-04-08 | 2026-04-12 | 3
| Amtico flooring /Carpets |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Carpets |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Carpets |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Carpets |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Carpets |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Carpets |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Carpets |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Carpets |  | 2026-06-25 | 2026-06-28 | 2
| De snag all trades test & commision |  | 2025-12-07 | 2025-12-08 | 1
| De snag all trades test & commision |  | 2025-12-14 | 2025-12-15 | 1
| De snag all trades test & commision |  | 2025-12-21 | 2025-12-22 | 1
| De snag all trades test & commision |  | 2025-12-28 | 2025-12-29 | 1
| De snag all trades test & commision |  | 2026-01-05 | 2026-01-06 | 2
| De snag all trades test & commision |  | 2026-01-12 | 2026-01-13 | 2
| De snag all trades test & commision |  | 2026-01-19 | 2026-01-21 | 3
| De snag all trades test & commision |  | 2026-01-23 | 2026-02-04 | 9
| De snag all trades test & commision |  | 2026-02-06 | 2026-02-10 | 3
| De snag all trades test & commision |  | 2026-02-15 | 2026-02-17 | 2
| De snag all trades test & commision |  | 2026-02-22 | 2026-02-25 | 3
| De snag all trades test & commision |  | 2026-03-06 | 2026-03-07 | 1
| De snag all trades test & commision |  | 2026-03-13 | 2026-03-14 | 1
| De snag all trades test & commision |  | 2026-03-20 | 2026-03-21 | 1
| De snag all trades test & commision |  | 2026-03-27 | 2026-03-28 | 1
| De snag all trades test & commision |  | 2026-04-04 | 2026-04-05 | 1
| De snag all trades test & commision |  | 2026-04-11 | 2026-04-19 | 5
| De snag all trades test & commision |  | 2026-04-25 | 2026-04-26 | 1
| De snag all trades test & commision |  | 2026-05-01 | 2026-05-02 | 1
| De snag all trades test & commision |  | 2026-05-08 | 2026-05-09 | 1
| De snag all trades test & commision |  | 2026-05-15 | 2026-05-16 | 1
| De snag all trades test & commision |  | 2026-05-22 | 2026-05-23 | 1
| De snag all trades test & commision |  | 2026-05-29 | 2026-05-30 | 1
| De snag all trades test & commision |  | 2026-06-06 | 2026-06-07 | 1
| De snag all trades test & commision |  | 2026-06-13 | 2026-06-14 | 1
| De snag all trades test & commision |  | 2026-06-20 | 2026-06-21 | 1
| De snag all trades test & commision |  | 2026-06-25 | 2026-06-28 | 2
| Sparkle clean |  | 2025-12-07 | 2025-12-08 | 1
| Sparkle clean |  | 2025-12-14 | 2025-12-15 | 1
| Sparkle clean |  | 2025-12-21 | 2025-12-22 | 1
| Sparkle clean |  | 2025-12-28 | 2025-12-29 | 1
| Sparkle clean |  | 2026-01-05 | 2026-01-06 | 2
| Sparkle clean |  | 2026-01-12 | 2026-01-13 | 2
| Sparkle clean |  | 2026-01-19 | 2026-01-21 | 3
| Sparkle clean |  | 2026-01-23 | 2026-02-04 | 9
| Sparkle clean |  | 2026-02-06 | 2026-02-10 | 3
| Sparkle clean |  | 2026-02-15 | 2026-02-17 | 2
| Sparkle clean |  | 2026-02-22 | 2026-02-25 | 3
| Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
| Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
| Sparkle clean |  | 2026-03-20 | 2026-03-21 | 1
| Sparkle clean |  | 2026-03-27 | 2026-03-28 | 1
| Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
| Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
| Sparkle clean |  | 2026-04-18 | 2026-04-26 | 5
| Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
| Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
| Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
| Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
| Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
| Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
| Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
| Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
| Sparkle clean |  | 2026-06-25 | 2026-06-28 | 2
73 | Mastic |  | 2025-12-07 | 2025-12-08 | 1
73 | Mastic |  | 2025-12-14 | 2025-12-15 | 1
73 | Mastic |  | 2025-12-21 | 2025-12-22 | 1
73 | Mastic |  | 2025-12-28 | 2025-12-29 | 1
73 | Mastic |  | 2026-01-05 | 2026-01-06 | 2
73 | Mastic |  | 2026-01-12 | 2026-01-13 | 2
73 | Mastic |  | 2026-01-19 | 2026-01-21 | 3
73 | Mastic |  | 2026-01-23 | 2026-02-04 | 9
73 | Mastic |  | 2026-02-06 | 2026-02-10 | 3
73 | Mastic |  | 2026-02-15 | 2026-02-17 | 2
73 | Mastic |  | 2026-02-22 | 2026-02-25 | 3
73 | Mastic |  | 2026-03-06 | 2026-03-07 | 1
73 | Mastic |  | 2026-03-13 | 2026-03-14 | 1
73 | Mastic |  | 2026-03-20 | 2026-03-21 | 1
73 | Mastic |  | 2026-03-27 | 2026-03-28 | 1
73 | Mastic |  | 2026-04-04 | 2026-04-05 | 1
73 | Mastic |  | 2026-04-11 | 2026-04-12 | 1
73 | Mastic |  | 2026-04-18 | 2026-04-19 | 1
73 | Mastic |  | 2026-04-25 | 2026-04-28 | 2
73 | Mastic |  | 2026-05-01 | 2026-05-02 | 1
73 | Mastic |  | 2026-05-08 | 2026-05-09 | 1
73 | Mastic |  | 2026-05-15 | 2026-05-16 | 1
73 | Mastic |  | 2026-05-22 | 2026-05-23 | 1
73 | Mastic |  | 2026-05-29 | 2026-05-30 | 1
73 | Mastic |  | 2026-06-06 | 2026-06-07 | 1
73 | Mastic |  | 2026-06-13 | 2026-06-14 | 1
73 | Mastic |  | 2026-06-20 | 2026-06-21 | 1
73 | Mastic |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-15 | 1
| Handover to client |  | 2025-12-21 | 2025-12-22 | 1
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-12 | 2026-01-13 | 2
| Handover to client |  | 2026-01-19 | 2026-01-21 | 3
| Handover to client |  | 2026-01-23 | 2026-02-04 | 9
| Handover to client |  | 2026-02-06 | 2026-02-10 | 3
| Handover to client |  | 2026-02-15 | 2026-02-17 | 2
| Handover to client |  | 2026-02-22 | 2026-02-25 | 3
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-10 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
74 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
74 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
74 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
74 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
74 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
74 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
74 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
74 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
74 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
74 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
74 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
74 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
74 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
74 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
74 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
74 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
74 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
74 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
74 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
74 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
74 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
74 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
74 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
74 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
74 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
75 | Edencroft |  | 2025-12-07 | 2025-12-08 | 1
75 | Edencroft |  | 2025-12-14 | 2025-12-15 | 1
75 | Edencroft |  | 2025-12-21 | 2025-12-22 | 1
75 | Edencroft |  | 2025-12-28 | 2025-12-29 | 1
75 | Edencroft |  | 2026-01-05 | 2026-01-06 | 2
75 | Edencroft |  | 2026-01-12 | 2026-01-13 | 2
75 | Edencroft |  | 2026-01-19 | 2026-01-21 | 3
75 | Edencroft |  | 2026-01-25 | 2026-03-03 | 27
75 | Edencroft |  | 2026-03-06 | 2026-03-07 | 1
75 | Edencroft |  | 2026-03-13 | 2026-03-14 | 1
75 | Edencroft |  | 2026-03-20 | 2026-03-21 | 1
75 | Edencroft |  | 2026-03-27 | 2026-03-28 | 1
75 | Edencroft |  | 2026-04-04 | 2026-04-05 | 1
75 | Edencroft |  | 2026-04-11 | 2026-04-12 | 1
75 | Edencroft |  | 2026-04-18 | 2026-04-19 | 1
75 | Edencroft |  | 2026-04-25 | 2026-04-26 | 1
75 | Edencroft |  | 2026-05-01 | 2026-05-02 | 1
75 | Edencroft |  | 2026-05-08 | 2026-05-09 | 1
75 | Edencroft |  | 2026-05-15 | 2026-05-16 | 1
75 | Edencroft |  | 2026-05-22 | 2026-05-23 | 1
75 | Edencroft |  | 2026-05-29 | 2026-05-30 | 1
75 | Edencroft |  | 2026-06-06 | 2026-06-07 | 1
75 | Edencroft |  | 2026-06-13 | 2026-06-14 | 1
75 | Edencroft |  | 2026-06-20 | 2026-06-21 | 1
75 | Edencroft |  | 2026-06-25 | 2026-06-28 | 2
76 | GPL |  | 2025-12-07 | 2025-12-08 | 1
76 | GPL |  | 2025-12-14 | 2025-12-15 | 1
76 | GPL |  | 2025-12-21 | 2025-12-22 | 1
76 | GPL |  | 2025-12-28 | 2025-12-29 | 1
76 | GPL |  | 2026-01-05 | 2026-01-06 | 2
76 | GPL |  | 2026-01-12 | 2026-01-13 | 2
76 | GPL |  | 2026-01-19 | 2026-01-21 | 3
76 | GPL |  | 2026-01-25 | 2026-03-03 | 27
76 | GPL |  | 2026-03-06 | 2026-03-07 | 1
76 | GPL |  | 2026-03-13 | 2026-03-14 | 1
76 | GPL |  | 2026-03-20 | 2026-03-21 | 1
76 | GPL |  | 2026-03-27 | 2026-03-28 | 1
76 | GPL |  | 2026-04-04 | 2026-04-05 | 1
76 | GPL |  | 2026-04-11 | 2026-04-12 | 1
76 | GPL |  | 2026-04-18 | 2026-04-19 | 1
76 | GPL |  | 2026-04-25 | 2026-04-26 | 1
76 | GPL |  | 2026-05-01 | 2026-05-02 | 1
76 | GPL |  | 2026-05-08 | 2026-05-09 | 1
76 | GPL |  | 2026-05-15 | 2026-05-16 | 1
76 | GPL |  | 2026-05-22 | 2026-05-23 | 1
76 | GPL |  | 2026-05-29 | 2026-05-30 | 1
76 | GPL |  | 2026-06-06 | 2026-06-07 | 1
76 | GPL |  | 2026-06-13 | 2026-06-14 | 1
76 | GPL |  | 2026-06-20 | 2026-06-21 | 1
76 | GPL |  | 2026-06-25 | 2026-06-28 | 2
77 | ARMSTRONG |  | 2025-12-07 | 2025-12-08 | 1
77 | ARMSTRONG |  | 2025-12-10 | 2025-12-11 | 2
77 | ARMSTRONG |  | 2025-12-14 | 2025-12-15 | 1
77 | ARMSTRONG |  | 2025-12-21 | 2025-12-22 | 1
77 | ARMSTRONG |  | 2025-12-28 | 2025-12-29 | 1
77 | ARMSTRONG |  | 2026-01-05 | 2026-01-06 | 2
77 | ARMSTRONG |  | 2026-01-12 | 2026-01-13 | 2
77 | ARMSTRONG |  | 2026-01-19 | 2026-01-21 | 3
77 | ARMSTRONG |  | 2026-01-25 | 2026-03-03 | 27
77 | ARMSTRONG |  | 2026-03-06 | 2026-03-07 | 1
77 | ARMSTRONG |  | 2026-03-13 | 2026-03-14 | 1
77 | ARMSTRONG |  | 2026-03-20 | 2026-03-21 | 1
77 | ARMSTRONG |  | 2026-03-27 | 2026-03-28 | 1
77 | ARMSTRONG |  | 2026-04-04 | 2026-04-05 | 1
77 | ARMSTRONG |  | 2026-04-11 | 2026-04-12 | 1
77 | ARMSTRONG |  | 2026-04-18 | 2026-04-19 | 1
77 | ARMSTRONG |  | 2026-04-25 | 2026-04-26 | 1
77 | ARMSTRONG |  | 2026-05-01 | 2026-05-02 | 1
77 | ARMSTRONG |  | 2026-05-08 | 2026-05-09 | 1
77 | ARMSTRONG |  | 2026-05-15 | 2026-05-16 | 1
77 | ARMSTRONG |  | 2026-05-22 | 2026-05-23 | 1
77 | ARMSTRONG |  | 2026-05-29 | 2026-05-30 | 1
77 | ARMSTRONG |  | 2026-06-06 | 2026-06-07 | 1
77 | ARMSTRONG |  | 2026-06-13 | 2026-06-14 | 1
77 | ARMSTRONG |  | 2026-06-20 | 2026-06-21 | 1
77 | ARMSTRONG |  | 2026-06-25 | 2026-06-28 | 2
| Ceilings board |  | 2025-12-07 | 2025-12-15 | 6
| Ceilings board |  | 2025-12-21 | 2025-12-22 | 1
| Ceilings board |  | 2025-12-28 | 2025-12-29 | 1
| Ceilings board |  | 2026-01-05 | 2026-01-06 | 2
| Ceilings board |  | 2026-01-12 | 2026-01-13 | 2
| Ceilings board |  | 2026-01-19 | 2026-01-21 | 3
| Ceilings board |  | 2026-01-25 | 2026-03-03 | 27
| Ceilings board |  | 2026-03-06 | 2026-03-07 | 1
| Ceilings board |  | 2026-03-13 | 2026-03-14 | 1
| Ceilings board |  | 2026-03-20 | 2026-03-21 | 1
| Ceilings board |  | 2026-03-27 | 2026-03-28 | 1
| Ceilings board |  | 2026-04-04 | 2026-04-05 | 1
| Ceilings board |  | 2026-04-11 | 2026-04-12 | 1
| Ceilings board |  | 2026-04-18 | 2026-04-19 | 1
| Ceilings board |  | 2026-04-25 | 2026-04-26 | 1
| Ceilings board |  | 2026-05-01 | 2026-05-02 | 1
| Ceilings board |  | 2026-05-08 | 2026-05-09 | 1
| Ceilings board |  | 2026-05-15 | 2026-05-16 | 1
| Ceilings board |  | 2026-05-22 | 2026-05-23 | 1
| Ceilings board |  | 2026-05-29 | 2026-05-30 | 1
| Ceilings board |  | 2026-06-06 | 2026-06-07 | 1
| Ceilings board |  | 2026-06-13 | 2026-06-14 | 1
| Ceilings board |  | 2026-06-20 | 2026-06-21 | 1
| Ceilings board |  | 2026-06-25 | 2026-06-28 | 2
| Plaster spray |  | 2025-12-07 | 2025-12-15 | 6
| Plaster spray |  | 2025-12-21 | 2025-12-22 | 1
| Plaster spray |  | 2025-12-28 | 2025-12-29 | 1
| Plaster spray |  | 2026-01-05 | 2026-01-06 | 2
| Plaster spray |  | 2026-01-12 | 2026-01-13 | 2
| Plaster spray |  | 2026-01-19 | 2026-01-21 | 3
| Plaster spray |  | 2026-01-25 | 2026-03-03 | 27
| Plaster spray |  | 2026-03-06 | 2026-03-07 | 1
| Plaster spray |  | 2026-03-13 | 2026-03-14 | 1
| Plaster spray |  | 2026-03-20 | 2026-03-21 | 1
| Plaster spray |  | 2026-03-27 | 2026-03-28 | 1
| Plaster spray |  | 2026-04-04 | 2026-04-05 | 1
| Plaster spray |  | 2026-04-11 | 2026-04-12 | 1
| Plaster spray |  | 2026-04-18 | 2026-04-19 | 1
| Plaster spray |  | 2026-04-25 | 2026-04-26 | 1
| Plaster spray |  | 2026-05-01 | 2026-05-02 | 1
| Plaster spray |  | 2026-05-08 | 2026-05-09 | 1
| Plaster spray |  | 2026-05-15 | 2026-05-16 | 1
| Plaster spray |  | 2026-05-22 | 2026-05-23 | 1
| Plaster spray |  | 2026-05-29 | 2026-05-30 | 1
| Plaster spray |  | 2026-06-06 | 2026-06-07 | 1
| Plaster spray |  | 2026-06-13 | 2026-06-14 | 1
| Plaster spray |  | 2026-06-20 | 2026-06-21 | 1
| Plaster spray |  | 2026-06-25 | 2026-06-28 | 2
| Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-08 | 1
| Levveling screed /smoothing compound |  | 2025-12-14 | 2025-12-15 | 1
| Levveling screed /smoothing compound |  | 2025-12-21 | 2025-12-22 | 1
| Levveling screed /smoothing compound |  | 2025-12-28 | 2025-12-29 | 1
| Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-06 | 2
| Levveling screed /smoothing compound |  | 2026-01-12 | 2026-01-13 | 2
| Levveling screed /smoothing compound |  | 2026-01-19 | 2026-01-21 | 3
| Levveling screed /smoothing compound |  | 2026-01-25 | 2026-03-03 | 27
| Levveling screed /smoothing compound |  | 2026-03-06 | 2026-03-07 | 1
| Levveling screed /smoothing compound |  | 2026-03-13 | 2026-03-14 | 1
| Levveling screed /smoothing compound |  | 2026-03-20 | 2026-03-21 | 1
| Levveling screed /smoothing compound |  | 2026-03-27 | 2026-03-28 | 1
| Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
| Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
| Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
| Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
| Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
| Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
| Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
| Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
| Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
| Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
| Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
| Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
| Levveling screed /smoothing compound |  | 2026-06-25 | 2026-06-28 | 2
78 | Drying out |  | 2025-12-07 | 2025-12-08 | 1
78 | Drying out |  | 2025-12-14 | 2025-12-15 | 1
78 | Drying out |  | 2025-12-21 | 2025-12-22 | 1
78 | Drying out |  | 2025-12-28 | 2025-12-29 | 1
78 | Drying out |  | 2026-01-05 | 2026-01-06 | 2
78 | Drying out |  | 2026-01-12 | 2026-01-13 | 2
78 | Drying out |  | 2026-01-19 | 2026-01-21 | 3
78 | Drying out |  | 2026-01-25 | 2026-03-03 | 27
78 | Drying out |  | 2026-03-06 | 2026-03-07 | 1
78 | Drying out |  | 2026-03-13 | 2026-03-14 | 1
78 | Drying out |  | 2026-03-20 | 2026-03-21 | 1
78 | Drying out |  | 2026-03-27 | 2026-03-28 | 1
78 | Drying out |  | 2026-04-04 | 2026-04-05 | 1
78 | Drying out |  | 2026-04-11 | 2026-04-12 | 1
78 | Drying out |  | 2026-04-18 | 2026-04-19 | 1
78 | Drying out |  | 2026-04-25 | 2026-04-26 | 1
78 | Drying out |  | 2026-05-01 | 2026-05-02 | 1
78 | Drying out |  | 2026-05-08 | 2026-05-09 | 1
78 | Drying out |  | 2026-05-15 | 2026-05-16 | 1
78 | Drying out |  | 2026-05-22 | 2026-05-23 | 1
78 | Drying out |  | 2026-05-29 | 2026-05-30 | 1
78 | Drying out |  | 2026-06-06 | 2026-06-07 | 1
78 | Drying out |  | 2026-06-13 | 2026-06-14 | 1
78 | Drying out |  | 2026-06-20 | 2026-06-21 | 1
78 | Drying out |  | 2026-06-25 | 2026-06-28 | 2
79 | MCL |  | 2025-12-07 | 2025-12-08 | 1
79 | MCL |  | 2025-12-14 | 2025-12-15 | 1
79 | MCL |  | 2025-12-21 | 2025-12-22 | 1
79 | MCL |  | 2025-12-28 | 2025-12-29 | 1
79 | MCL |  | 2026-01-05 | 2026-01-06 | 2
79 | MCL |  | 2026-01-12 | 2026-01-13 | 2
79 | MCL |  | 2026-01-19 | 2026-01-21 | 3
79 | MCL |  | 2026-01-25 | 2026-03-03 | 27
79 | MCL |  | 2026-03-06 | 2026-03-07 | 1
79 | MCL |  | 2026-03-13 | 2026-03-14 | 1
79 | MCL |  | 2026-03-20 | 2026-03-21 | 1
79 | MCL |  | 2026-03-27 | 2026-03-28 | 1
79 | MCL |  | 2026-04-04 | 2026-04-05 | 1
79 | MCL |  | 2026-04-11 | 2026-04-12 | 1
79 | MCL |  | 2026-04-18 | 2026-04-19 | 1
79 | MCL |  | 2026-04-25 | 2026-04-26 | 1
79 | MCL |  | 2026-05-01 | 2026-05-02 | 1
79 | MCL |  | 2026-05-08 | 2026-05-09 | 1
79 | MCL |  | 2026-05-15 | 2026-05-16 | 1
79 | MCL |  | 2026-05-22 | 2026-05-23 | 1
79 | MCL |  | 2026-05-29 | 2026-05-30 | 1
79 | MCL |  | 2026-06-06 | 2026-06-07 | 1
79 | MCL |  | 2026-06-13 | 2026-06-14 | 1
79 | MCL |  | 2026-06-20 | 2026-06-21 | 1
79 | MCL |  | 2026-06-25 | 2026-06-28 | 2
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-08 | 1
| Vanity 1st fix framing |  | 2025-12-14 | 2025-12-15 | 1
| Vanity 1st fix framing |  | 2025-12-21 | 2025-12-22 | 1
| Vanity 1st fix framing |  | 2025-12-28 | 2025-12-29 | 1
| Vanity 1st fix framing |  | 2026-01-05 | 2026-01-06 | 2
| Vanity 1st fix framing |  | 2026-01-12 | 2026-01-13 | 2
| Vanity 1st fix framing |  | 2026-01-19 | 2026-01-21 | 3
| Vanity 1st fix framing |  | 2026-01-25 | 2026-03-03 | 27
| Vanity 1st fix framing |  | 2026-03-06 | 2026-03-07 | 1
| Vanity 1st fix framing |  | 2026-03-13 | 2026-03-14 | 1
| Vanity 1st fix framing |  | 2026-03-20 | 2026-03-21 | 1
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2026-06-25 | 2026-06-28 | 2
80 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
80 | PANACEA |  | 2025-12-10 | 2025-12-15 | 4
80 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
80 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
80 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
80 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
80 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
80 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
80 | PANACEA |  | 2026-03-06 | 2026-03-14 | 6
80 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
80 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
80 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
80 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
80 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
80 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
80 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
80 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
80 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
80 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
80 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
80 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
80 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
80 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
80 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-10 | 2025-12-15 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-25 | 2026-03-03 | 27
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
81 | TECL |  | 2025-12-07 | 2025-12-08 | 1
81 | TECL |  | 2025-12-14 | 2025-12-22 | 6
81 | TECL |  | 2025-12-28 | 2025-12-29 | 1
81 | TECL |  | 2026-01-05 | 2026-01-06 | 2
81 | TECL |  | 2026-01-12 | 2026-01-13 | 2
81 | TECL |  | 2026-01-19 | 2026-01-21 | 3
81 | TECL |  | 2026-01-25 | 2026-03-10 | 32
81 | TECL |  | 2026-03-13 | 2026-03-14 | 1
81 | TECL |  | 2026-03-20 | 2026-03-21 | 1
81 | TECL |  | 2026-03-27 | 2026-03-28 | 1
81 | TECL |  | 2026-04-04 | 2026-04-05 | 1
81 | TECL |  | 2026-04-11 | 2026-04-12 | 1
81 | TECL |  | 2026-04-18 | 2026-04-19 | 1
81 | TECL |  | 2026-04-25 | 2026-04-26 | 1
81 | TECL |  | 2026-05-01 | 2026-05-02 | 1
81 | TECL |  | 2026-05-08 | 2026-05-09 | 1
81 | TECL |  | 2026-05-15 | 2026-05-16 | 1
81 | TECL |  | 2026-05-22 | 2026-05-23 | 1
81 | TECL |  | 2026-05-29 | 2026-05-30 | 1
81 | TECL |  | 2026-06-06 | 2026-06-07 | 1
81 | TECL |  | 2026-06-13 | 2026-06-14 | 1
81 | TECL |  | 2026-06-20 | 2026-06-21 | 1
81 | TECL |  | 2026-06-25 | 2026-06-28 | 2
| Floor and wall tiling JD tiling |  | 2025-12-07 | 2025-12-08 | 1
| Floor and wall tiling JD tiling |  | 2025-12-14 | 2025-12-15 | 1
| Floor and wall tiling JD tiling |  | 2025-12-21 | 2025-12-26 | 5
| Floor and wall tiling JD tiling |  | 2025-12-28 | 2025-12-29 | 1
| Floor and wall tiling JD tiling |  | 2026-01-05 | 2026-01-06 | 2
| Floor and wall tiling JD tiling |  | 2026-01-12 | 2026-01-13 | 2
| Floor and wall tiling JD tiling |  | 2026-01-19 | 2026-01-21 | 3
| Floor and wall tiling JD tiling |  | 2026-01-25 | 2026-03-08 | 30
| Floor and wall tiling JD tiling |  | 2026-03-13 | 2026-03-14 | 1
| Floor and wall tiling JD tiling |  | 2026-03-20 | 2026-03-21 | 1
| Floor and wall tiling JD tiling |  | 2026-03-27 | 2026-03-28 | 1
| Floor and wall tiling JD tiling |  | 2026-04-04 | 2026-04-05 | 1
| Floor and wall tiling JD tiling |  | 2026-04-11 | 2026-04-12 | 1
| Floor and wall tiling JD tiling |  | 2026-04-18 | 2026-04-19 | 1
| Floor and wall tiling JD tiling |  | 2026-04-25 | 2026-04-26 | 1
| Floor and wall tiling JD tiling |  | 2026-05-01 | 2026-05-02 | 1
| Floor and wall tiling JD tiling |  | 2026-05-08 | 2026-05-09 | 1
| Floor and wall tiling JD tiling |  | 2026-05-15 | 2026-05-16 | 1
| Floor and wall tiling JD tiling |  | 2026-05-22 | 2026-05-23 | 1
| Floor and wall tiling JD tiling |  | 2026-05-29 | 2026-05-30 | 1
| Floor and wall tiling JD tiling |  | 2026-06-06 | 2026-06-07 | 1
| Floor and wall tiling JD tiling |  | 2026-06-13 | 2026-06-14 | 1
| Floor and wall tiling JD tiling |  | 2026-06-20 | 2026-06-21 | 1
| Floor and wall tiling JD tiling |  | 2026-06-25 | 2026-06-28 | 2
82 | service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-08 | 1
82 | service cupbaord -plywood flooring |  | 2025-12-14 | 2025-12-15 | 1
82 | service cupbaord -plywood flooring |  | 2025-12-21 | 2025-12-22 | 1
82 | service cupbaord -plywood flooring |  | 2025-12-27 | 2025-12-29 | 1
82 | service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-06 | 2
82 | service cupbaord -plywood flooring |  | 2026-01-12 | 2026-01-13 | 2
82 | service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-21 | 3
82 | service cupbaord -plywood flooring |  | 2026-01-25 | 2026-03-03 | 27
82 | service cupbaord -plywood flooring |  | 2026-03-06 | 2026-03-07 | 1
82 | service cupbaord -plywood flooring |  | 2026-03-09 | 2026-03-10 | 2
82 | service cupbaord -plywood flooring |  | 2026-03-13 | 2026-03-14 | 1
82 | service cupbaord -plywood flooring |  | 2026-03-20 | 2026-03-21 | 1
82 | service cupbaord -plywood flooring |  | 2026-03-27 | 2026-03-28 | 1
82 | service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
82 | service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
82 | service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
82 | service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
82 | service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
82 | service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
82 | service cupbaord -plywood flooring |  | 2026-05-15 | 2026-05-16 | 1
82 | service cupbaord -plywood flooring |  | 2026-05-22 | 2026-05-23 | 1
82 | service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
82 | service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
82 | service cupbaord -plywood flooring |  | 2026-06-13 | 2026-06-14 | 1
82 | service cupbaord -plywood flooring |  | 2026-06-20 | 2026-06-21 | 1
82 | service cupbaord -plywood flooring |  | 2026-06-25 | 2026-06-28 | 2
83 | MCL |  | 2025-12-07 | 2025-12-08 | 1
83 | MCL |  | 2025-12-14 | 2025-12-15 | 1
83 | MCL |  | 2025-12-21 | 2025-12-22 | 1
83 | MCL |  | 2025-12-28 | 2025-12-29 | 1
83 | MCL |  | 2026-01-05 | 2026-01-06 | 2
83 | MCL |  | 2026-01-12 | 2026-01-13 | 2
83 | MCL |  | 2026-01-19 | 2026-01-21 | 3
83 | MCL |  | 2026-01-25 | 2026-03-03 | 27
83 | MCL |  | 2026-03-06 | 2026-03-07 | 1
83 | MCL |  | 2026-03-11 | 2026-03-14 | 3
83 | MCL |  | 2026-03-20 | 2026-03-21 | 1
83 | MCL |  | 2026-03-27 | 2026-03-28 | 1
83 | MCL |  | 2026-04-04 | 2026-04-05 | 1
83 | MCL |  | 2026-04-11 | 2026-04-12 | 1
83 | MCL |  | 2026-04-18 | 2026-04-19 | 1
83 | MCL |  | 2026-04-25 | 2026-04-26 | 1
83 | MCL |  | 2026-05-01 | 2026-05-02 | 1
83 | MCL |  | 2026-05-08 | 2026-05-09 | 1
83 | MCL |  | 2026-05-15 | 2026-05-16 | 1
83 | MCL |  | 2026-05-22 | 2026-05-23 | 1
83 | MCL |  | 2026-05-29 | 2026-05-30 | 1
83 | MCL |  | 2026-06-06 | 2026-06-07 | 1
83 | MCL |  | 2026-06-13 | 2026-06-14 | 1
83 | MCL |  | 2026-06-20 | 2026-06-21 | 1
83 | MCL |  | 2026-06-25 | 2026-06-28 | 2
85 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
85 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
85 | PANACEA |  | 2025-12-21 | 2025-12-29 | 6
85 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
85 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
85 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
85 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
85 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
85 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
85 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
85 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
85 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
85 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
85 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
85 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
85 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
85 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
85 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
85 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
85 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
85 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
85 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
85 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
85 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-29 | 6
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-21 | 3
| Amtico flooring /Bathrooms |  | 2026-01-25 | 2026-03-03 | 27
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-21 | 6
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-26 | 2025-12-29 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-25 | 2026-03-03 | 27
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-23 | 2026-03-29 | 5
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-25 | 2026-06-28 | 2
| Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-08 | 1
| Electrical 2nd fix & live testing |  | 2025-12-14 | 2025-12-15 | 1
| Electrical 2nd fix & live testing |  | 2025-12-21 | 2025-12-22 | 1
| Electrical 2nd fix & live testing |  | 2025-12-28 | 2026-01-06 | 7
| Electrical 2nd fix & live testing |  | 2026-01-12 | 2026-01-13 | 2
| Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
| Electrical 2nd fix & live testing |  | 2026-01-25 | 2026-03-03 | 27
| Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
| Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
| Electrical 2nd fix & live testing |  | 2026-03-20 | 2026-03-21 | 1
| Electrical 2nd fix & live testing |  | 2026-03-27 | 2026-03-28 | 1
| Electrical 2nd fix & live testing |  | 2026-03-30 | 2026-04-06 | 6
| Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
| Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
| Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
| Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
| Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
| Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
| Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
| Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
| Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
| Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
| Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
| Electrical 2nd fix & live testing |  | 2026-06-25 | 2026-06-28 | 2
86 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
86 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
86 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
86 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
86 | PANACEA |  | 2026-01-05 | 2026-01-13 | 7
86 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
86 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
86 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
86 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
86 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
86 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
86 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
86 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
86 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
86 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
86 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
86 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
86 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
86 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
86 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
86 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
86 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
86 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
86 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
87 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
87 | Active flooring |  | 2025-12-14 | 2025-12-15 | 1
87 | Active flooring |  | 2025-12-21 | 2025-12-22 | 1
87 | Active flooring |  | 2025-12-28 | 2025-12-29 | 1
87 | Active flooring |  | 2026-01-05 | 2026-01-06 | 2
87 | Active flooring |  | 2026-01-12 | 2026-01-13 | 2
87 | Active flooring |  | 2026-01-19 | 2026-03-03 | 32
87 | Active flooring |  | 2026-03-06 | 2026-03-07 | 1
87 | Active flooring |  | 2026-03-13 | 2026-03-14 | 1
87 | Active flooring |  | 2026-03-20 | 2026-03-21 | 1
87 | Active flooring |  | 2026-03-27 | 2026-03-28 | 1
87 | Active flooring |  | 2026-04-04 | 2026-04-05 | 1
87 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
87 | Active flooring |  | 2026-04-18 | 2026-04-19 | 1
87 | Active flooring |  | 2026-04-25 | 2026-04-26 | 1
87 | Active flooring |  | 2026-05-01 | 2026-05-02 | 1
87 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
87 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
87 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
87 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
87 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
87 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
87 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
87 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
88 | MCL |  | 2025-12-07 | 2025-12-08 | 1
88 | MCL |  | 2025-12-14 | 2025-12-15 | 1
88 | MCL |  | 2025-12-21 | 2025-12-22 | 1
88 | MCL |  | 2025-12-28 | 2025-12-29 | 1
88 | MCL |  | 2026-01-05 | 2026-01-06 | 2
88 | MCL |  | 2026-01-12 | 2026-01-13 | 2
88 | MCL |  | 2026-01-19 | 2026-03-03 | 32
88 | MCL |  | 2026-03-06 | 2026-03-07 | 1
88 | MCL |  | 2026-03-13 | 2026-03-14 | 1
88 | MCL |  | 2026-03-20 | 2026-03-21 | 1
88 | MCL |  | 2026-03-27 | 2026-03-28 | 1
88 | MCL |  | 2026-04-04 | 2026-04-05 | 1
88 | MCL |  | 2026-04-08 | 2026-04-14 | 5
88 | MCL |  | 2026-04-18 | 2026-04-19 | 1
88 | MCL |  | 2026-04-25 | 2026-04-26 | 1
88 | MCL |  | 2026-05-01 | 2026-05-02 | 1
88 | MCL |  | 2026-05-08 | 2026-05-09 | 1
88 | MCL |  | 2026-05-15 | 2026-05-16 | 1
88 | MCL |  | 2026-05-22 | 2026-05-23 | 1
88 | MCL |  | 2026-05-29 | 2026-05-30 | 1
88 | MCL |  | 2026-06-06 | 2026-06-07 | 1
88 | MCL |  | 2026-06-13 | 2026-06-14 | 1
88 | MCL |  | 2026-06-20 | 2026-06-21 | 1
88 | MCL |  | 2026-06-25 | 2026-06-28 | 2
89 | Smiths |  | 2025-12-07 | 2025-12-08 | 1
89 | Smiths |  | 2025-12-14 | 2025-12-15 | 1
89 | Smiths |  | 2025-12-21 | 2025-12-22 | 1
89 | Smiths |  | 2025-12-28 | 2025-12-29 | 1
89 | Smiths |  | 2026-01-05 | 2026-01-06 | 2
89 | Smiths |  | 2026-01-12 | 2026-01-13 | 2
89 | Smiths |  | 2026-01-19 | 2026-03-03 | 32
89 | Smiths |  | 2026-03-06 | 2026-03-07 | 1
89 | Smiths |  | 2026-03-13 | 2026-03-14 | 1
89 | Smiths |  | 2026-03-20 | 2026-03-21 | 1
89 | Smiths |  | 2026-03-27 | 2026-03-28 | 1
89 | Smiths |  | 2026-04-04 | 2026-04-05 | 1
89 | Smiths |  | 2026-04-11 | 2026-04-12 | 1
89 | Smiths |  | 2026-04-15 | 2026-04-19 | 3
89 | Smiths |  | 2026-04-25 | 2026-04-26 | 1
89 | Smiths |  | 2026-05-01 | 2026-05-02 | 1
89 | Smiths |  | 2026-05-08 | 2026-05-09 | 1
89 | Smiths |  | 2026-05-15 | 2026-05-16 | 1
89 | Smiths |  | 2026-05-22 | 2026-05-23 | 1
89 | Smiths |  | 2026-05-29 | 2026-05-30 | 1
89 | Smiths |  | 2026-06-06 | 2026-06-07 | 1
89 | Smiths |  | 2026-06-13 | 2026-06-14 | 1
89 | Smiths |  | 2026-06-20 | 2026-06-21 | 1
89 | Smiths |  | 2026-06-25 | 2026-06-28 | 2
90 | MCL |  | 2025-12-07 | 2025-12-08 | 1
90 | MCL |  | 2025-12-14 | 2025-12-15 | 1
90 | MCL |  | 2025-12-21 | 2025-12-22 | 1
90 | MCL |  | 2025-12-28 | 2025-12-29 | 1
90 | MCL |  | 2026-01-05 | 2026-01-06 | 2
90 | MCL |  | 2026-01-12 | 2026-01-13 | 2
90 | MCL |  | 2026-01-19 | 2026-03-03 | 32
90 | MCL |  | 2026-03-06 | 2026-03-07 | 1
90 | MCL |  | 2026-03-13 | 2026-03-14 | 1
90 | MCL |  | 2026-03-20 | 2026-03-21 | 1
90 | MCL |  | 2026-03-27 | 2026-03-28 | 1
90 | MCL |  | 2026-04-04 | 2026-04-05 | 1
90 | MCL |  | 2026-04-11 | 2026-04-12 | 1
90 | MCL |  | 2026-04-18 | 2026-04-26 | 5
90 | MCL |  | 2026-05-01 | 2026-05-02 | 1
90 | MCL |  | 2026-05-08 | 2026-05-09 | 1
90 | MCL |  | 2026-05-15 | 2026-05-16 | 1
90 | MCL |  | 2026-05-22 | 2026-05-23 | 1
90 | MCL |  | 2026-05-29 | 2026-05-30 | 1
90 | MCL |  | 2026-06-06 | 2026-06-07 | 1
90 | MCL |  | 2026-06-13 | 2026-06-14 | 1
90 | MCL |  | 2026-06-20 | 2026-06-21 | 1
90 | MCL |  | 2026-06-25 | 2026-06-28 | 2
| Sparkle clean |  | 2025-12-07 | 2025-12-08 | 1
| Sparkle clean |  | 2025-12-14 | 2025-12-15 | 1
| Sparkle clean |  | 2025-12-21 | 2025-12-22 | 1
| Sparkle clean |  | 2025-12-28 | 2025-12-29 | 1
| Sparkle clean |  | 2026-01-05 | 2026-01-06 | 2
| Sparkle clean |  | 2026-01-12 | 2026-01-13 | 2
| Sparkle clean |  | 2026-01-19 | 2026-03-03 | 32
| Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
| Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
| Sparkle clean |  | 2026-03-20 | 2026-03-21 | 1
| Sparkle clean |  | 2026-03-27 | 2026-03-28 | 1
| Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
| Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
| Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
| Sparkle clean |  | 2026-04-25 | 2026-05-02 | 5
| Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
| Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
| Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
| Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
| Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
| Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
| Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
| Sparkle clean |  | 2026-06-25 | 2026-06-28 | 2
| Mastic |  | 2025-12-07 | 2025-12-08 | 1
| Mastic |  | 2025-12-14 | 2025-12-15 | 1
| Mastic |  | 2025-12-21 | 2025-12-22 | 1
| Mastic |  | 2025-12-28 | 2025-12-29 | 1
| Mastic |  | 2026-01-05 | 2026-01-06 | 2
| Mastic |  | 2026-01-12 | 2026-01-13 | 2
| Mastic |  | 2026-01-19 | 2026-01-21 | 3
| Mastic |  | 2026-01-25 | 2026-03-03 | 27
| Mastic |  | 2026-03-06 | 2026-03-07 | 1
| Mastic |  | 2026-03-13 | 2026-03-14 | 1
| Mastic |  | 2026-03-20 | 2026-03-21 | 1
| Mastic |  | 2026-03-27 | 2026-03-28 | 1
| Mastic |  | 2026-04-04 | 2026-04-05 | 1
| Mastic |  | 2026-04-11 | 2026-04-12 | 1
| Mastic |  | 2026-04-18 | 2026-04-19 | 1
| Mastic |  | 2026-04-25 | 2026-04-26 | 1
| Mastic |  | 2026-05-01 | 2026-05-04 | 2
| Mastic |  | 2026-05-08 | 2026-05-09 | 1
| Mastic |  | 2026-05-15 | 2026-05-16 | 1
| Mastic |  | 2026-05-22 | 2026-05-23 | 1
| Mastic |  | 2026-05-29 | 2026-05-30 | 1
| Mastic |  | 2026-06-06 | 2026-06-07 | 1
| Mastic |  | 2026-06-13 | 2026-06-14 | 1
| Mastic |  | 2026-06-20 | 2026-06-21 | 1
| Mastic |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-15 | 1
| Handover to client |  | 2025-12-21 | 2025-12-22 | 1
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-12 | 2026-01-13 | 2
| Handover to client |  | 2026-01-19 | 2026-01-21 | 3
| Handover to client |  | 2026-01-25 | 2026-03-03 | 27
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-17 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
| Level 4 Apartment fit out -cluster 2 |  | 2025-12-07 | 2025-12-08 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2025-12-14 | 2025-12-15 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2025-12-21 | 2025-12-22 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2025-12-28 | 2025-12-29 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-01-05 | 2026-01-06 | 2
| Level 4 Apartment fit out -cluster 2 |  | 2026-01-12 | 2026-01-13 | 2
| Level 4 Apartment fit out -cluster 2 |  | 2026-01-19 | 2026-01-21 | 3
| Level 4 Apartment fit out -cluster 2 |  | 2026-01-23 | 2026-03-03 | 28
| Level 4 Apartment fit out -cluster 2 |  | 2026-03-06 | 2026-03-07 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-03-13 | 2026-03-14 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-03-20 | 2026-03-21 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-03-27 | 2026-03-28 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-04-04 | 2026-04-05 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-04-11 | 2026-04-12 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-04-18 | 2026-04-19 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-04-25 | 2026-04-26 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-05-01 | 2026-05-02 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-05-08 | 2026-05-09 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-05-15 | 2026-05-16 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-05-22 | 2026-05-23 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-05-29 | 2026-05-30 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-06-06 | 2026-06-07 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-06-13 | 2026-06-14 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-06-20 | 2026-06-21 | 1
| Level 4 Apartment fit out -cluster 2 |  | 2026-06-25 | 2026-06-28 | 2
| Ceiling void closure checklist sign off |  | 2025-12-07 | 2025-12-08 | 1
| Ceiling void closure checklist sign off |  | 2025-12-14 | 2025-12-15 | 1
| Ceiling void closure checklist sign off |  | 2025-12-21 | 2025-12-22 | 1
| Ceiling void closure checklist sign off |  | 2025-12-28 | 2025-12-29 | 1
| Ceiling void closure checklist sign off |  | 2026-01-05 | 2026-01-06 | 2
| Ceiling void closure checklist sign off |  | 2026-01-12 | 2026-01-13 | 2
| Ceiling void closure checklist sign off |  | 2026-01-19 | 2026-03-03 | 32
| Ceiling void closure checklist sign off |  | 2026-03-06 | 2026-03-07 | 1
| Ceiling void closure checklist sign off |  | 2026-03-13 | 2026-03-14 | 1
| Ceiling void closure checklist sign off |  | 2026-03-20 | 2026-03-21 | 1
| Ceiling void closure checklist sign off |  | 2026-03-27 | 2026-03-28 | 1
| Ceiling void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
| Ceiling void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
| Ceiling void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
| Ceiling void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
| Ceiling void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
| Ceiling void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
| Ceiling void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
| Ceiling void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
| Ceiling void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
| Ceiling void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
| Ceiling void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
| Ceiling void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
| Ceiling void closure checklist sign off |  | 2026-06-25 | 2026-06-28 | 2
| Ceilings - metal |  | 2025-12-07 | 2025-12-08 | 1
| Ceilings - metal |  | 2025-12-14 | 2025-12-15 | 1
| Ceilings - metal |  | 2025-12-21 | 2025-12-22 | 1
| Ceilings - metal |  | 2025-12-28 | 2025-12-29 | 1
| Ceilings - metal |  | 2026-01-05 | 2026-01-06 | 2
| Ceilings - metal |  | 2026-01-12 | 2026-01-13 | 2
| Ceilings - metal |  | 2026-01-19 | 2026-01-20 | 2
| Ceilings - metal |  | 2026-01-23 | 2026-03-03 | 28
| Ceilings - metal |  | 2026-03-06 | 2026-03-07 | 1
| Ceilings - metal |  | 2026-03-13 | 2026-03-14 | 1
| Ceilings - metal |  | 2026-03-20 | 2026-03-21 | 1
| Ceilings - metal |  | 2026-03-27 | 2026-03-28 | 1
| Ceilings - metal |  | 2026-04-04 | 2026-04-05 | 1
| Ceilings - metal |  | 2026-04-11 | 2026-04-12 | 1
| Ceilings - metal |  | 2026-04-18 | 2026-04-19 | 1
| Ceilings - metal |  | 2026-04-25 | 2026-04-26 | 1
| Ceilings - metal |  | 2026-05-01 | 2026-05-02 | 1
| Ceilings - metal |  | 2026-05-08 | 2026-05-09 | 1
| Ceilings - metal |  | 2026-05-15 | 2026-05-16 | 1
| Ceilings - metal |  | 2026-05-22 | 2026-05-23 | 1
| Ceilings - metal |  | 2026-05-29 | 2026-05-30 | 1
| Ceilings - metal |  | 2026-06-06 | 2026-06-07 | 1
| Ceilings - metal |  | 2026-06-13 | 2026-06-14 | 1
| Ceilings - metal |  | 2026-06-20 | 2026-06-21 | 1
| Ceilings - metal |  | 2026-06-25 | 2026-06-28 | 2
| Sprinkler 2nd fix & test Armstrong preistly |  | 2025-12-07 | 2025-12-08 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2025-12-14 | 2025-12-15 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2025-12-21 | 2025-12-22 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2025-12-28 | 2025-12-29 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-01-05 | 2026-01-06 | 2
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-01-12 | 2026-01-13 | 2
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-01-19 | 2026-01-20 | 2
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-01-23 | 2026-03-03 | 28
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-03-06 | 2026-03-07 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-03-13 | 2026-03-14 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-03-20 | 2026-03-21 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-03-27 | 2026-03-28 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-04-04 | 2026-04-05 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-04-11 | 2026-04-12 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-04-18 | 2026-04-19 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-04-25 | 2026-04-26 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-05-01 | 2026-05-02 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-05-08 | 2026-05-09 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-05-15 | 2026-05-16 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-05-22 | 2026-05-23 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-05-29 | 2026-05-30 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-06-06 | 2026-06-07 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-06-13 | 2026-06-14 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-06-20 | 2026-06-21 | 1
| Sprinkler 2nd fix & test Armstrong preistly |  | 2026-06-25 | 2026-06-28 | 2
| Ceilings board |  | 2025-12-07 | 2025-12-08 | 1
| Ceilings board |  | 2025-12-14 | 2025-12-15 | 1
| Ceilings board |  | 2025-12-21 | 2025-12-22 | 1
| Ceilings board |  | 2025-12-28 | 2025-12-29 | 1
| Ceilings board |  | 2026-01-05 | 2026-01-06 | 2
| Ceilings board |  | 2026-01-12 | 2026-01-13 | 2
| Ceilings board |  | 2026-01-19 | 2026-01-21 | 3
| Ceilings board |  | 2026-01-23 | 2026-03-03 | 28
| Ceilings board |  | 2026-03-06 | 2026-03-07 | 1
| Ceilings board |  | 2026-03-13 | 2026-03-14 | 1
| Ceilings board |  | 2026-03-20 | 2026-03-21 | 1
| Ceilings board |  | 2026-03-27 | 2026-03-28 | 1
| Ceilings board |  | 2026-04-04 | 2026-04-05 | 1
| Ceilings board |  | 2026-04-11 | 2026-04-12 | 1
| Ceilings board |  | 2026-04-18 | 2026-04-19 | 1
| Ceilings board |  | 2026-04-25 | 2026-04-26 | 1
| Ceilings board |  | 2026-05-01 | 2026-05-02 | 1
| Ceilings board |  | 2026-05-08 | 2026-05-09 | 1
| Ceilings board |  | 2026-05-15 | 2026-05-16 | 1
| Ceilings board |  | 2026-05-22 | 2026-05-23 | 1
| Ceilings board |  | 2026-05-29 | 2026-05-30 | 1
| Ceilings board |  | 2026-06-06 | 2026-06-07 | 1
| Ceilings board |  | 2026-06-13 | 2026-06-14 | 1
| Ceilings board |  | 2026-06-20 | 2026-06-21 | 1
| Ceilings board |  | 2026-06-25 | 2026-06-28 | 2
| Plaster spray |  | 2025-12-07 | 2025-12-08 | 1
| Plaster spray |  | 2025-12-14 | 2025-12-15 | 1
| Plaster spray |  | 2025-12-21 | 2025-12-22 | 1
| Plaster spray |  | 2025-12-28 | 2025-12-29 | 1
| Plaster spray |  | 2026-01-05 | 2026-01-06 | 2
| Plaster spray |  | 2026-01-12 | 2026-01-13 | 2
| Plaster spray |  | 2026-01-19 | 2026-01-21 | 3
| Plaster spray |  | 2026-01-23 | 2026-03-03 | 28
| Plaster spray |  | 2026-03-06 | 2026-03-07 | 1
| Plaster spray |  | 2026-03-13 | 2026-03-14 | 1
| Plaster spray |  | 2026-03-20 | 2026-03-21 | 1
| Plaster spray |  | 2026-03-27 | 2026-03-28 | 1
| Plaster spray |  | 2026-04-04 | 2026-04-05 | 1
| Plaster spray |  | 2026-04-11 | 2026-04-12 | 1
| Plaster spray |  | 2026-04-18 | 2026-04-19 | 1
| Plaster spray |  | 2026-04-25 | 2026-04-26 | 1
| Plaster spray |  | 2026-05-01 | 2026-05-02 | 1
| Plaster spray |  | 2026-05-08 | 2026-05-09 | 1
| Plaster spray |  | 2026-05-15 | 2026-05-16 | 1
| Plaster spray |  | 2026-05-22 | 2026-05-23 | 1
| Plaster spray |  | 2026-05-29 | 2026-05-30 | 1
| Plaster spray |  | 2026-06-06 | 2026-06-07 | 1
| Plaster spray |  | 2026-06-13 | 2026-06-14 | 1
| Plaster spray |  | 2026-06-20 | 2026-06-21 | 1
| Plaster spray |  | 2026-06-25 | 2026-06-28 | 2
| Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-08 | 1
| Levveling screed /smoothing compound |  | 2025-12-14 | 2025-12-15 | 1
| Levveling screed /smoothing compound |  | 2025-12-21 | 2025-12-22 | 1
| Levveling screed /smoothing compound |  | 2025-12-28 | 2025-12-29 | 1
| Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-06 | 2
| Levveling screed /smoothing compound |  | 2026-01-12 | 2026-01-13 | 2
| Levveling screed /smoothing compound |  | 2026-01-19 | 2026-01-21 | 3
| Levveling screed /smoothing compound |  | 2026-01-23 | 2026-03-03 | 28
| Levveling screed /smoothing compound |  | 2026-03-06 | 2026-03-07 | 1
| Levveling screed /smoothing compound |  | 2026-03-13 | 2026-03-14 | 1
| Levveling screed /smoothing compound |  | 2026-03-20 | 2026-03-21 | 1
| Levveling screed /smoothing compound |  | 2026-03-27 | 2026-03-28 | 1
| Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
| Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
| Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
| Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
| Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
| Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
| Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
| Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
| Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
| Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
| Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
| Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
| Levveling screed /smoothing compound |  | 2026-06-25 | 2026-06-28 | 2
| Drying out |  | 2025-12-07 | 2025-12-08 | 1
| Drying out |  | 2025-12-14 | 2025-12-15 | 1
| Drying out |  | 2025-12-21 | 2025-12-22 | 1
| Drying out |  | 2025-12-28 | 2025-12-29 | 1
| Drying out |  | 2026-01-05 | 2026-01-06 | 2
| Drying out |  | 2026-01-12 | 2026-01-13 | 2
| Drying out |  | 2026-01-19 | 2026-01-21 | 3
| Drying out |  | 2026-01-23 | 2026-03-03 | 28
| Drying out |  | 2026-03-06 | 2026-03-07 | 1
| Drying out |  | 2026-03-13 | 2026-03-14 | 1
| Drying out |  | 2026-03-20 | 2026-03-21 | 1
| Drying out |  | 2026-03-27 | 2026-03-28 | 1
| Drying out |  | 2026-04-04 | 2026-04-05 | 1
| Drying out |  | 2026-04-11 | 2026-04-12 | 1
| Drying out |  | 2026-04-18 | 2026-04-19 | 1
| Drying out |  | 2026-04-25 | 2026-04-26 | 1
| Drying out |  | 2026-05-01 | 2026-05-02 | 1
| Drying out |  | 2026-05-08 | 2026-05-09 | 1
| Drying out |  | 2026-05-15 | 2026-05-16 | 1
| Drying out |  | 2026-05-22 | 2026-05-23 | 1
| Drying out |  | 2026-05-29 | 2026-05-30 | 1
| Drying out |  | 2026-06-06 | 2026-06-07 | 1
| Drying out |  | 2026-06-13 | 2026-06-14 | 1
| Drying out |  | 2026-06-20 | 2026-06-21 | 1
| Drying out |  | 2026-06-25 | 2026-06-28 | 2
| Mist coat |  | 2025-12-07 | 2025-12-08 | 1
| Mist coat |  | 2025-12-14 | 2025-12-15 | 1
| Mist coat |  | 2025-12-21 | 2025-12-22 | 1
| Mist coat |  | 2025-12-28 | 2025-12-29 | 1
| Mist coat |  | 2026-01-05 | 2026-01-06 | 2
| Mist coat |  | 2026-01-12 | 2026-01-13 | 2
| Mist coat |  | 2026-01-19 | 2026-01-21 | 3
| Mist coat |  | 2026-01-23 | 2026-03-03 | 28
| Mist coat |  | 2026-03-06 | 2026-03-07 | 1
| Mist coat |  | 2026-03-13 | 2026-03-14 | 1
| Mist coat |  | 2026-03-20 | 2026-03-21 | 1
| Mist coat |  | 2026-03-27 | 2026-03-28 | 1
| Mist coat |  | 2026-04-04 | 2026-04-05 | 1
| Mist coat |  | 2026-04-11 | 2026-04-12 | 1
| Mist coat |  | 2026-04-18 | 2026-04-19 | 1
| Mist coat |  | 2026-04-25 | 2026-04-26 | 1
| Mist coat |  | 2026-05-01 | 2026-05-02 | 1
| Mist coat |  | 2026-05-08 | 2026-05-09 | 1
| Mist coat |  | 2026-05-15 | 2026-05-16 | 1
| Mist coat |  | 2026-05-22 | 2026-05-23 | 1
| Mist coat |  | 2026-05-29 | 2026-05-30 | 1
| Mist coat |  | 2026-06-06 | 2026-06-07 | 1
| Mist coat |  | 2026-06-13 | 2026-06-14 | 1
| Mist coat |  | 2026-06-20 | 2026-06-21 | 1
| Mist coat |  | 2026-06-25 | 2026-06-28 | 2
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-08 | 1
| Vanity 1st fix framing |  | 2025-12-14 | 2025-12-15 | 1
| Vanity 1st fix framing |  | 2025-12-21 | 2025-12-22 | 1
| Vanity 1st fix framing |  | 2025-12-28 | 2025-12-29 | 1
| Vanity 1st fix framing |  | 2026-01-05 | 2026-01-06 | 2
| Vanity 1st fix framing |  | 2026-01-12 | 2026-01-13 | 2
| Vanity 1st fix framing |  | 2026-01-19 | 2026-01-21 | 3
| Vanity 1st fix framing |  | 2026-01-23 | 2026-03-03 | 28
| Vanity 1st fix framing |  | 2026-03-06 | 2026-03-07 | 1
| Vanity 1st fix framing |  | 2026-03-13 | 2026-03-14 | 1
| Vanity 1st fix framing |  | 2026-03-20 | 2026-03-21 | 1
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2026-06-25 | 2026-06-28 | 2
| Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-08 | 1
| Kitchen 1st fix,units tops & appliances |  | 2025-12-14 | 2025-12-15 | 1
| Kitchen 1st fix,units tops & appliances |  | 2025-12-21 | 2025-12-22 | 1
| Kitchen 1st fix,units tops & appliances |  | 2025-12-28 | 2025-12-29 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-06 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-01-12 | 2026-01-13 | 2
| Kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-21 | 3
| Kitchen 1st fix,units tops & appliances |  | 2026-01-23 | 2026-03-03 | 28
| Kitchen 1st fix,units tops & appliances |  | 2026-03-06 | 2026-03-07 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-03-13 | 2026-03-21 | 6
| Kitchen 1st fix,units tops & appliances |  | 2026-03-27 | 2026-03-28 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-05 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-15 | 2026-05-16 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-22 | 2026-05-23 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-20 | 2026-06-21 | 1
| Kitchen 1st fix,units tops & appliances |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-23 | 2026-03-07 | 31
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-08 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-14 | 2025-12-15 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-21 | 2025-12-22 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-28 | 2025-12-29 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-05 | 2026-01-06 | 2
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-12 | 2026-01-13 | 2
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-19 | 2026-01-21 | 3
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-23 | 2026-03-03 | 28
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-06 | 2026-03-07 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-11 | 2026-03-17 | 5
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-20 | 2026-03-21 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-03-27 | 2026-03-28 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-04 | 2026-04-05 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-18 | 2026-04-19 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-25 | 2026-04-26 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-01 | 2026-05-02 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-15 | 2026-05-16 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-22 | 2026-05-23 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-29 | 2026-05-30 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-06 | 2026-06-07 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-13 | 2026-06-14 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-20 | 2026-06-21 | 1
91 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-25 | 2026-06-28 | 2
92 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
92 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
92 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
92 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
92 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
92 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
92 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
92 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
92 | PANACEA |  | 2026-03-06 | 2026-03-14 | 6
92 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
92 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
92 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
92 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
92 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
92 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
92 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
92 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
92 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
92 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
92 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
92 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
92 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
92 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
92 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
93 | Edencroft |  | 2025-12-07 | 2025-12-08 | 1
93 | Edencroft |  | 2025-12-14 | 2025-12-15 | 1
93 | Edencroft |  | 2025-12-21 | 2025-12-22 | 1
93 | Edencroft |  | 2025-12-28 | 2025-12-29 | 1
93 | Edencroft |  | 2026-01-05 | 2026-01-06 | 2
93 | Edencroft |  | 2026-01-12 | 2026-01-13 | 2
93 | Edencroft |  | 2026-01-19 | 2026-01-21 | 3
93 | Edencroft |  | 2026-01-25 | 2026-03-03 | 27
93 | Edencroft |  | 2026-03-06 | 2026-03-07 | 1
93 | Edencroft |  | 2026-03-13 | 2026-03-14 | 1
93 | Edencroft |  | 2026-03-16 | 2026-03-17 | 2
93 | Edencroft |  | 2026-03-20 | 2026-03-21 | 1
93 | Edencroft |  | 2026-03-27 | 2026-03-28 | 1
93 | Edencroft |  | 2026-04-04 | 2026-04-05 | 1
93 | Edencroft |  | 2026-04-11 | 2026-04-12 | 1
93 | Edencroft |  | 2026-04-18 | 2026-04-19 | 1
93 | Edencroft |  | 2026-04-25 | 2026-04-26 | 1
93 | Edencroft |  | 2026-05-01 | 2026-05-02 | 1
93 | Edencroft |  | 2026-05-08 | 2026-05-09 | 1
93 | Edencroft |  | 2026-05-15 | 2026-05-16 | 1
93 | Edencroft |  | 2026-05-22 | 2026-05-23 | 1
93 | Edencroft |  | 2026-05-29 | 2026-05-30 | 1
93 | Edencroft |  | 2026-06-06 | 2026-06-07 | 1
93 | Edencroft |  | 2026-06-13 | 2026-06-14 | 1
93 | Edencroft |  | 2026-06-20 | 2026-06-21 | 1
93 | Edencroft |  | 2026-06-25 | 2026-06-28 | 2
94 | GPL |  | 2025-12-07 | 2025-12-08 | 1
94 | GPL |  | 2025-12-14 | 2025-12-15 | 1
94 | GPL |  | 2025-12-21 | 2025-12-22 | 1
94 | GPL |  | 2025-12-28 | 2025-12-29 | 1
94 | GPL |  | 2026-01-05 | 2026-01-06 | 2
94 | GPL |  | 2026-01-12 | 2026-01-13 | 2
94 | GPL |  | 2026-01-19 | 2026-01-21 | 3
94 | GPL |  | 2026-01-25 | 2026-03-03 | 27
94 | GPL |  | 2026-03-06 | 2026-03-07 | 1
94 | GPL |  | 2026-03-13 | 2026-03-14 | 1
94 | GPL |  | 2026-03-18 | 2026-03-21 | 3
94 | GPL |  | 2026-03-27 | 2026-03-28 | 1
94 | GPL |  | 2026-04-04 | 2026-04-05 | 1
94 | GPL |  | 2026-04-11 | 2026-04-12 | 1
94 | GPL |  | 2026-04-18 | 2026-04-19 | 1
94 | GPL |  | 2026-04-25 | 2026-04-26 | 1
94 | GPL |  | 2026-05-01 | 2026-05-02 | 1
94 | GPL |  | 2026-05-08 | 2026-05-09 | 1
94 | GPL |  | 2026-05-15 | 2026-05-16 | 1
94 | GPL |  | 2026-05-22 | 2026-05-23 | 1
94 | GPL |  | 2026-05-29 | 2026-05-30 | 1
94 | GPL |  | 2026-06-06 | 2026-06-07 | 1
94 | GPL |  | 2026-06-13 | 2026-06-14 | 1
94 | GPL |  | 2026-06-20 | 2026-06-21 | 1
94 | GPL |  | 2026-06-25 | 2026-06-28 | 2
95 | ARMSTRONG |  | 2025-12-07 | 2025-12-08 | 1
95 | ARMSTRONG |  | 2025-12-12 | 2025-12-15 | 2
95 | ARMSTRONG |  | 2025-12-18 | 2025-12-29 | 8
95 | ARMSTRONG |  | 2026-01-05 | 2026-01-06 | 2
95 | ARMSTRONG |  | 2026-01-12 | 2026-01-13 | 2
95 | ARMSTRONG |  | 2026-01-19 | 2026-01-21 | 3
95 | ARMSTRONG |  | 2026-01-25 | 2026-03-03 | 27
95 | ARMSTRONG |  | 2026-03-06 | 2026-03-07 | 1
95 | ARMSTRONG |  | 2026-03-13 | 2026-03-14 | 1
95 | ARMSTRONG |  | 2026-03-20 | 2026-03-21 | 1
95 | ARMSTRONG |  | 2026-03-27 | 2026-03-28 | 1
95 | ARMSTRONG |  | 2026-04-04 | 2026-04-05 | 1
95 | ARMSTRONG |  | 2026-04-11 | 2026-04-12 | 1
95 | ARMSTRONG |  | 2026-04-18 | 2026-04-19 | 1
95 | ARMSTRONG |  | 2026-04-25 | 2026-04-26 | 1
95 | ARMSTRONG |  | 2026-05-01 | 2026-05-02 | 1
95 | ARMSTRONG |  | 2026-05-08 | 2026-05-09 | 1
95 | ARMSTRONG |  | 2026-05-15 | 2026-05-16 | 1
95 | ARMSTRONG |  | 2026-05-22 | 2026-05-23 | 1
95 | ARMSTRONG |  | 2026-05-29 | 2026-05-30 | 1
95 | ARMSTRONG |  | 2026-06-06 | 2026-06-07 | 1
95 | ARMSTRONG |  | 2026-06-13 | 2026-06-14 | 1
95 | ARMSTRONG |  | 2026-06-20 | 2026-06-21 | 1
95 | ARMSTRONG |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-12 | 2025-12-15 | 2
| Amtico flooring /Bathrooms |  | 2025-12-18 | 2025-12-29 | 8
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-21 | 3
| Amtico flooring /Bathrooms |  | 2026-01-25 | 2026-03-03 | 27
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-28 | 6
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-14 | 2025-12-22 | 6
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-25 | 2026-03-03 | 27
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-27 | 2026-04-05 | 6
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-25 | 2026-06-28 | 2
| Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-08 | 1
| Electrical 2nd fix & live testing |  | 2025-12-14 | 2025-12-22 | 6
| Electrical 2nd fix & live testing |  | 2025-12-28 | 2025-12-29 | 1
| Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-06 | 2
| Electrical 2nd fix & live testing |  | 2026-01-12 | 2026-01-13 | 2
| Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
| Electrical 2nd fix & live testing |  | 2026-01-25 | 2026-03-03 | 27
| Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
| Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
| Electrical 2nd fix & live testing |  | 2026-03-20 | 2026-03-21 | 1
| Electrical 2nd fix & live testing |  | 2026-03-27 | 2026-03-28 | 1
| Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-12 | 5
| Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
| Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
| Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
| Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
| Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
| Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
| Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
| Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
| Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
| Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
| Electrical 2nd fix & live testing |  | 2026-06-25 | 2026-06-28 | 2
| Builders clean |  | 2025-12-07 | 2025-12-08 | 1
| Builders clean |  | 2025-12-14 | 2025-12-15 | 1
| Builders clean |  | 2025-12-21 | 2025-12-22 | 1
| Builders clean |  | 2025-12-28 | 2026-01-06 | 7
| Builders clean |  | 2026-01-12 | 2026-01-13 | 2
| Builders clean |  | 2026-01-19 | 2026-01-21 | 3
| Builders clean |  | 2026-01-25 | 2026-03-03 | 27
| Builders clean |  | 2026-03-06 | 2026-03-07 | 1
| Builders clean |  | 2026-03-13 | 2026-03-14 | 1
| Builders clean |  | 2026-03-20 | 2026-03-21 | 1
| Builders clean |  | 2026-03-27 | 2026-03-28 | 1
| Builders clean |  | 2026-04-04 | 2026-04-05 | 1
| Builders clean |  | 2026-04-11 | 2026-04-12 | 1
| Builders clean |  | 2026-04-18 | 2026-04-19 | 1
| Builders clean |  | 2026-04-25 | 2026-04-26 | 1
| Builders clean |  | 2026-05-01 | 2026-05-02 | 1
| Builders clean |  | 2026-05-08 | 2026-05-09 | 1
| Builders clean |  | 2026-05-15 | 2026-05-16 | 1
| Builders clean |  | 2026-05-22 | 2026-05-23 | 1
| Builders clean |  | 2026-05-29 | 2026-05-30 | 1
| Builders clean |  | 2026-06-06 | 2026-06-07 | 1
| Builders clean |  | 2026-06-13 | 2026-06-14 | 1
| Builders clean |  | 2026-06-20 | 2026-06-21 | 1
| Builders clean |  | 2026-06-25 | 2026-06-28 | 2
96 | Pre -dec -snagging |  | 2025-12-07 | 2025-12-08 | 1
96 | Pre -dec -snagging |  | 2025-12-14 | 2025-12-15 | 1
96 | Pre -dec -snagging |  | 2025-12-21 | 2025-12-22 | 1
96 | Pre -dec -snagging |  | 2025-12-28 | 2025-12-29 | 1
96 | Pre -dec -snagging |  | 2026-01-05 | 2026-01-06 | 2
96 | Pre -dec -snagging |  | 2026-01-12 | 2026-01-13 | 2
96 | Pre -dec -snagging |  | 2026-01-19 | 2026-01-21 | 3
96 | Pre -dec -snagging |  | 2026-01-25 | 2026-03-03 | 27
96 | Pre -dec -snagging |  | 2026-03-06 | 2026-03-07 | 1
96 | Pre -dec -snagging |  | 2026-03-13 | 2026-03-14 | 1
96 | Pre -dec -snagging |  | 2026-03-20 | 2026-03-21 | 1
96 | Pre -dec -snagging |  | 2026-03-27 | 2026-03-28 | 1
96 | Pre -dec -snagging |  | 2026-04-04 | 2026-04-05 | 1
96 | Pre -dec -snagging |  | 2026-04-11 | 2026-04-12 | 1
96 | Pre -dec -snagging |  | 2026-04-18 | 2026-04-19 | 1
96 | Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
96 | Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
96 | Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
96 | Pre -dec -snagging |  | 2026-05-15 | 2026-05-16 | 1
96 | Pre -dec -snagging |  | 2026-05-22 | 2026-05-23 | 1
96 | Pre -dec -snagging |  | 2026-05-29 | 2026-05-30 | 1
96 | Pre -dec -snagging |  | 2026-06-06 | 2026-06-07 | 1
96 | Pre -dec -snagging |  | 2026-06-13 | 2026-06-14 | 1
96 | Pre -dec -snagging |  | 2026-06-20 | 2026-06-21 | 1
96 | Pre -dec -snagging |  | 2026-06-25 | 2026-06-28 | 2
97 | MCL |  | 2025-12-07 | 2025-12-08 | 1
97 | MCL |  | 2025-12-14 | 2025-12-15 | 1
97 | MCL |  | 2025-12-21 | 2025-12-22 | 1
97 | MCL |  | 2025-12-28 | 2025-12-29 | 1
97 | MCL |  | 2026-01-05 | 2026-01-06 | 2
97 | MCL |  | 2026-01-12 | 2026-01-13 | 2
97 | MCL |  | 2026-01-19 | 2026-01-21 | 3
97 | MCL |  | 2026-01-25 | 2026-03-03 | 27
97 | MCL |  | 2026-03-06 | 2026-03-07 | 1
97 | MCL |  | 2026-03-13 | 2026-03-14 | 1
97 | MCL |  | 2026-03-20 | 2026-03-21 | 1
97 | MCL |  | 2026-03-27 | 2026-03-28 | 1
97 | MCL |  | 2026-04-04 | 2026-04-05 | 1
97 | MCL |  | 2026-04-11 | 2026-04-12 | 1
97 | MCL |  | 2026-04-15 | 2026-04-21 | 5
97 | MCL |  | 2026-04-25 | 2026-04-26 | 1
97 | MCL |  | 2026-05-01 | 2026-05-02 | 1
97 | MCL |  | 2026-05-08 | 2026-05-09 | 1
97 | MCL |  | 2026-05-15 | 2026-05-16 | 1
97 | MCL |  | 2026-05-22 | 2026-05-23 | 1
97 | MCL |  | 2026-05-29 | 2026-05-30 | 1
97 | MCL |  | 2026-06-06 | 2026-06-07 | 1
97 | MCL |  | 2026-06-13 | 2026-06-14 | 1
97 | MCL |  | 2026-06-20 | 2026-06-21 | 1
97 | MCL |  | 2026-06-25 | 2026-06-28 | 2
98 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
98 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
98 | PANACEA |  | 2025-12-21 | 2025-12-29 | 6
98 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
98 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
98 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
98 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
98 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
98 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
98 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
98 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
98 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
98 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
98 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
98 | PANACEA |  | 2026-04-22 | 2026-04-26 | 3
98 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
98 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
98 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
98 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
98 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
98 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
98 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
98 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
98 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
99 | TECL |  | 2025-12-07 | 2025-12-08 | 1
99 | TECL |  | 2025-12-14 | 2025-12-15 | 1
99 | TECL |  | 2025-12-21 | 2025-12-22 | 1
99 | TECL |  | 2025-12-28 | 2026-01-06 | 7
99 | TECL |  | 2026-01-12 | 2026-01-13 | 2
99 | TECL |  | 2026-01-19 | 2026-01-21 | 3
99 | TECL |  | 2026-01-25 | 2026-03-03 | 27
99 | TECL |  | 2026-03-06 | 2026-03-07 | 1
99 | TECL |  | 2026-03-13 | 2026-03-14 | 1
99 | TECL |  | 2026-03-20 | 2026-03-21 | 1
99 | TECL |  | 2026-03-27 | 2026-03-28 | 1
99 | TECL |  | 2026-04-04 | 2026-04-05 | 1
99 | TECL |  | 2026-04-11 | 2026-04-12 | 1
99 | TECL |  | 2026-04-18 | 2026-04-19 | 1
99 | TECL |  | 2026-04-25 | 2026-05-02 | 5
99 | TECL |  | 2026-05-08 | 2026-05-09 | 1
99 | TECL |  | 2026-05-15 | 2026-05-16 | 1
99 | TECL |  | 2026-05-22 | 2026-05-23 | 1
99 | TECL |  | 2026-05-29 | 2026-05-30 | 1
99 | TECL |  | 2026-06-06 | 2026-06-07 | 1
99 | TECL |  | 2026-06-13 | 2026-06-14 | 1
99 | TECL |  | 2026-06-20 | 2026-06-21 | 1
99 | TECL |  | 2026-06-25 | 2026-06-28 | 2
100 | Sparkle clean |  | 2025-12-07 | 2025-12-08 | 1
100 | Sparkle clean |  | 2025-12-14 | 2025-12-15 | 1
100 | Sparkle clean |  | 2025-12-21 | 2025-12-22 | 1
100 | Sparkle clean |  | 2025-12-28 | 2025-12-29 | 1
100 | Sparkle clean |  | 2026-01-05 | 2026-01-06 | 2
100 | Sparkle clean |  | 2026-01-12 | 2026-01-13 | 2
100 | Sparkle clean |  | 2026-01-19 | 2026-01-21 | 3
100 | Sparkle clean |  | 2026-01-25 | 2026-03-03 | 27
100 | Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
100 | Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
100 | Sparkle clean |  | 2026-03-20 | 2026-03-21 | 1
100 | Sparkle clean |  | 2026-03-27 | 2026-03-28 | 1
100 | Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
100 | Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
100 | Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
100 | Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
100 | Sparkle clean |  | 2026-05-01 | 2026-05-09 | 6
100 | Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
100 | Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
100 | Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
100 | Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
100 | Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
100 | Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
100 | Sparkle clean |  | 2026-06-25 | 2026-06-28 | 2
101 | MCL |  | 2025-12-07 | 2025-12-08 | 1
101 | MCL |  | 2025-12-14 | 2025-12-15 | 1
101 | MCL |  | 2025-12-21 | 2025-12-22 | 1
101 | MCL |  | 2025-12-28 | 2025-12-29 | 1
101 | MCL |  | 2026-01-05 | 2026-01-06 | 2
101 | MCL |  | 2026-01-12 | 2026-01-13 | 2
101 | MCL |  | 2026-01-19 | 2026-01-21 | 3
101 | MCL |  | 2026-01-25 | 2026-03-03 | 27
101 | MCL |  | 2026-03-06 | 2026-03-07 | 1
101 | MCL |  | 2026-03-13 | 2026-03-14 | 1
101 | MCL |  | 2026-03-20 | 2026-03-21 | 1
101 | MCL |  | 2026-03-27 | 2026-03-28 | 1
101 | MCL |  | 2026-04-04 | 2026-04-05 | 1
101 | MCL |  | 2026-04-11 | 2026-04-12 | 1
101 | MCL |  | 2026-04-18 | 2026-04-19 | 1
101 | MCL |  | 2026-04-25 | 2026-04-26 | 1
101 | MCL |  | 2026-05-01 | 2026-05-02 | 1
101 | MCL |  | 2026-05-08 | 2026-05-11 | 2
101 | MCL |  | 2026-05-15 | 2026-05-16 | 1
101 | MCL |  | 2026-05-22 | 2026-05-23 | 1
101 | MCL |  | 2026-05-29 | 2026-05-30 | 1
101 | MCL |  | 2026-06-06 | 2026-06-07 | 1
101 | MCL |  | 2026-06-13 | 2026-06-14 | 1
101 | MCL |  | 2026-06-20 | 2026-06-21 | 1
101 | MCL |  | 2026-06-25 | 2026-06-28 | 2
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-15 | 1
| Handover to client |  | 2025-12-21 | 2025-12-22 | 1
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-12 | 2026-01-13 | 2
| Handover to client |  | 2026-01-19 | 2026-01-21 | 3
| Handover to client |  | 2026-01-25 | 2026-03-03 | 27
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-24 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2026-06-25 | 2026-06-28 | 2
103 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
103 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
103 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
103 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
103 | PANACEA |  | 2026-01-05 | 2026-01-13 | 7
103 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
103 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
103 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
103 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
103 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
103 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
103 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
103 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
103 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
103 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
103 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
103 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
103 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
103 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
103 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
103 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
103 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
103 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
103 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
| 2nd fix Partitions - insulation and board |  | 2025-12-07 | 2025-12-08 | 1
| 2nd fix Partitions - insulation and board |  | 2025-12-14 | 2025-12-15 | 1
| 2nd fix Partitions - insulation and board |  | 2025-12-21 | 2025-12-22 | 1
| 2nd fix Partitions - insulation and board |  | 2025-12-28 | 2025-12-29 | 1
| 2nd fix Partitions - insulation and board |  | 2026-01-05 | 2026-01-06 | 2
| 2nd fix Partitions - insulation and board |  | 2026-01-10 | 2026-01-14 | 3
| 2nd fix Partitions - insulation and board |  | 2026-01-19 | 2026-01-20 | 2
| 2nd fix Partitions - insulation and board |  | 2026-01-25 | 2026-03-03 | 27
| 2nd fix Partitions - insulation and board |  | 2026-03-06 | 2026-03-07 | 1
| 2nd fix Partitions - insulation and board |  | 2026-03-13 | 2026-03-14 | 1
| 2nd fix Partitions - insulation and board |  | 2026-03-20 | 2026-03-21 | 1
| 2nd fix Partitions - insulation and board |  | 2026-03-27 | 2026-03-28 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-04 | 2026-04-05 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-11 | 2026-04-12 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-18 | 2026-04-19 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-25 | 2026-04-26 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-01 | 2026-05-02 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-08 | 2026-05-09 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-15 | 2026-05-16 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-22 | 2026-05-23 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-29 | 2026-05-30 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-06 | 2026-06-07 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-13 | 2026-06-14 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-20 | 2026-06-21 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-25 | 2026-06-28 | 2
Ceilings board | Install Vents/ducts |  | 2025-12-07 | 2025-12-08 | 1
Ceilings board | Install Vents/ducts |  | 2025-12-14 | 2025-12-15 | 1
Ceilings board | Install Vents/ducts |  | 2025-12-21 | 2025-12-22 | 1
Ceilings board | Install Vents/ducts |  | 2025-12-28 | 2025-12-29 | 1
Ceilings board | Install Vents/ducts |  | 2026-01-05 | 2026-01-06 | 2
Ceilings board | Install Vents/ducts |  | 2026-01-12 | 2026-01-13 | 2
Ceilings board | Install Vents/ducts |  | 2026-01-15 | 2026-01-20 | 4
Ceilings board | Install Vents/ducts |  | 2026-01-25 | 2026-03-03 | 27
Ceilings board | Install Vents/ducts |  | 2026-03-06 | 2026-03-07 | 1
Ceilings board | Install Vents/ducts |  | 2026-03-13 | 2026-03-14 | 1
Ceilings board | Install Vents/ducts |  | 2026-03-20 | 2026-03-21 | 1
Ceilings board | Install Vents/ducts |  | 2026-03-27 | 2026-03-28 | 1
Ceilings board | Install Vents/ducts |  | 2026-04-04 | 2026-04-05 | 1
Ceilings board | Install Vents/ducts |  | 2026-04-11 | 2026-04-12 | 1
Ceilings board | Install Vents/ducts |  | 2026-04-18 | 2026-04-19 | 1
Ceilings board | Install Vents/ducts |  | 2026-04-25 | 2026-04-26 | 1
Ceilings board | Install Vents/ducts |  | 2026-05-01 | 2026-05-02 | 1
Ceilings board | Install Vents/ducts |  | 2026-05-08 | 2026-05-09 | 1
Ceilings board | Install Vents/ducts |  | 2026-05-15 | 2026-05-16 | 1
Ceilings board | Install Vents/ducts |  | 2026-05-22 | 2026-05-23 | 1
Ceilings board | Install Vents/ducts |  | 2026-05-29 | 2026-05-30 | 1
Ceilings board | Install Vents/ducts |  | 2026-06-06 | 2026-06-07 | 1
Ceilings board | Install Vents/ducts |  | 2026-06-13 | 2026-06-14 | 1
Ceilings board | Install Vents/ducts |  | 2026-06-20 | 2026-06-21 | 1
Ceilings board | Install Vents/ducts |  | 2026-06-25 | 2026-06-28 | 2
| CONTROL POINT 3 CP3 |  | 2025-12-07 | 2025-12-08 | 1
| CONTROL POINT 3 CP3 |  | 2025-12-14 | 2025-12-15 | 1
| CONTROL POINT 3 CP3 |  | 2025-12-21 | 2025-12-22 | 1
| CONTROL POINT 3 CP3 |  | 2025-12-28 | 2025-12-29 | 1
| CONTROL POINT 3 CP3 |  | 2026-01-05 | 2026-01-06 | 2
| CONTROL POINT 3 CP3 |  | 2026-01-12 | 2026-01-13 | 2
| CONTROL POINT 3 CP3 |  | 2026-01-15 | 2026-01-20 | 4
| CONTROL POINT 3 CP3 |  | 2026-01-25 | 2026-03-03 | 27
| CONTROL POINT 3 CP3 |  | 2026-03-06 | 2026-03-07 | 1
| CONTROL POINT 3 CP3 |  | 2026-03-13 | 2026-03-14 | 1
| CONTROL POINT 3 CP3 |  | 2026-03-20 | 2026-03-21 | 1
| CONTROL POINT 3 CP3 |  | 2026-03-27 | 2026-03-28 | 1
| CONTROL POINT 3 CP3 |  | 2026-04-04 | 2026-04-05 | 1
| CONTROL POINT 3 CP3 |  | 2026-04-11 | 2026-04-12 | 1
| CONTROL POINT 3 CP3 |  | 2026-04-18 | 2026-04-19 | 1
| CONTROL POINT 3 CP3 |  | 2026-04-25 | 2026-04-26 | 1
| CONTROL POINT 3 CP3 |  | 2026-05-01 | 2026-05-02 | 1
| CONTROL POINT 3 CP3 |  | 2026-05-08 | 2026-05-09 | 1
| CONTROL POINT 3 CP3 |  | 2026-05-15 | 2026-05-16 | 1
| CONTROL POINT 3 CP3 |  | 2026-05-22 | 2026-05-23 | 1
| CONTROL POINT 3 CP3 |  | 2026-05-29 | 2026-05-30 | 1
| CONTROL POINT 3 CP3 |  | 2026-06-06 | 2026-06-07 | 1
| CONTROL POINT 3 CP3 |  | 2026-06-13 | 2026-06-14 | 1
| CONTROL POINT 3 CP3 |  | 2026-06-20 | 2026-06-21 | 1
| CONTROL POINT 3 CP3 |  | 2026-06-25 | 2026-06-28 | 2
105 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
105 | Active flooring |  | 2025-12-14 | 2025-12-15 | 1
105 | Active flooring |  | 2025-12-21 | 2025-12-22 | 1
105 | Active flooring |  | 2025-12-28 | 2025-12-29 | 1
105 | Active flooring |  | 2026-01-05 | 2026-01-06 | 2
105 | Active flooring |  | 2026-01-12 | 2026-01-13 | 2
105 | Active flooring |  | 2026-01-19 | 2026-01-21 | 3
105 | Active flooring |  | 2026-01-23 | 2026-03-03 | 28
105 | Active flooring |  | 2026-03-06 | 2026-03-07 | 1
105 | Active flooring |  | 2026-03-13 | 2026-03-14 | 1
105 | Active flooring |  | 2026-03-20 | 2026-03-21 | 1
105 | Active flooring |  | 2026-03-27 | 2026-03-28 | 1
105 | Active flooring |  | 2026-04-04 | 2026-04-05 | 1
105 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
105 | Active flooring |  | 2026-04-18 | 2026-04-19 | 1
105 | Active flooring |  | 2026-04-25 | 2026-04-26 | 1
105 | Active flooring |  | 2026-05-01 | 2026-05-02 | 1
105 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
105 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
105 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
105 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
105 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
105 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
105 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
105 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
106 | MCL |  | 2025-12-07 | 2025-12-08 | 1
106 | MCL |  | 2025-12-14 | 2025-12-15 | 1
106 | MCL |  | 2025-12-21 | 2025-12-22 | 1
106 | MCL |  | 2025-12-28 | 2025-12-29 | 1
106 | MCL |  | 2026-01-05 | 2026-01-06 | 2
106 | MCL |  | 2026-01-12 | 2026-01-13 | 2
106 | MCL |  | 2026-01-19 | 2026-01-21 | 3
106 | MCL |  | 2026-01-25 | 2026-03-03 | 27
106 | MCL |  | 2026-03-06 | 2026-03-07 | 1
106 | MCL |  | 2026-03-13 | 2026-03-14 | 1
106 | MCL |  | 2026-03-20 | 2026-03-21 | 1
106 | MCL |  | 2026-03-27 | 2026-03-28 | 1
106 | MCL |  | 2026-04-04 | 2026-04-05 | 1
106 | MCL |  | 2026-04-11 | 2026-04-12 | 1
106 | MCL |  | 2026-04-18 | 2026-04-19 | 1
106 | MCL |  | 2026-04-25 | 2026-04-26 | 1
106 | MCL |  | 2026-05-01 | 2026-05-02 | 1
106 | MCL |  | 2026-05-08 | 2026-05-09 | 1
106 | MCL |  | 2026-05-15 | 2026-05-16 | 1
106 | MCL |  | 2026-05-22 | 2026-05-23 | 1
106 | MCL |  | 2026-05-29 | 2026-05-30 | 1
106 | MCL |  | 2026-06-06 | 2026-06-07 | 1
106 | MCL |  | 2026-06-13 | 2026-06-14 | 1
106 | MCL |  | 2026-06-20 | 2026-06-21 | 1
106 | MCL |  | 2026-06-25 | 2026-06-28 | 2
107 | Sprinkler 2nd fix & test |  | 2025-12-07 | 2025-12-08 | 1
107 | Sprinkler 2nd fix & test |  | 2025-12-14 | 2025-12-15 | 1
107 | Sprinkler 2nd fix & test |  | 2025-12-21 | 2025-12-22 | 1
107 | Sprinkler 2nd fix & test |  | 2025-12-28 | 2025-12-29 | 1
107 | Sprinkler 2nd fix & test |  | 2026-01-05 | 2026-01-06 | 2
107 | Sprinkler 2nd fix & test |  | 2026-01-12 | 2026-01-13 | 2
107 | Sprinkler 2nd fix & test |  | 2026-01-19 | 2026-01-21 | 3
107 | Sprinkler 2nd fix & test |  | 2026-01-25 | 2026-03-03 | 27
107 | Sprinkler 2nd fix & test |  | 2026-03-06 | 2026-03-07 | 1
107 | Sprinkler 2nd fix & test |  | 2026-03-13 | 2026-03-14 | 1
107 | Sprinkler 2nd fix & test |  | 2026-03-20 | 2026-03-21 | 1
107 | Sprinkler 2nd fix & test |  | 2026-03-27 | 2026-03-28 | 1
107 | Sprinkler 2nd fix & test |  | 2026-04-04 | 2026-04-05 | 1
107 | Sprinkler 2nd fix & test |  | 2026-04-11 | 2026-04-12 | 1
107 | Sprinkler 2nd fix & test |  | 2026-04-18 | 2026-04-19 | 1
107 | Sprinkler 2nd fix & test |  | 2026-04-25 | 2026-04-26 | 1
107 | Sprinkler 2nd fix & test |  | 2026-05-01 | 2026-05-02 | 1
107 | Sprinkler 2nd fix & test |  | 2026-05-08 | 2026-05-09 | 1
107 | Sprinkler 2nd fix & test |  | 2026-05-15 | 2026-05-16 | 1
107 | Sprinkler 2nd fix & test |  | 2026-05-22 | 2026-05-23 | 1
107 | Sprinkler 2nd fix & test |  | 2026-05-29 | 2026-05-30 | 1
107 | Sprinkler 2nd fix & test |  | 2026-06-06 | 2026-06-07 | 1
107 | Sprinkler 2nd fix & test |  | 2026-06-13 | 2026-06-14 | 1
107 | Sprinkler 2nd fix & test |  | 2026-06-20 | 2026-06-21 | 1
107 | Sprinkler 2nd fix & test |  | 2026-06-25 | 2026-06-28 | 2
108 | MCL |  | 2025-12-07 | 2025-12-09 | 2
108 | MCL |  | 2025-12-14 | 2025-12-15 | 1
108 | MCL |  | 2025-12-21 | 2025-12-22 | 1
108 | MCL |  | 2025-12-28 | 2025-12-29 | 1
108 | MCL |  | 2026-01-05 | 2026-01-06 | 2
108 | MCL |  | 2026-01-12 | 2026-01-13 | 2
108 | MCL |  | 2026-01-19 | 2026-01-21 | 3
108 | MCL |  | 2026-01-25 | 2026-03-03 | 27
108 | MCL |  | 2026-03-06 | 2026-03-07 | 1
108 | MCL |  | 2026-03-13 | 2026-03-14 | 1
108 | MCL |  | 2026-03-20 | 2026-03-21 | 1
108 | MCL |  | 2026-03-27 | 2026-03-28 | 1
108 | MCL |  | 2026-04-04 | 2026-04-05 | 1
108 | MCL |  | 2026-04-11 | 2026-04-12 | 1
108 | MCL |  | 2026-04-18 | 2026-04-19 | 1
108 | MCL |  | 2026-04-25 | 2026-04-26 | 1
108 | MCL |  | 2026-05-01 | 2026-05-02 | 1
108 | MCL |  | 2026-05-08 | 2026-05-09 | 1
108 | MCL |  | 2026-05-15 | 2026-05-16 | 1
108 | MCL |  | 2026-05-22 | 2026-05-23 | 1
108 | MCL |  | 2026-05-29 | 2026-05-30 | 1
108 | MCL |  | 2026-06-06 | 2026-06-07 | 1
108 | MCL |  | 2026-06-13 | 2026-06-14 | 1
108 | MCL |  | 2026-06-20 | 2026-06-21 | 1
108 | MCL |  | 2026-06-25 | 2026-06-28 | 2
109 | Active flooring |  | 2025-12-07 | 2025-12-08 | 1
109 | Active flooring |  | 2025-12-14 | 2025-12-15 | 1
109 | Active flooring |  | 2025-12-21 | 2025-12-22 | 1
109 | Active flooring |  | 2025-12-28 | 2025-12-29 | 1
109 | Active flooring |  | 2026-01-05 | 2026-01-06 | 2
109 | Active flooring |  | 2026-01-12 | 2026-01-13 | 2
109 | Active flooring |  | 2026-01-19 | 2026-01-21 | 3
109 | Active flooring |  | 2026-01-25 | 2026-03-04 | 28
109 | Active flooring |  | 2026-03-06 | 2026-03-07 | 1
109 | Active flooring |  | 2026-03-13 | 2026-03-14 | 1
109 | Active flooring |  | 2026-03-20 | 2026-03-21 | 1
109 | Active flooring |  | 2026-03-27 | 2026-03-28 | 1
109 | Active flooring |  | 2026-04-04 | 2026-04-05 | 1
109 | Active flooring |  | 2026-04-11 | 2026-04-12 | 1
109 | Active flooring |  | 2026-04-18 | 2026-04-19 | 1
109 | Active flooring |  | 2026-04-25 | 2026-04-26 | 1
109 | Active flooring |  | 2026-05-01 | 2026-05-02 | 1
109 | Active flooring |  | 2026-05-08 | 2026-05-09 | 1
109 | Active flooring |  | 2026-05-15 | 2026-05-16 | 1
109 | Active flooring |  | 2026-05-22 | 2026-05-23 | 1
109 | Active flooring |  | 2026-05-29 | 2026-05-30 | 1
109 | Active flooring |  | 2026-06-06 | 2026-06-07 | 1
109 | Active flooring |  | 2026-06-13 | 2026-06-14 | 1
109 | Active flooring |  | 2026-06-20 | 2026-06-21 | 1
109 | Active flooring |  | 2026-06-25 | 2026-06-28 | 2
110 | Branniff |  | 2025-12-07 | 2025-12-08 | 1
110 | Branniff |  | 2025-12-14 | 2025-12-15 | 1
110 | Branniff |  | 2025-12-21 | 2025-12-22 | 1
110 | Branniff |  | 2025-12-28 | 2025-12-29 | 1
110 | Branniff |  | 2026-01-05 | 2026-01-06 | 2
110 | Branniff |  | 2026-01-12 | 2026-01-13 | 2
110 | Branniff |  | 2026-01-19 | 2026-01-21 | 3
110 | Branniff |  | 2026-01-25 | 2026-03-03 | 27
110 | Branniff |  | 2026-03-05 | 2026-03-11 | 5
110 | Branniff |  | 2026-03-13 | 2026-03-14 | 1
110 | Branniff |  | 2026-03-20 | 2026-03-21 | 1
110 | Branniff |  | 2026-03-27 | 2026-03-28 | 1
110 | Branniff |  | 2026-04-04 | 2026-04-05 | 1
110 | Branniff |  | 2026-04-11 | 2026-04-12 | 1
110 | Branniff |  | 2026-04-18 | 2026-04-19 | 1
110 | Branniff |  | 2026-04-25 | 2026-04-26 | 1
110 | Branniff |  | 2026-05-01 | 2026-05-02 | 1
110 | Branniff |  | 2026-05-08 | 2026-05-09 | 1
110 | Branniff |  | 2026-05-15 | 2026-05-16 | 1
110 | Branniff |  | 2026-05-22 | 2026-05-23 | 1
110 | Branniff |  | 2026-05-29 | 2026-05-30 | 1
110 | Branniff |  | 2026-06-06 | 2026-06-07 | 1
110 | Branniff |  | 2026-06-13 | 2026-06-14 | 1
110 | Branniff |  | 2026-06-20 | 2026-06-21 | 1
110 | Branniff |  | 2026-06-25 | 2026-06-28 | 2
Drying out | Wren |  | 2025-12-07 | 2025-12-08 | 1
Drying out | Wren |  | 2025-12-14 | 2025-12-15 | 1
Drying out | Wren |  | 2025-12-21 | 2025-12-22 | 1
Drying out | Wren |  | 2025-12-28 | 2025-12-29 | 1
Drying out | Wren |  | 2026-01-05 | 2026-01-06 | 2
Drying out | Wren |  | 2026-01-12 | 2026-01-13 | 2
Drying out | Wren |  | 2026-01-19 | 2026-01-21 | 3
Drying out | Wren |  | 2026-01-25 | 2026-03-03 | 27
Drying out | Wren |  | 2026-03-06 | 2026-03-07 | 1
Drying out | Wren |  | 2026-03-13 | 2026-03-14 | 1
Drying out | Wren |  | 2026-03-20 | 2026-03-21 | 1
Drying out | Wren |  | 2026-03-27 | 2026-03-28 | 1
Drying out | Wren |  | 2026-04-04 | 2026-04-05 | 1
Drying out | Wren |  | 2026-04-11 | 2026-04-12 | 1
Drying out | Wren |  | 2026-04-18 | 2026-04-19 | 1
Drying out | Wren |  | 2026-04-25 | 2026-04-26 | 1
Drying out | Wren |  | 2026-05-01 | 2026-05-02 | 1
Drying out | Wren |  | 2026-05-08 | 2026-05-09 | 1
Drying out | Wren |  | 2026-05-15 | 2026-05-16 | 1
Drying out | Wren |  | 2026-05-22 | 2026-05-23 | 1
Drying out | Wren |  | 2026-05-29 | 2026-05-30 | 1
Drying out | Wren |  | 2026-06-06 | 2026-06-07 | 1
Drying out | Wren |  | 2026-06-13 | 2026-06-14 | 1
Drying out | Wren |  | 2026-06-20 | 2026-06-21 | 1
Drying out | Wren |  | 2026-06-25 | 2026-06-28 | 2
| Mist coat |  | 2025-12-07 | 2025-12-08 | 1
| Mist coat |  | 2025-12-14 | 2025-12-15 | 1
| Mist coat |  | 2025-12-21 | 2025-12-22 | 1
| Mist coat |  | 2025-12-28 | 2025-12-29 | 1
| Mist coat |  | 2026-01-05 | 2026-01-06 | 2
| Mist coat |  | 2026-01-12 | 2026-01-13 | 2
| Mist coat |  | 2026-01-19 | 2026-01-21 | 3
| Mist coat |  | 2026-01-25 | 2026-03-07 | 30
| Mist coat |  | 2026-03-13 | 2026-03-14 | 1
| Mist coat |  | 2026-03-20 | 2026-03-21 | 1
| Mist coat |  | 2026-03-27 | 2026-03-28 | 1
| Mist coat |  | 2026-04-04 | 2026-04-05 | 1
| Mist coat |  | 2026-04-11 | 2026-04-12 | 1
| Mist coat |  | 2026-04-18 | 2026-04-19 | 1
| Mist coat |  | 2026-04-25 | 2026-04-26 | 1
| Mist coat |  | 2026-05-01 | 2026-05-02 | 1
| Mist coat |  | 2026-05-08 | 2026-05-09 | 1
| Mist coat |  | 2026-05-15 | 2026-05-16 | 1
| Mist coat |  | 2026-05-22 | 2026-05-23 | 1
| Mist coat |  | 2026-05-29 | 2026-05-30 | 1
| Mist coat |  | 2026-06-06 | 2026-06-07 | 1
| Mist coat |  | 2026-06-13 | 2026-06-14 | 1
| Mist coat |  | 2026-06-20 | 2026-06-21 | 1
| Mist coat |  | 2026-06-25 | 2026-06-28 | 2
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-08 | 1
| Vanity 1st fix framing |  | 2025-12-14 | 2025-12-15 | 1
| Vanity 1st fix framing |  | 2025-12-21 | 2025-12-22 | 1
| Vanity 1st fix framing |  | 2025-12-28 | 2025-12-29 | 1
| Vanity 1st fix framing |  | 2026-01-05 | 2026-01-06 | 2
| Vanity 1st fix framing |  | 2026-01-12 | 2026-01-13 | 2
| Vanity 1st fix framing |  | 2026-01-19 | 2026-01-21 | 3
| Vanity 1st fix framing |  | 2026-01-25 | 2026-03-03 | 27
| Vanity 1st fix framing |  | 2026-03-06 | 2026-03-07 | 1
| Vanity 1st fix framing |  | 2026-03-13 | 2026-03-14 | 1
| Vanity 1st fix framing |  | 2026-03-20 | 2026-03-21 | 1
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2026-06-25 | 2026-06-28 | 2
111 | Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-08 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2025-12-14 | 2025-12-15 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2025-12-21 | 2025-12-22 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2025-12-28 | 2025-12-29 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-06 | 2
111 | Kitchen 1st fix,units tops & appliances |  | 2026-01-12 | 2026-01-13 | 2
111 | Kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-21 | 3
111 | Kitchen 1st fix,units tops & appliances |  | 2026-01-25 | 2026-03-03 | 27
111 | Kitchen 1st fix,units tops & appliances |  | 2026-03-06 | 2026-03-07 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-03-13 | 2026-03-14 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-03-20 | 2026-03-28 | 6
111 | Kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-05 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-05-15 | 2026-05-16 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-05-22 | 2026-05-23 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-06-20 | 2026-06-21 | 1
111 | Kitchen 1st fix,units tops & appliances |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-21 | 2025-12-22 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-28 | 2025-12-29 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-25 | 2026-03-03 | 27
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-10 | 2026-03-16 | 5
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-25 | 2026-06-28 | 2
112 | PANACEA |  | 2025-12-07 | 2025-12-08 | 1
112 | PANACEA |  | 2025-12-14 | 2025-12-15 | 1
112 | PANACEA |  | 2025-12-21 | 2025-12-22 | 1
112 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
112 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
112 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
112 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
112 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
112 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
112 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
112 | PANACEA |  | 2026-03-18 | 2026-03-24 | 5
112 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
112 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
112 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
112 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
112 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
112 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
112 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
112 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
112 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
112 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
112 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
112 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
112 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
112 | PANACEA |  | 2026-06-25 | 2026-06-28 | 2
113 | Edencroft |  | 2025-12-07 | 2025-12-08 | 1
113 | Edencroft |  | 2025-12-14 | 2025-12-15 | 1
113 | Edencroft |  | 2025-12-21 | 2025-12-22 | 1
113 | Edencroft |  | 2025-12-28 | 2025-12-29 | 1
113 | Edencroft |  | 2026-01-05 | 2026-01-06 | 2
113 | Edencroft |  | 2026-01-12 | 2026-01-13 | 2
113 | Edencroft |  | 2026-01-19 | 2026-01-21 | 3
113 | Edencroft |  | 2026-01-25 | 2026-03-03 | 27
113 | Edencroft |  | 2026-03-06 | 2026-03-07 | 1
113 | Edencroft |  | 2026-03-13 | 2026-03-21 | 6
113 | Edencroft |  | 2026-03-27 | 2026-03-28 | 1
113 | Edencroft |  | 2026-04-04 | 2026-04-05 | 1
113 | Edencroft |  | 2026-04-11 | 2026-04-12 | 1
113 | Edencroft |  | 2026-04-18 | 2026-04-19 | 1
113 | Edencroft |  | 2026-04-25 | 2026-04-26 | 1
113 | Edencroft |  | 2026-05-01 | 2026-05-02 | 1
113 | Edencroft |  | 2026-05-08 | 2026-05-09 | 1
113 | Edencroft |  | 2026-05-15 | 2026-05-16 | 1
113 | Edencroft |  | 2026-05-22 | 2026-05-23 | 1
113 | Edencroft |  | 2026-05-29 | 2026-05-30 | 1
113 | Edencroft |  | 2026-06-06 | 2026-06-07 | 1
113 | Edencroft |  | 2026-06-13 | 2026-06-14 | 1
113 | Edencroft |  | 2026-06-20 | 2026-06-21 | 1
113 | Edencroft |  | 2026-06-25 | 2026-06-28 | 2
| Control point 4 CP 4 |  | 2025-12-07 | 2025-12-08 | 1
| Control point 4 CP 4 |  | 2025-12-14 | 2025-12-15 | 1
| Control point 4 CP 4 |  | 2025-12-21 | 2025-12-22 | 1
| Control point 4 CP 4 |  | 2025-12-28 | 2025-12-29 | 1
| Control point 4 CP 4 |  | 2026-01-05 | 2026-01-06 | 2
| Control point 4 CP 4 |  | 2026-01-12 | 2026-01-13 | 2
| Control point 4 CP 4 |  | 2026-01-19 | 2026-01-21 | 3
| Control point 4 CP 4 |  | 2026-01-25 | 2026-03-03 | 27
| Control point 4 CP 4 |  | 2026-03-06 | 2026-03-07 | 1
| Control point 4 CP 4 |  | 2026-03-13 | 2026-03-14 | 1
| Control point 4 CP 4 |  | 2026-03-20 | 2026-03-21 | 1
| Control point 4 CP 4 |  | 2026-03-27 | 2026-03-28 | 1
| Control point 4 CP 4 |  | 2026-04-04 | 2026-04-05 | 1
| Control point 4 CP 4 |  | 2026-04-11 | 2026-04-12 | 1
| Control point 4 CP 4 |  | 2026-04-18 | 2026-04-19 | 1
| Control point 4 CP 4 |  | 2026-04-25 | 2026-04-26 | 1
| Control point 4 CP 4 |  | 2026-05-01 | 2026-05-02 | 1
| Control point 4 CP 4 |  | 2026-05-08 | 2026-05-09 | 1
| Control point 4 CP 4 |  | 2026-05-15 | 2026-05-16 | 1
| Control point 4 CP 4 |  | 2026-05-22 | 2026-05-23 | 1
| Control point 4 CP 4 |  | 2026-05-29 | 2026-05-30 | 1
| Control point 4 CP 4 |  | 2026-06-06 | 2026-06-07 | 1
| Control point 4 CP 4 |  | 2026-06-13 | 2026-06-14 | 1
| Control point 4 CP 4 |  | 2026-06-20 | 2026-06-21 | 1
| Control point 4 CP 4 |  | 2026-06-25 | 2026-06-28 | 2
114 | GPL |  | 2025-12-07 | 2025-12-08 | 1
114 | GPL |  | 2025-12-13 | 2025-12-15 | 1
114 | GPL |  | 2025-12-21 | 2025-12-22 | 1
114 | GPL |  | 2025-12-28 | 2025-12-29 | 1
114 | GPL |  | 2026-01-05 | 2026-01-06 | 2
114 | GPL |  | 2026-01-12 | 2026-01-13 | 2
114 | GPL |  | 2026-01-19 | 2026-01-21 | 3
114 | GPL |  | 2026-01-25 | 2026-03-03 | 27
114 | GPL |  | 2026-03-06 | 2026-03-07 | 1
114 | GPL |  | 2026-03-13 | 2026-03-14 | 1
114 | GPL |  | 2026-03-20 | 2026-03-21 | 1
114 | GPL |  | 2026-03-23 | 2026-03-24 | 2
114 | GPL |  | 2026-03-27 | 2026-03-28 | 1
114 | GPL |  | 2026-04-04 | 2026-04-05 | 1
114 | GPL |  | 2026-04-11 | 2026-04-12 | 1
114 | GPL |  | 2026-04-18 | 2026-04-19 | 1
114 | GPL |  | 2026-04-25 | 2026-04-26 | 1
114 | GPL |  | 2026-05-01 | 2026-05-02 | 1
114 | GPL |  | 2026-05-08 | 2026-05-09 | 1
114 | GPL |  | 2026-05-15 | 2026-05-16 | 1
114 | GPL |  | 2026-05-22 | 2026-05-23 | 1
114 | GPL |  | 2026-05-29 | 2026-05-30 | 1
114 | GPL |  | 2026-06-06 | 2026-06-07 | 1
114 | GPL |  | 2026-06-13 | 2026-06-14 | 1
114 | GPL |  | 2026-06-20 | 2026-06-21 | 1
114 | GPL |  | 2026-06-25 | 2026-06-28 | 2
115 | service cupboard decoration |  | 2025-12-07 | 2025-12-08 | 1
115 | service cupboard decoration |  | 2025-12-14 | 2025-12-15 | 1
115 | service cupboard decoration |  | 2025-12-21 | 2025-12-22 | 1
115 | service cupboard decoration |  | 2025-12-28 | 2026-01-06 | 7
115 | service cupboard decoration |  | 2026-01-12 | 2026-01-13 | 2
115 | service cupboard decoration |  | 2026-01-19 | 2026-01-21 | 3
115 | service cupboard decoration |  | 2026-01-25 | 2026-03-03 | 27
115 | service cupboard decoration |  | 2026-03-06 | 2026-03-07 | 1
115 | service cupboard decoration |  | 2026-03-13 | 2026-03-14 | 1
115 | service cupboard decoration |  | 2026-03-20 | 2026-03-21 | 1
115 | service cupboard decoration |  | 2026-03-25 | 2026-03-28 | 3
115 | service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
115 | service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
115 | service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
115 | service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
115 | service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
115 | service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
115 | service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
115 | service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
115 | service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
115 | service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
115 | service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
115 | service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
115 | service cupboard decoration |  | 2026-06-25 | 2026-06-28 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-07 | 2025-12-08 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-14 | 2025-12-15 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-21 | 2025-12-22 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-28 | 2025-12-29 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-05 | 2026-01-06 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-12 | 2026-01-13 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-19 | 2026-01-21 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-25 | 2026-03-03 | 27
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-06 | 2026-03-07 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-13 | 2026-03-14 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-20 | 2026-03-21 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-27 | 2026-03-28 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-04 | 2026-04-05 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-11 | 2026-04-12 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-18 | 2026-04-19 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-25 | 2026-04-26 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-01 | 2026-05-02 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-08 | 2026-05-09 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-15 | 2026-05-16 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-22 | 2026-05-23 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-29 | 2026-05-30 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-06 | 2026-06-07 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-13 | 2026-06-14 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-20 | 2026-06-21 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-25 | 2026-06-28 | 2
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-08 | 1
| Amtico flooring /Bathrooms |  | 2025-12-14 | 2025-12-15 | 1
| Amtico flooring /Bathrooms |  | 2025-12-21 | 2025-12-22 | 1
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-21 | 3
| Amtico flooring /Bathrooms |  | 2026-01-25 | 2026-03-03 | 27
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-04-05 | 6
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2026-06-25 | 2026-06-28 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-08 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-14 | 2025-12-15 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2025-12-21 | 2025-12-29 | 6
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-12 | 2026-01-13 | 2
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing second fix sanitaryware & pressure testing |  | 2026-01-25 | 2026-03-03 | 27
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-20 | 2026-03-21 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-12 | 5
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing second fix sanitaryware & pressure testing |  | 2026-06-20 | 2026-06-21 | 1
| Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-08 | 1
| Electrical 2nd fix & live testing |  | 2025-12-14 | 2025-12-15 | 1
| Electrical 2nd fix & live testing |  | 2025-12-21 | 2025-12-22 | 1
| Electrical 2nd fix & live testing |  | 2025-12-28 | 2026-01-06 | 7
| Electrical 2nd fix & live testing |  | 2026-01-12 | 2026-01-13 | 2
| Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
| Electrical 2nd fix & live testing |  | 2026-01-25 | 2026-03-03 | 27
| Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
| Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
| Electrical 2nd fix & live testing |  | 2026-03-20 | 2026-03-21 | 1
| Electrical 2nd fix & live testing |  | 2026-03-27 | 2026-03-28 | 1
| Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
| Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-19 | 5
| Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
| Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
| Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
| Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
| Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
| Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
| Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
| Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
| Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
116 | Builders clean |  | 2025-12-07 | 2025-12-08 | 1
116 | Builders clean |  | 2025-12-14 | 2025-12-15 | 1
116 | Builders clean |  | 2025-12-21 | 2025-12-22 | 1
116 | Builders clean |  | 2025-12-28 | 2025-12-29 | 1
116 | Builders clean |  | 2026-01-05 | 2026-01-06 | 2
116 | Builders clean |  | 2026-01-12 | 2026-01-13 | 2
116 | Builders clean |  | 2026-01-19 | 2026-01-21 | 3
116 | Builders clean |  | 2026-01-25 | 2026-03-03 | 27
116 | Builders clean |  | 2026-03-06 | 2026-03-07 | 1
116 | Builders clean |  | 2026-03-13 | 2026-03-14 | 1
116 | Builders clean |  | 2026-03-20 | 2026-03-21 | 1
116 | Builders clean |  | 2026-03-27 | 2026-03-28 | 1
116 | Builders clean |  | 2026-04-04 | 2026-04-05 | 1
116 | Builders clean |  | 2026-04-11 | 2026-04-12 | 1
116 | Builders clean |  | 2026-04-18 | 2026-04-19 | 1
116 | Builders clean |  | 2026-04-25 | 2026-04-26 | 1
116 | Builders clean |  | 2026-05-01 | 2026-05-02 | 1
116 | Builders clean |  | 2026-05-08 | 2026-05-09 | 1
116 | Builders clean |  | 2026-05-15 | 2026-05-16 | 1
116 | Builders clean |  | 2026-05-22 | 2026-05-23 | 1
116 | Builders clean |  | 2026-05-29 | 2026-05-30 | 1
116 | Builders clean |  | 2026-06-06 | 2026-06-07 | 1
116 | Builders clean |  | 2026-06-13 | 2026-06-14 | 1
116 | Builders clean |  | 2026-06-20 | 2026-06-21 | 1
117 | MCL |  | 2025-12-07 | 2025-12-12 | 5
117 | MCL |  | 2025-12-14 | 2025-12-16 | 2
117 | MCL |  | 2025-12-21 | 2025-12-24 | 3
117 | MCL |  | 2025-12-28 | 2025-12-29 | 1
117 | MCL |  | 2026-01-05 | 2026-01-06 | 2
117 | MCL |  | 2026-01-12 | 2026-01-13 | 2
117 | MCL |  | 2026-01-19 | 2026-01-21 | 3
117 | MCL |  | 2026-01-25 | 2026-03-03 | 27
117 | MCL |  | 2026-03-06 | 2026-03-07 | 1
117 | MCL |  | 2026-03-13 | 2026-03-14 | 1
117 | MCL |  | 2026-03-20 | 2026-03-21 | 1
117 | MCL |  | 2026-03-27 | 2026-03-28 | 1
117 | MCL |  | 2026-04-04 | 2026-04-05 | 1
117 | MCL |  | 2026-04-11 | 2026-04-12 | 1
117 | MCL |  | 2026-04-18 | 2026-04-19 | 1
117 | MCL |  | 2026-04-25 | 2026-04-26 | 1
117 | MCL |  | 2026-05-01 | 2026-05-02 | 1
117 | MCL |  | 2026-05-08 | 2026-05-09 | 1
117 | MCL |  | 2026-05-15 | 2026-05-16 | 1
117 | MCL |  | 2026-05-22 | 2026-05-23 | 1
117 | MCL |  | 2026-05-29 | 2026-05-30 | 1
117 | MCL |  | 2026-06-06 | 2026-06-07 | 1
117 | MCL |  | 2026-06-13 | 2026-06-14 | 1
117 | MCL |  | 2026-06-20 | 2026-06-21 | 1
118 | PANACEA |  | 2025-12-07 | 2025-12-12 | 5
118 | PANACEA |  | 2025-12-14 | 2025-12-16 | 2
118 | PANACEA |  | 2025-12-21 | 2025-12-24 | 3
118 | PANACEA |  | 2025-12-26 | 2026-01-01 | 5
118 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
118 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
118 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
118 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
118 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
118 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
118 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
118 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
118 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
118 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
118 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
118 | PANACEA |  | 2026-04-22 | 2026-04-28 | 5
118 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
118 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
118 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
118 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
118 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
118 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
118 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
118 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
119 | TECL |  | 2025-12-07 | 2025-12-12 | 5
119 | TECL |  | 2025-12-14 | 2025-12-16 | 2
119 | TECL |  | 2025-12-21 | 2025-12-24 | 3
119 | TECL |  | 2025-12-28 | 2025-12-29 | 1
119 | TECL |  | 2026-01-05 | 2026-01-13 | 7
119 | TECL |  | 2026-01-19 | 2026-01-21 | 3
119 | TECL |  | 2026-01-25 | 2026-03-03 | 27
119 | TECL |  | 2026-03-06 | 2026-03-07 | 1
119 | TECL |  | 2026-03-13 | 2026-03-14 | 1
119 | TECL |  | 2026-03-20 | 2026-03-21 | 1
119 | TECL |  | 2026-03-27 | 2026-03-28 | 1
119 | TECL |  | 2026-04-04 | 2026-04-05 | 1
119 | TECL |  | 2026-04-11 | 2026-04-12 | 1
119 | TECL |  | 2026-04-18 | 2026-04-19 | 1
119 | TECL |  | 2026-04-25 | 2026-04-26 | 1
119 | TECL |  | 2026-04-29 | 2026-05-02 | 3
119 | TECL |  | 2026-05-08 | 2026-05-09 | 1
119 | TECL |  | 2026-05-15 | 2026-05-16 | 1
119 | TECL |  | 2026-05-22 | 2026-05-23 | 1
119 | TECL |  | 2026-05-29 | 2026-05-30 | 1
119 | TECL |  | 2026-06-06 | 2026-06-07 | 1
119 | TECL |  | 2026-06-13 | 2026-06-14 | 1
119 | TECL |  | 2026-06-20 | 2026-06-21 | 1
120 | De snag all trades test & commision |  | 2025-12-07 | 2025-12-08 | 1
120 | De snag all trades test & commision |  | 2025-12-14 | 2025-12-15 | 1
120 | De snag all trades test & commision |  | 2025-12-21 | 2025-12-22 | 1
120 | De snag all trades test & commision |  | 2025-12-28 | 2025-12-29 | 1
120 | De snag all trades test & commision |  | 2026-01-05 | 2026-01-06 | 2
120 | De snag all trades test & commision |  | 2026-01-12 | 2026-01-13 | 2
120 | De snag all trades test & commision |  | 2026-01-19 | 2026-01-21 | 3
120 | De snag all trades test & commision |  | 2026-01-25 | 2026-03-03 | 27
120 | De snag all trades test & commision |  | 2026-03-06 | 2026-03-07 | 1
120 | De snag all trades test & commision |  | 2026-03-13 | 2026-03-14 | 1
120 | De snag all trades test & commision |  | 2026-03-20 | 2026-03-21 | 1
120 | De snag all trades test & commision |  | 2026-03-27 | 2026-03-28 | 1
120 | De snag all trades test & commision |  | 2026-04-04 | 2026-04-05 | 1
120 | De snag all trades test & commision |  | 2026-04-11 | 2026-04-12 | 1
120 | De snag all trades test & commision |  | 2026-04-18 | 2026-04-19 | 1
120 | De snag all trades test & commision |  | 2026-04-25 | 2026-04-26 | 1
120 | De snag all trades test & commision |  | 2026-05-01 | 2026-05-09 | 6
120 | De snag all trades test & commision |  | 2026-05-15 | 2026-05-16 | 1
120 | De snag all trades test & commision |  | 2026-05-22 | 2026-05-23 | 1
120 | De snag all trades test & commision |  | 2026-05-29 | 2026-05-30 | 1
120 | De snag all trades test & commision |  | 2026-06-06 | 2026-06-07 | 1
120 | De snag all trades test & commision |  | 2026-06-13 | 2026-06-14 | 1
120 | De snag all trades test & commision |  | 2026-06-20 | 2026-06-21 | 1
121 | MCL |  | 2025-12-07 | 2025-12-08 | 1
121 | MCL |  | 2025-12-14 | 2025-12-15 | 1
121 | MCL |  | 2025-12-21 | 2025-12-22 | 1
121 | MCL |  | 2025-12-28 | 2025-12-29 | 1
121 | MCL |  | 2026-01-05 | 2026-01-06 | 2
121 | MCL |  | 2026-01-12 | 2026-01-13 | 2
121 | MCL |  | 2026-01-19 | 2026-01-21 | 3
121 | MCL |  | 2026-01-25 | 2026-03-03 | 27
121 | MCL |  | 2026-03-06 | 2026-03-07 | 1
121 | MCL |  | 2026-03-13 | 2026-03-14 | 1
121 | MCL |  | 2026-03-20 | 2026-03-21 | 1
121 | MCL |  | 2026-03-27 | 2026-03-28 | 1
121 | MCL |  | 2026-04-04 | 2026-04-05 | 1
121 | MCL |  | 2026-04-11 | 2026-04-12 | 1
121 | MCL |  | 2026-04-18 | 2026-04-19 | 1
121 | MCL |  | 2026-04-25 | 2026-04-26 | 1
121 | MCL |  | 2026-05-01 | 2026-05-02 | 1
121 | MCL |  | 2026-05-08 | 2026-05-16 | 6
121 | MCL |  | 2026-05-22 | 2026-05-23 | 1
121 | MCL |  | 2026-05-29 | 2026-05-30 | 1
121 | MCL |  | 2026-06-06 | 2026-06-07 | 1
121 | MCL |  | 2026-06-13 | 2026-06-14 | 1
121 | MCL |  | 2026-06-20 | 2026-06-21 | 1
122 | ARMSTRONG |  | 2025-12-07 | 2025-12-08 | 1
122 | ARMSTRONG |  | 2025-12-14 | 2025-12-15 | 1
122 | ARMSTRONG |  | 2025-12-21 | 2025-12-22 | 1
122 | ARMSTRONG |  | 2025-12-28 | 2025-12-29 | 1
122 | ARMSTRONG |  | 2026-01-05 | 2026-01-06 | 2
122 | ARMSTRONG |  | 2026-01-12 | 2026-01-21 | 8
122 | ARMSTRONG |  | 2026-01-25 | 2026-03-03 | 27
122 | ARMSTRONG |  | 2026-03-06 | 2026-03-07 | 1
122 | ARMSTRONG |  | 2026-03-13 | 2026-03-14 | 1
122 | ARMSTRONG |  | 2026-03-20 | 2026-03-21 | 1
122 | ARMSTRONG |  | 2026-03-27 | 2026-03-28 | 1
122 | ARMSTRONG |  | 2026-04-04 | 2026-04-05 | 1
122 | ARMSTRONG |  | 2026-04-11 | 2026-04-12 | 1
122 | ARMSTRONG |  | 2026-04-18 | 2026-04-19 | 1
122 | ARMSTRONG |  | 2026-04-25 | 2026-04-26 | 1
122 | ARMSTRONG |  | 2026-05-01 | 2026-05-02 | 1
122 | ARMSTRONG |  | 2026-05-08 | 2026-05-09 | 1
122 | ARMSTRONG |  | 2026-05-15 | 2026-05-18 | 2
122 | ARMSTRONG |  | 2026-05-22 | 2026-05-23 | 1
122 | ARMSTRONG |  | 2026-05-29 | 2026-05-30 | 1
122 | ARMSTRONG |  | 2026-06-06 | 2026-06-07 | 1
122 | ARMSTRONG |  | 2026-06-13 | 2026-06-14 | 1
122 | ARMSTRONG |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2025-12-07 | 2025-12-08 | 1
| Handover to client |  | 2025-12-14 | 2025-12-15 | 1
| Handover to client |  | 2025-12-21 | 2025-12-22 | 1
| Handover to client |  | 2025-12-28 | 2025-12-29 | 1
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-12 | 2026-01-21 | 8
| Handover to client |  | 2026-01-25 | 2026-03-03 | 27
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-06-01 | 2
| Handover to client |  | 2026-06-06 | 2026-06-07 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
| Level 5Apartment fit out -cluster 2 |  | 2025-12-07 | 2025-12-08 | 1
| Level 5Apartment fit out -cluster 2 |  | 2025-12-14 | 2025-12-15 | 1
| Level 5Apartment fit out -cluster 2 |  | 2025-12-21 | 2025-12-22 | 1
| Level 5Apartment fit out -cluster 2 |  | 2025-12-28 | 2025-12-29 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-01-05 | 2026-01-06 | 2
| Level 5Apartment fit out -cluster 2 |  | 2026-01-12 | 2026-01-13 | 2
| Level 5Apartment fit out -cluster 2 |  | 2026-01-15 | 2026-01-21 | 5
| Level 5Apartment fit out -cluster 2 |  | 2026-01-25 | 2026-03-03 | 27
| Level 5Apartment fit out -cluster 2 |  | 2026-03-06 | 2026-03-07 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-03-13 | 2026-03-14 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-03-20 | 2026-03-21 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-03-27 | 2026-03-28 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-04-04 | 2026-04-05 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-04-11 | 2026-04-12 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-04-18 | 2026-04-19 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-04-25 | 2026-04-26 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-05-01 | 2026-05-02 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-05-08 | 2026-05-09 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-05-15 | 2026-05-16 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-05-22 | 2026-05-23 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-05-29 | 2026-05-30 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-06-06 | 2026-06-07 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-06-13 | 2026-06-14 | 1
| Level 5Apartment fit out -cluster 2 |  | 2026-06-20 | 2026-06-21 | 1
| CONTROL POINT 2 (CP2) |  | 2025-12-07 | 2025-12-09 | 2
| CONTROL POINT 2 (CP2) |  | 2025-12-14 | 2025-12-15 | 1
| CONTROL POINT 2 (CP2) |  | 2025-12-21 | 2025-12-22 | 1
| CONTROL POINT 2 (CP2) |  | 2025-12-24 | 2025-12-26 | 3
| CONTROL POINT 2 (CP2) |  | 2025-12-28 | 2025-12-29 | 1
| CONTROL POINT 2 (CP2) |  | 2026-01-05 | 2026-01-06 | 2
| CONTROL POINT 2 (CP2) |  | 2026-01-11 | 2026-01-13 | 2
| CONTROL POINT 2 (CP2) |  | 2026-01-19 | 2026-01-21 | 3
| CONTROL POINT 2 (CP2) |  | 2026-01-25 | 2026-03-03 | 27
| CONTROL POINT 2 (CP2) |  | 2026-03-06 | 2026-03-07 | 1
| CONTROL POINT 2 (CP2) |  | 2026-03-13 | 2026-03-14 | 1
| CONTROL POINT 2 (CP2) |  | 2026-03-20 | 2026-03-21 | 1
| CONTROL POINT 2 (CP2) |  | 2026-03-27 | 2026-03-28 | 1
| CONTROL POINT 2 (CP2) |  | 2026-04-04 | 2026-04-05 | 1
| CONTROL POINT 2 (CP2) |  | 2026-04-11 | 2026-04-12 | 1
| CONTROL POINT 2 (CP2) |  | 2026-04-18 | 2026-04-19 | 1
| CONTROL POINT 2 (CP2) |  | 2026-04-25 | 2026-04-26 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-01 | 2026-05-02 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-08 | 2026-05-09 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-15 | 2026-05-16 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-22 | 2026-05-23 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-29 | 2026-05-30 | 1
| CONTROL POINT 2 (CP2) |  | 2026-06-06 | 2026-06-07 | 1
| CONTROL POINT 2 (CP2) |  | 2026-06-13 | 2026-06-14 | 1
| CONTROL POINT 2 (CP2) |  | 2026-06-20 | 2026-06-21 | 1
128 | MCL |  | 2025-12-07 | 2025-12-11 | 4
128 | MCL |  | 2025-12-13 | 2025-12-16 | 2
128 | MCL |  | 2025-12-19 | 2025-12-24 | 4
128 | MCL |  | 2025-12-26 | 2025-12-29 | 2
128 | MCL |  | 2026-01-05 | 2026-01-06 | 2
128 | MCL |  | 2026-01-11 | 2026-01-13 | 2
128 | MCL |  | 2026-01-19 | 2026-01-21 | 3
128 | MCL |  | 2026-01-25 | 2026-03-03 | 27
128 | MCL |  | 2026-03-06 | 2026-03-07 | 1
128 | MCL |  | 2026-03-13 | 2026-03-14 | 1
128 | MCL |  | 2026-03-20 | 2026-03-21 | 1
128 | MCL |  | 2026-03-27 | 2026-03-28 | 1
128 | MCL |  | 2026-04-04 | 2026-04-05 | 1
128 | MCL |  | 2026-04-11 | 2026-04-12 | 1
128 | MCL |  | 2026-04-18 | 2026-04-19 | 1
128 | MCL |  | 2026-04-25 | 2026-04-26 | 1
128 | MCL |  | 2026-05-01 | 2026-05-02 | 1
128 | MCL |  | 2026-05-08 | 2026-05-09 | 1
128 | MCL |  | 2026-05-15 | 2026-05-16 | 1
128 | MCL |  | 2026-05-22 | 2026-05-23 | 1
128 | MCL |  | 2026-05-29 | 2026-05-30 | 1
128 | MCL |  | 2026-06-06 | 2026-06-07 | 1
128 | MCL |  | 2026-06-13 | 2026-06-14 | 1
128 | MCL |  | 2026-06-20 | 2026-06-21 | 1
| 2nd fix Partitions - insulation and board |  | 2025-12-07 | 2025-12-11 | 4
| 2nd fix Partitions - insulation and board |  | 2025-12-13 | 2025-12-16 | 2
| 2nd fix Partitions - insulation and board |  | 2025-12-19 | 2025-12-24 | 4
| 2nd fix Partitions - insulation and board |  | 2025-12-26 | 2025-12-29 | 2
| 2nd fix Partitions - insulation and board |  | 2026-01-05 | 2026-01-06 | 2
| 2nd fix Partitions - insulation and board |  | 2026-01-11 | 2026-01-13 | 2
| 2nd fix Partitions - insulation and board |  | 2026-01-19 | 2026-01-21 | 3
| 2nd fix Partitions - insulation and board |  | 2026-01-25 | 2026-03-03 | 27
| 2nd fix Partitions - insulation and board |  | 2026-03-06 | 2026-03-07 | 1
| 2nd fix Partitions - insulation and board |  | 2026-03-13 | 2026-03-14 | 1
| 2nd fix Partitions - insulation and board |  | 2026-03-20 | 2026-03-21 | 1
| 2nd fix Partitions - insulation and board |  | 2026-03-27 | 2026-03-28 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-04 | 2026-04-05 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-11 | 2026-04-12 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-18 | 2026-04-19 | 1
| 2nd fix Partitions - insulation and board |  | 2026-04-25 | 2026-04-26 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-01 | 2026-05-02 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-08 | 2026-05-09 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-15 | 2026-05-16 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-22 | 2026-05-23 | 1
| 2nd fix Partitions - insulation and board |  | 2026-05-29 | 2026-05-30 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-06 | 2026-06-07 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-13 | 2026-06-14 | 1
| 2nd fix Partitions - insulation and board |  | 2026-06-20 | 2026-06-21 | 1
| Install Vents/ducts |  | 2025-12-07 | 2025-12-11 | 4
| Install Vents/ducts |  | 2025-12-13 | 2025-12-16 | 2
| Install Vents/ducts |  | 2025-12-19 | 2025-12-24 | 4
| Install Vents/ducts |  | 2025-12-26 | 2025-12-29 | 2
| Install Vents/ducts |  | 2026-01-05 | 2026-01-06 | 2
| Install Vents/ducts |  | 2026-01-11 | 2026-01-13 | 2
| Install Vents/ducts |  | 2026-01-19 | 2026-01-21 | 3
| Install Vents/ducts |  | 2026-01-25 | 2026-03-03 | 27
| Install Vents/ducts |  | 2026-03-06 | 2026-03-07 | 1
| Install Vents/ducts |  | 2026-03-13 | 2026-03-14 | 1
| Install Vents/ducts |  | 2026-03-20 | 2026-03-21 | 1
| Install Vents/ducts |  | 2026-03-27 | 2026-03-28 | 1
| Install Vents/ducts |  | 2026-04-04 | 2026-04-05 | 1
| Install Vents/ducts |  | 2026-04-11 | 2026-04-12 | 1
| Install Vents/ducts |  | 2026-04-18 | 2026-04-19 | 1
| Install Vents/ducts |  | 2026-04-25 | 2026-04-26 | 1
| Install Vents/ducts |  | 2026-05-01 | 2026-05-02 | 1
| Install Vents/ducts |  | 2026-05-08 | 2026-05-09 | 1
| Install Vents/ducts |  | 2026-05-15 | 2026-05-16 | 1
| Install Vents/ducts |  | 2026-05-22 | 2026-05-23 | 1
| Install Vents/ducts |  | 2026-05-29 | 2026-05-30 | 1
| Install Vents/ducts |  | 2026-06-06 | 2026-06-07 | 1
| Install Vents/ducts |  | 2026-06-13 | 2026-06-14 | 1
| Install Vents/ducts |  | 2026-06-20 | 2026-06-21 | 1
| CONTROL POINT 3 (CP3) |  | 2025-12-07 | 2025-12-11 | 4
| CONTROL POINT 3 (CP3) |  | 2025-12-13 | 2025-12-16 | 2
| CONTROL POINT 3 (CP3) |  | 2025-12-19 | 2025-12-24 | 4
| CONTROL POINT 3 (CP3) |  | 2025-12-26 | 2025-12-29 | 2
| CONTROL POINT 3 (CP3) |  | 2026-01-05 | 2026-01-06 | 2
| CONTROL POINT 3 (CP3) |  | 2026-01-11 | 2026-01-13 | 2
| CONTROL POINT 3 (CP3) |  | 2026-01-19 | 2026-01-21 | 3
| CONTROL POINT 3 (CP3) |  | 2026-01-25 | 2026-03-03 | 27
| CONTROL POINT 3 (CP3) |  | 2026-03-06 | 2026-03-07 | 1
| CONTROL POINT 3 (CP3) |  | 2026-03-13 | 2026-03-14 | 1
| CONTROL POINT 3 (CP3) |  | 2026-03-20 | 2026-03-21 | 1
| CONTROL POINT 3 (CP3) |  | 2026-03-27 | 2026-03-28 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-04 | 2026-04-05 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-11 | 2026-04-12 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-18 | 2026-04-19 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-25 | 2026-04-26 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-01 | 2026-05-02 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-08 | 2026-05-09 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-15 | 2026-05-16 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-22 | 2026-05-23 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-29 | 2026-05-30 | 1
| CONTROL POINT 3 (CP3) |  | 2026-06-06 | 2026-06-07 | 1
| CONTROL POINT 3 (CP3) |  | 2026-06-13 | 2026-06-14 | 1
| CONTROL POINT 3 (CP3) |  | 2026-06-20 | 2026-06-21 | 1
129 | Ceiling void closure checklist sign off |  | 2025-12-07 | 2025-12-09 | 2
129 | Ceiling void closure checklist sign off |  | 2025-12-13 | 2025-12-16 | 2
129 | Ceiling void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
129 | Ceiling void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
129 | Ceiling void closure checklist sign off |  | 2026-01-05 | 2026-01-06 | 2
129 | Ceiling void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
129 | Ceiling void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
129 | Ceiling void closure checklist sign off |  | 2026-01-25 | 2026-03-03 | 27
129 | Ceiling void closure checklist sign off |  | 2026-03-06 | 2026-03-07 | 1
129 | Ceiling void closure checklist sign off |  | 2026-03-13 | 2026-03-14 | 1
129 | Ceiling void closure checklist sign off |  | 2026-03-20 | 2026-03-21 | 1
129 | Ceiling void closure checklist sign off |  | 2026-03-27 | 2026-03-28 | 1
129 | Ceiling void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
129 | Ceiling void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
129 | Ceiling void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
129 | Ceiling void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
129 | Ceiling void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
129 | Ceiling void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
129 | Ceiling void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
129 | Ceiling void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
129 | Ceiling void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
129 | Ceiling void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
129 | Ceiling void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
129 | Ceiling void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
130 | PANACEA |  | 2025-12-07 | 2025-12-16 | 7
130 | PANACEA |  | 2025-12-19 | 2025-12-24 | 4
130 | PANACEA |  | 2025-12-26 | 2025-12-29 | 2
130 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
130 | PANACEA |  | 2026-01-11 | 2026-01-13 | 2
130 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
130 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
130 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
130 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
130 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
130 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
130 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
130 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
130 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
130 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
130 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
130 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
130 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
130 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
130 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
130 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
130 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
130 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
131 | CARA |  | 2025-12-07 | 2025-12-09 | 2
131 | CARA |  | 2025-12-13 | 2025-12-16 | 2
131 | CARA |  | 2025-12-19 | 2025-12-24 | 4
131 | CARA |  | 2025-12-26 | 2025-12-29 | 2
131 | CARA |  | 2026-01-05 | 2026-01-06 | 2
131 | CARA |  | 2026-01-11 | 2026-01-13 | 2
131 | CARA |  | 2026-01-19 | 2026-01-21 | 3
131 | CARA |  | 2026-01-25 | 2026-03-03 | 27
131 | CARA |  | 2026-03-06 | 2026-03-07 | 1
131 | CARA |  | 2026-03-13 | 2026-03-14 | 1
131 | CARA |  | 2026-03-20 | 2026-03-21 | 1
131 | CARA |  | 2026-03-27 | 2026-03-28 | 1
131 | CARA |  | 2026-04-04 | 2026-04-05 | 1
131 | CARA |  | 2026-04-11 | 2026-04-12 | 1
131 | CARA |  | 2026-04-18 | 2026-04-19 | 1
131 | CARA |  | 2026-04-25 | 2026-04-26 | 1
131 | CARA |  | 2026-05-01 | 2026-05-02 | 1
131 | CARA |  | 2026-05-08 | 2026-05-09 | 1
131 | CARA |  | 2026-05-15 | 2026-05-16 | 1
131 | CARA |  | 2026-05-22 | 2026-05-23 | 1
131 | CARA |  | 2026-05-29 | 2026-05-30 | 1
131 | CARA |  | 2026-06-06 | 2026-06-07 | 1
131 | CARA |  | 2026-06-13 | 2026-06-14 | 1
131 | CARA |  | 2026-06-20 | 2026-06-21 | 1
132 | Ceilings - board (cut holes for lights) |  | 2025-12-07 | 2025-12-09 | 2
132 | Ceilings - board (cut holes for lights) |  | 2025-12-13 | 2025-12-16 | 2
132 | Ceilings - board (cut holes for lights) |  | 2025-12-19 | 2025-12-24 | 4
132 | Ceilings - board (cut holes for lights) |  | 2025-12-26 | 2025-12-29 | 2
132 | Ceilings - board (cut holes for lights) |  | 2026-01-05 | 2026-01-06 | 2
132 | Ceilings - board (cut holes for lights) |  | 2026-01-11 | 2026-01-13 | 2
132 | Ceilings - board (cut holes for lights) |  | 2026-01-19 | 2026-01-21 | 3
132 | Ceilings - board (cut holes for lights) |  | 2026-01-25 | 2026-03-03 | 27
132 | Ceilings - board (cut holes for lights) |  | 2026-03-06 | 2026-03-07 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-03-13 | 2026-03-14 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-03-20 | 2026-03-21 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-03-27 | 2026-03-28 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-04-04 | 2026-04-05 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-04-11 | 2026-04-12 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-04-18 | 2026-04-19 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-04-25 | 2026-04-26 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-05-01 | 2026-05-02 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-05-08 | 2026-05-09 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-05-15 | 2026-05-16 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-05-22 | 2026-05-23 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-05-29 | 2026-05-30 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-06-06 | 2026-06-07 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-06-13 | 2026-06-14 | 1
132 | Ceilings - board (cut holes for lights) |  | 2026-06-20 | 2026-06-21 | 1
133 | GPL |  | 2025-12-07 | 2025-12-09 | 2
133 | GPL |  | 2025-12-13 | 2025-12-16 | 2
133 | GPL |  | 2025-12-19 | 2025-12-24 | 4
133 | GPL |  | 2025-12-26 | 2025-12-29 | 2
133 | GPL |  | 2026-01-02 | 2026-01-08 | 5
133 | GPL |  | 2026-01-11 | 2026-01-13 | 2
133 | GPL |  | 2026-01-19 | 2026-01-21 | 3
133 | GPL |  | 2026-01-25 | 2026-03-08 | 30
133 | GPL |  | 2026-03-13 | 2026-03-14 | 1
133 | GPL |  | 2026-03-20 | 2026-03-21 | 1
133 | GPL |  | 2026-03-27 | 2026-03-28 | 1
133 | GPL |  | 2026-04-04 | 2026-04-05 | 1
133 | GPL |  | 2026-04-11 | 2026-04-12 | 1
133 | GPL |  | 2026-04-18 | 2026-04-19 | 1
133 | GPL |  | 2026-04-25 | 2026-04-26 | 1
133 | GPL |  | 2026-05-01 | 2026-05-02 | 1
133 | GPL |  | 2026-05-08 | 2026-05-09 | 1
133 | GPL |  | 2026-05-15 | 2026-05-16 | 1
133 | GPL |  | 2026-05-22 | 2026-05-23 | 1
133 | GPL |  | 2026-05-29 | 2026-05-30 | 1
133 | GPL |  | 2026-06-06 | 2026-06-07 | 1
133 | GPL |  | 2026-06-13 | 2026-06-14 | 1
133 | GPL |  | 2026-06-20 | 2026-06-21 | 1
| Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-09 | 2
| Levveling screed /smoothing compound |  | 2025-12-13 | 2025-12-16 | 2
| Levveling screed /smoothing compound |  | 2025-12-19 | 2025-12-24 | 4
| Levveling screed /smoothing compound |  | 2025-12-26 | 2025-12-29 | 2
| Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-13 | 7
| Levveling screed /smoothing compound |  | 2026-01-19 | 2026-01-21 | 3
| Levveling screed /smoothing compound |  | 2026-01-25 | 2026-03-03 | 27
| Levveling screed /smoothing compound |  | 2026-03-06 | 2026-03-07 | 1
| Levveling screed /smoothing compound |  | 2026-03-09 | 2026-03-15 | 5
| Levveling screed /smoothing compound |  | 2026-03-20 | 2026-03-21 | 1
| Levveling screed /smoothing compound |  | 2026-03-27 | 2026-03-28 | 1
| Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
| Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
| Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
| Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
| Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
| Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
| Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
| Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
| Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
| Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
| Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
| Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
| Drying out |  | 2025-12-07 | 2025-12-09 | 2
| Drying out |  | 2025-12-13 | 2025-12-16 | 2
| Drying out |  | 2025-12-19 | 2025-12-24 | 4
| Drying out |  | 2025-12-26 | 2026-01-13 | 13
| Drying out |  | 2026-01-19 | 2026-01-21 | 3
| Drying out |  | 2026-01-25 | 2026-03-03 | 27
| Drying out |  | 2026-03-06 | 2026-03-07 | 1
| Drying out |  | 2026-03-13 | 2026-03-14 | 1
| Drying out |  | 2026-03-20 | 2026-03-21 | 1
| Drying out |  | 2026-03-27 | 2026-03-28 | 1
| Drying out |  | 2026-04-04 | 2026-04-05 | 1
| Drying out |  | 2026-04-11 | 2026-04-12 | 1
| Drying out |  | 2026-04-18 | 2026-04-19 | 1
| Drying out |  | 2026-04-25 | 2026-04-26 | 1
| Drying out |  | 2026-05-01 | 2026-05-02 | 1
| Drying out |  | 2026-05-08 | 2026-05-09 | 1
| Drying out |  | 2026-05-15 | 2026-05-16 | 1
| Drying out |  | 2026-05-22 | 2026-05-23 | 1
| Drying out |  | 2026-05-29 | 2026-05-30 | 1
| Drying out |  | 2026-06-06 | 2026-06-07 | 1
| Drying out |  | 2026-06-13 | 2026-06-14 | 1
| Drying out |  | 2026-06-20 | 2026-06-21 | 1
134 | PANACEA |  | 2025-12-07 | 2025-12-16 | 7
134 | PANACEA |  | 2025-12-19 | 2025-12-24 | 4
134 | PANACEA |  | 2025-12-26 | 2025-12-29 | 2
134 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
134 | PANACEA |  | 2026-01-11 | 2026-01-13 | 2
134 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
134 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
134 | PANACEA |  | 2026-03-06 | 2026-03-09 | 2
134 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
134 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
134 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
134 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
134 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
134 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
134 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
134 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
134 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
134 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
134 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
134 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
134 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
134 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
134 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-16 | 7
| Vanity 1st fix framing |  | 2025-12-19 | 2025-12-24 | 4
| Vanity 1st fix framing |  | 2025-12-26 | 2025-12-29 | 2
| Vanity 1st fix framing |  | 2026-01-05 | 2026-01-06 | 2
| Vanity 1st fix framing |  | 2026-01-11 | 2026-01-13 | 2
| Vanity 1st fix framing |  | 2026-01-19 | 2026-01-21 | 3
| Vanity 1st fix framing |  | 2026-01-25 | 2026-03-07 | 30
| Vanity 1st fix framing |  | 2026-03-12 | 2026-03-15 | 2
| Vanity 1st fix framing |  | 2026-03-20 | 2026-03-21 | 1
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
135 | CARA |  | 2025-12-07 | 2025-12-16 | 7
135 | CARA |  | 2025-12-19 | 2025-12-24 | 4
135 | CARA |  | 2025-12-26 | 2025-12-29 | 2
135 | CARA |  | 2026-01-05 | 2026-01-06 | 2
135 | CARA |  | 2026-01-11 | 2026-01-13 | 2
135 | CARA |  | 2026-01-19 | 2026-01-21 | 3
135 | CARA |  | 2026-01-25 | 2026-03-03 | 27
135 | CARA |  | 2026-03-06 | 2026-03-07 | 1
135 | CARA |  | 2026-03-13 | 2026-03-14 | 1
135 | CARA |  | 2026-03-20 | 2026-03-21 | 1
135 | CARA |  | 2026-03-27 | 2026-04-05 | 6
135 | CARA |  | 2026-04-11 | 2026-04-12 | 1
135 | CARA |  | 2026-04-18 | 2026-04-19 | 1
135 | CARA |  | 2026-04-25 | 2026-04-26 | 1
135 | CARA |  | 2026-05-01 | 2026-05-02 | 1
135 | CARA |  | 2026-05-08 | 2026-05-09 | 1
135 | CARA |  | 2026-05-15 | 2026-05-16 | 1
135 | CARA |  | 2026-05-22 | 2026-05-23 | 1
135 | CARA |  | 2026-05-29 | 2026-05-30 | 1
135 | CARA |  | 2026-06-06 | 2026-06-07 | 1
135 | CARA |  | 2026-06-13 | 2026-06-14 | 1
135 | CARA |  | 2026-06-20 | 2026-06-21 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-07 | 2025-12-16 | 7
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-19 | 2025-12-24 | 4
| Plumbing mid fix ,bath ,showers cisterns |  | 2025-12-26 | 2025-12-29 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-05 | 2026-01-06 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-11 | 2026-01-13 | 2
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-19 | 2026-01-21 | 3
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-01-25 | 2026-03-03 | 27
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-06 | 2026-03-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-13 | 2026-03-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-17 | 2026-03-23 | 5
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-03-27 | 2026-03-28 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-04 | 2026-04-05 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-11 | 2026-04-12 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-18 | 2026-04-19 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-04-25 | 2026-04-26 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-01 | 2026-05-02 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-08 | 2026-05-09 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-15 | 2026-05-16 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-22 | 2026-05-23 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-05-29 | 2026-05-30 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-06 | 2026-06-07 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-13 | 2026-06-14 | 1
| Plumbing mid fix ,bath ,showers cisterns |  | 2026-06-20 | 2026-06-21 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2025-12-07 | 2025-12-16 | 7
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2025-12-19 | 2025-12-24 | 4
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2025-12-26 | 2025-12-29 | 2
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-01-05 | 2026-01-06 | 2
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-01-11 | 2026-01-13 | 2
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-01-19 | 2026-01-21 | 3
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-01-25 | 2026-03-03 | 27
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-03-06 | 2026-03-07 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-03-13 | 2026-03-14 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-03-20 | 2026-03-21 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-03-25 | 2026-04-02 | 7
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-04-04 | 2026-04-05 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-04-11 | 2026-04-12 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-04-18 | 2026-04-19 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-04-25 | 2026-04-26 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-05-01 | 2026-05-02 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-05-08 | 2026-05-09 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-05-15 | 2026-05-16 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-05-22 | 2026-05-23 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-05-29 | 2026-05-30 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-06-06 | 2026-06-07 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-06-13 | 2026-06-14 | 1
136 | Joinery 1st fix -doors, frames ,skirtings,archs & plinths . |  | 2026-06-20 | 2026-06-21 | 1
137 | RED |  | 2025-12-07 | 2025-12-16 | 7
137 | RED |  | 2025-12-19 | 2025-12-24 | 4
137 | RED |  | 2025-12-26 | 2025-12-29 | 2
137 | RED |  | 2026-01-05 | 2026-01-21 | 13
137 | RED |  | 2026-01-25 | 2026-03-03 | 27
137 | RED |  | 2026-03-06 | 2026-03-07 | 1
137 | RED |  | 2026-03-13 | 2026-03-14 | 1
137 | RED |  | 2026-03-20 | 2026-03-28 | 6
137 | RED |  | 2026-04-04 | 2026-04-05 | 1
137 | RED |  | 2026-04-11 | 2026-04-12 | 1
137 | RED |  | 2026-04-18 | 2026-04-19 | 1
137 | RED |  | 2026-04-25 | 2026-04-26 | 1
137 | RED |  | 2026-05-01 | 2026-05-02 | 1
137 | RED |  | 2026-05-08 | 2026-05-09 | 1
137 | RED |  | 2026-05-15 | 2026-05-16 | 1
137 | RED |  | 2026-05-22 | 2026-05-23 | 1
137 | RED |  | 2026-05-29 | 2026-05-30 | 1
137 | RED |  | 2026-06-06 | 2026-06-07 | 1
137 | RED |  | 2026-06-13 | 2026-06-14 | 1
137 | RED |  | 2026-06-20 | 2026-06-21 | 1
138 | PANACEA |  | 2025-12-07 | 2025-12-24 | 13
138 | PANACEA |  | 2025-12-26 | 2025-12-29 | 2
138 | PANACEA |  | 2026-01-05 | 2026-01-13 | 7
138 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
138 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
138 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
138 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
138 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
138 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
138 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
138 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
138 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
138 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
138 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
138 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
138 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
138 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
138 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
138 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
138 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
138 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
139 | PANACEA |  | 2025-12-07 | 2025-12-11 | 4
139 | PANACEA |  | 2025-12-13 | 2025-12-24 | 8
139 | PANACEA |  | 2025-12-26 | 2025-12-29 | 2
139 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
139 | PANACEA |  | 2026-01-11 | 2026-01-13 | 2
139 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
139 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
139 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
139 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
139 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
139 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
139 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
139 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
139 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
139 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
139 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
139 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
139 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
139 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
139 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
139 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
139 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
139 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
140 | service cupboard decoration |  | 2025-12-07 | 2025-12-11 | 4
140 | service cupboard decoration |  | 2025-12-13 | 2025-12-22 | 6
140 | service cupboard decoration |  | 2025-12-28 | 2025-12-29 | 1
140 | service cupboard decoration |  | 2026-01-05 | 2026-01-06 | 2
140 | service cupboard decoration |  | 2026-01-12 | 2026-01-13 | 2
140 | service cupboard decoration |  | 2026-01-17 | 2026-03-03 | 32
140 | service cupboard decoration |  | 2026-03-06 | 2026-03-07 | 1
140 | service cupboard decoration |  | 2026-03-13 | 2026-03-14 | 1
140 | service cupboard decoration |  | 2026-03-20 | 2026-03-21 | 1
140 | service cupboard decoration |  | 2026-03-27 | 2026-03-28 | 1
140 | service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
140 | service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
140 | service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
140 | service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
140 | service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
140 | service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
140 | service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
140 | service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
140 | service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
140 | service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
140 | service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
140 | service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
141 | step on safety |  | 2025-12-07 | 2025-12-11 | 4
141 | step on safety |  | 2025-12-13 | 2025-12-22 | 6
141 | step on safety |  | 2025-12-28 | 2025-12-29 | 1
141 | step on safety |  | 2026-01-05 | 2026-01-06 | 2
141 | step on safety |  | 2026-01-12 | 2026-01-13 | 2
141 | step on safety |  | 2026-01-19 | 2026-01-20 | 2
141 | step on safety |  | 2026-01-23 | 2026-03-03 | 28
141 | step on safety |  | 2026-03-06 | 2026-03-07 | 1
141 | step on safety |  | 2026-03-13 | 2026-03-14 | 1
141 | step on safety |  | 2026-03-20 | 2026-03-21 | 1
141 | step on safety |  | 2026-03-27 | 2026-03-28 | 1
141 | step on safety |  | 2026-04-04 | 2026-04-05 | 1
141 | step on safety |  | 2026-04-11 | 2026-04-12 | 1
141 | step on safety |  | 2026-04-18 | 2026-04-19 | 1
141 | step on safety |  | 2026-04-25 | 2026-04-26 | 1
141 | step on safety |  | 2026-05-01 | 2026-05-02 | 1
141 | step on safety |  | 2026-05-08 | 2026-05-09 | 1
141 | step on safety |  | 2026-05-15 | 2026-05-16 | 1
141 | step on safety |  | 2026-05-22 | 2026-05-23 | 1
141 | step on safety |  | 2026-05-29 | 2026-05-30 | 1
141 | step on safety |  | 2026-06-06 | 2026-06-07 | 1
141 | step on safety |  | 2026-06-13 | 2026-06-14 | 1
141 | step on safety |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-11 | 4
| Amtico flooring /Bathrooms |  | 2025-12-13 | 2025-12-22 | 6
| Amtico flooring /Bathrooms |  | 2025-12-28 | 2025-12-29 | 1
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-12 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-20 | 2
| Amtico flooring /Bathrooms |  | 2026-01-23 | 2026-03-03 | 28
| Amtico flooring /Bathrooms |  | 2026-03-06 | 2026-03-07 | 1
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-12 | 5
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
142 | PANACEA |  | 2025-12-07 | 2025-12-11 | 4
142 | PANACEA |  | 2025-12-13 | 2025-12-22 | 6
142 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
142 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
142 | PANACEA |  | 2026-01-12 | 2026-01-13 | 2
142 | PANACEA |  | 2026-01-19 | 2026-01-20 | 2
142 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
142 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
142 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
142 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
142 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
142 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
142 | PANACEA |  | 2026-04-11 | 2026-04-19 | 5
142 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
142 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
142 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
142 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
142 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
142 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
142 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
142 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
142 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
143 | Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-11 | 4
143 | Electrical 2nd fix & live testing |  | 2025-12-13 | 2025-12-22 | 6
143 | Electrical 2nd fix & live testing |  | 2025-12-28 | 2025-12-29 | 1
143 | Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-06 | 2
143 | Electrical 2nd fix & live testing |  | 2026-01-12 | 2026-01-13 | 2
143 | Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
143 | Electrical 2nd fix & live testing |  | 2026-01-25 | 2026-03-03 | 27
143 | Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
143 | Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
143 | Electrical 2nd fix & live testing |  | 2026-03-20 | 2026-03-21 | 1
143 | Electrical 2nd fix & live testing |  | 2026-03-27 | 2026-03-28 | 1
143 | Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
143 | Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
143 | Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-26 | 5
143 | Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
143 | Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
143 | Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
143 | Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
143 | Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
143 | Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
143 | Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
143 | Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
144 | Builders clean |  | 2025-12-07 | 2025-12-11 | 4
144 | Builders clean |  | 2025-12-13 | 2025-12-15 | 1
144 | Builders clean |  | 2025-12-17 | 2025-12-22 | 4
144 | Builders clean |  | 2025-12-28 | 2025-12-29 | 1
144 | Builders clean |  | 2026-01-05 | 2026-01-06 | 2
144 | Builders clean |  | 2026-01-12 | 2026-01-13 | 2
144 | Builders clean |  | 2026-01-19 | 2026-01-21 | 3
144 | Builders clean |  | 2026-01-25 | 2026-03-03 | 27
144 | Builders clean |  | 2026-03-06 | 2026-03-07 | 1
144 | Builders clean |  | 2026-03-13 | 2026-03-14 | 1
144 | Builders clean |  | 2026-03-20 | 2026-03-21 | 1
144 | Builders clean |  | 2026-03-27 | 2026-03-28 | 1
144 | Builders clean |  | 2026-04-04 | 2026-04-05 | 1
144 | Builders clean |  | 2026-04-11 | 2026-04-12 | 1
144 | Builders clean |  | 2026-04-18 | 2026-04-19 | 1
144 | Builders clean |  | 2026-04-25 | 2026-04-26 | 1
144 | Builders clean |  | 2026-05-01 | 2026-05-02 | 1
144 | Builders clean |  | 2026-05-08 | 2026-05-09 | 1
144 | Builders clean |  | 2026-05-15 | 2026-05-16 | 1
144 | Builders clean |  | 2026-05-22 | 2026-05-23 | 1
144 | Builders clean |  | 2026-05-29 | 2026-05-30 | 1
144 | Builders clean |  | 2026-06-06 | 2026-06-07 | 1
144 | Builders clean |  | 2026-06-13 | 2026-06-14 | 1
144 | Builders clean |  | 2026-06-20 | 2026-06-21 | 1
145 | RED |  | 2025-12-07 | 2025-12-11 | 4
145 | RED |  | 2025-12-13 | 2025-12-15 | 1
145 | RED |  | 2025-12-17 | 2025-12-25 | 7
145 | RED |  | 2025-12-28 | 2025-12-29 | 1
145 | RED |  | 2026-01-05 | 2026-01-13 | 7
145 | RED |  | 2026-01-19 | 2026-01-21 | 3
145 | RED |  | 2026-01-25 | 2026-03-03 | 27
145 | RED |  | 2026-03-06 | 2026-03-07 | 1
145 | RED |  | 2026-03-13 | 2026-03-14 | 1
145 | RED |  | 2026-03-20 | 2026-03-21 | 1
145 | RED |  | 2026-03-27 | 2026-03-28 | 1
145 | RED |  | 2026-04-04 | 2026-04-05 | 1
145 | RED |  | 2026-04-11 | 2026-04-12 | 1
145 | RED |  | 2026-04-18 | 2026-04-19 | 1
145 | RED |  | 2026-04-25 | 2026-04-26 | 1
145 | RED |  | 2026-05-01 | 2026-05-02 | 1
145 | RED |  | 2026-05-08 | 2026-05-09 | 1
145 | RED |  | 2026-05-15 | 2026-05-16 | 1
145 | RED |  | 2026-05-22 | 2026-05-23 | 1
145 | RED |  | 2026-05-29 | 2026-05-30 | 1
145 | RED |  | 2026-06-06 | 2026-06-07 | 1
145 | RED |  | 2026-06-13 | 2026-06-14 | 1
145 | RED |  | 2026-06-20 | 2026-06-21 | 1
146 | PANACEA |  | 2025-12-07 | 2025-12-11 | 4
146 | PANACEA |  | 2025-12-13 | 2025-12-15 | 1
146 | PANACEA |  | 2025-12-17 | 2025-12-23 | 5
146 | PANACEA |  | 2025-12-28 | 2025-12-29 | 1
146 | PANACEA |  | 2026-01-05 | 2026-01-13 | 7
146 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
146 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
146 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
146 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
146 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
146 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
146 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
146 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
146 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
146 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
146 | PANACEA |  | 2026-04-29 | 2026-05-04 | 4
146 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
146 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
146 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
146 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
146 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
146 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
146 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
147 | CARA |  | 2025-12-07 | 2025-12-11 | 4
147 | CARA |  | 2025-12-13 | 2025-12-15 | 1
147 | CARA |  | 2025-12-19 | 2025-12-25 | 5
147 | CARA |  | 2025-12-27 | 2025-12-30 | 2
147 | CARA |  | 2026-01-03 | 2026-01-13 | 7
147 | CARA |  | 2026-01-19 | 2026-01-21 | 3
147 | CARA |  | 2026-01-25 | 2026-03-03 | 27
147 | CARA |  | 2026-03-06 | 2026-03-07 | 1
147 | CARA |  | 2026-03-13 | 2026-03-14 | 1
147 | CARA |  | 2026-03-20 | 2026-03-21 | 1
147 | CARA |  | 2026-03-27 | 2026-03-28 | 1
147 | CARA |  | 2026-04-04 | 2026-04-05 | 1
147 | CARA |  | 2026-04-11 | 2026-04-12 | 1
147 | CARA |  | 2026-04-18 | 2026-04-19 | 1
147 | CARA |  | 2026-04-25 | 2026-04-26 | 1
147 | CARA |  | 2026-05-01 | 2026-05-02 | 1
147 | CARA |  | 2026-05-05 | 2026-05-09 | 4
147 | CARA |  | 2026-05-15 | 2026-05-16 | 1
147 | CARA |  | 2026-05-22 | 2026-05-23 | 1
147 | CARA |  | 2026-05-29 | 2026-05-30 | 1
147 | CARA |  | 2026-06-06 | 2026-06-07 | 1
147 | CARA |  | 2026-06-13 | 2026-06-14 | 1
147 | CARA |  | 2026-06-20 | 2026-06-21 | 1
| De snag all trades test & commision |  | 2025-12-07 | 2025-12-11 | 4
| De snag all trades test & commision |  | 2025-12-13 | 2025-12-15 | 1
| De snag all trades test & commision |  | 2025-12-19 | 2025-12-25 | 5
| De snag all trades test & commision |  | 2025-12-27 | 2025-12-30 | 2
| De snag all trades test & commision |  | 2026-01-03 | 2026-01-13 | 7
| De snag all trades test & commision |  | 2026-01-19 | 2026-01-21 | 3
| De snag all trades test & commision |  | 2026-01-25 | 2026-03-03 | 27
| De snag all trades test & commision |  | 2026-03-06 | 2026-03-07 | 1
| De snag all trades test & commision |  | 2026-03-13 | 2026-03-14 | 1
| De snag all trades test & commision |  | 2026-03-20 | 2026-03-21 | 1
| De snag all trades test & commision |  | 2026-03-27 | 2026-03-28 | 1
| De snag all trades test & commision |  | 2026-04-04 | 2026-04-05 | 1
| De snag all trades test & commision |  | 2026-04-11 | 2026-04-12 | 1
| De snag all trades test & commision |  | 2026-04-18 | 2026-04-19 | 1
| De snag all trades test & commision |  | 2026-04-25 | 2026-04-26 | 1
| De snag all trades test & commision |  | 2026-05-01 | 2026-05-02 | 1
| De snag all trades test & commision |  | 2026-05-08 | 2026-05-16 | 6
| De snag all trades test & commision |  | 2026-05-22 | 2026-05-23 | 1
| De snag all trades test & commision |  | 2026-05-29 | 2026-05-30 | 1
| De snag all trades test & commision |  | 2026-06-06 | 2026-06-07 | 1
| De snag all trades test & commision |  | 2026-06-13 | 2026-06-14 | 1
| De snag all trades test & commision |  | 2026-06-20 | 2026-06-21 | 1
148 | Sparkle clean |  | 2025-12-07 | 2025-12-11 | 4
148 | Sparkle clean |  | 2025-12-13 | 2025-12-16 | 2
148 | Sparkle clean |  | 2025-12-19 | 2025-12-24 | 4
148 | Sparkle clean |  | 2025-12-26 | 2025-12-29 | 2
148 | Sparkle clean |  | 2026-01-05 | 2026-01-06 | 2
148 | Sparkle clean |  | 2026-01-11 | 2026-01-13 | 2
148 | Sparkle clean |  | 2026-01-19 | 2026-01-21 | 3
148 | Sparkle clean |  | 2026-01-25 | 2026-03-03 | 27
148 | Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
148 | Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
148 | Sparkle clean |  | 2026-03-20 | 2026-03-21 | 1
148 | Sparkle clean |  | 2026-03-27 | 2026-03-28 | 1
148 | Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
148 | Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
148 | Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
148 | Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
148 | Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
148 | Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
148 | Sparkle clean |  | 2026-05-15 | 2026-05-23 | 6
148 | Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
148 | Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
148 | Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
148 | Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
149 | RED |  | 2025-12-07 | 2025-12-11 | 4
149 | RED |  | 2025-12-13 | 2025-12-16 | 2
149 | RED |  | 2025-12-19 | 2025-12-24 | 4
149 | RED |  | 2025-12-26 | 2025-12-29 | 2
149 | RED |  | 2026-01-05 | 2026-01-06 | 2
149 | RED |  | 2026-01-11 | 2026-01-13 | 2
149 | RED |  | 2026-01-19 | 2026-01-21 | 3
149 | RED |  | 2026-01-25 | 2026-03-03 | 27
149 | RED |  | 2026-03-06 | 2026-03-07 | 1
149 | RED |  | 2026-03-13 | 2026-03-14 | 1
149 | RED |  | 2026-03-20 | 2026-03-21 | 1
149 | RED |  | 2026-03-27 | 2026-03-28 | 1
149 | RED |  | 2026-04-04 | 2026-04-05 | 1
149 | RED |  | 2026-04-11 | 2026-04-12 | 1
149 | RED |  | 2026-04-18 | 2026-04-19 | 1
149 | RED |  | 2026-04-25 | 2026-04-26 | 1
149 | RED |  | 2026-05-01 | 2026-05-02 | 1
149 | RED |  | 2026-05-08 | 2026-05-09 | 1
149 | RED |  | 2026-05-15 | 2026-05-16 | 1
149 | RED |  | 2026-05-22 | 2026-05-25 | 2
149 | RED |  | 2026-05-29 | 2026-05-30 | 1
149 | RED |  | 2026-06-06 | 2026-06-07 | 1
149 | RED |  | 2026-06-13 | 2026-06-14 | 1
149 | RED |  | 2026-06-20 | 2026-06-21 | 1
| Handover to client |  | 2025-12-07 | 2025-12-11 | 4
| Handover to client |  | 2025-12-13 | 2025-12-16 | 2
| Handover to client |  | 2025-12-19 | 2025-12-24 | 4
| Handover to client |  | 2025-12-26 | 2025-12-29 | 2
| Handover to client |  | 2026-01-05 | 2026-01-06 | 2
| Handover to client |  | 2026-01-11 | 2026-01-13 | 2
| Handover to client |  | 2026-01-19 | 2026-01-21 | 3
| Handover to client |  | 2026-01-25 | 2026-03-03 | 27
| Handover to client |  | 2026-03-06 | 2026-03-07 | 1
| Handover to client |  | 2026-03-13 | 2026-03-14 | 1
| Handover to client |  | 2026-03-20 | 2026-03-21 | 1
| Handover to client |  | 2026-03-27 | 2026-03-28 | 1
| Handover to client |  | 2026-04-04 | 2026-04-05 | 1
| Handover to client |  | 2026-04-11 | 2026-04-12 | 1
| Handover to client |  | 2026-04-18 | 2026-04-19 | 1
| Handover to client |  | 2026-04-25 | 2026-04-26 | 1
| Handover to client |  | 2026-05-01 | 2026-05-02 | 1
| Handover to client |  | 2026-05-08 | 2026-05-09 | 1
| Handover to client |  | 2026-05-15 | 2026-05-16 | 1
| Handover to client |  | 2026-05-22 | 2026-05-23 | 1
| Handover to client |  | 2026-05-29 | 2026-05-30 | 1
| Handover to client |  | 2026-06-06 | 2026-06-08 | 1
| Handover to client |  | 2026-06-13 | 2026-06-14 | 1
| Handover to client |  | 2026-06-20 | 2026-06-21 | 1
150 | PANACEA |  | 2025-12-07 | 2025-12-11 | 4
150 | PANACEA |  | 2025-12-13 | 2025-12-16 | 2
150 | PANACEA |  | 2025-12-19 | 2025-12-24 | 4
150 | PANACEA |  | 2025-12-26 | 2025-12-29 | 2
150 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
150 | PANACEA |  | 2026-01-11 | 2026-01-13 | 2
150 | PANACEA |  | 2026-01-19 | 2026-01-21 | 3
150 | PANACEA |  | 2026-01-25 | 2026-03-03 | 27
150 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
150 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
150 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
150 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
150 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
150 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
150 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
150 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
150 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
150 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
150 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
150 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
150 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
150 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
150 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
150 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
152 | First fix wire -ceilings/walls |  | 2025-12-07 | 2025-12-11 | 4
152 | First fix wire -ceilings/walls |  | 2025-12-13 | 2025-12-16 | 2
152 | First fix wire -ceilings/walls |  | 2025-12-19 | 2025-12-24 | 4
152 | First fix wire -ceilings/walls |  | 2025-12-26 | 2025-12-29 | 2
152 | First fix wire -ceilings/walls |  | 2026-01-05 | 2026-01-06 | 2
152 | First fix wire -ceilings/walls |  | 2026-01-11 | 2026-01-13 | 2
152 | First fix wire -ceilings/walls |  | 2026-01-19 | 2026-01-21 | 3
152 | First fix wire -ceilings/walls |  | 2026-01-25 | 2026-03-03 | 27
152 | First fix wire -ceilings/walls |  | 2026-03-06 | 2026-03-07 | 1
152 | First fix wire -ceilings/walls |  | 2026-03-13 | 2026-03-14 | 1
152 | First fix wire -ceilings/walls |  | 2026-03-20 | 2026-03-21 | 1
152 | First fix wire -ceilings/walls |  | 2026-03-27 | 2026-03-28 | 1
152 | First fix wire -ceilings/walls |  | 2026-04-04 | 2026-04-05 | 1
152 | First fix wire -ceilings/walls |  | 2026-04-11 | 2026-04-12 | 1
152 | First fix wire -ceilings/walls |  | 2026-04-18 | 2026-04-19 | 1
152 | First fix wire -ceilings/walls |  | 2026-04-25 | 2026-04-26 | 1
152 | First fix wire -ceilings/walls |  | 2026-05-01 | 2026-05-02 | 1
152 | First fix wire -ceilings/walls |  | 2026-05-08 | 2026-05-09 | 1
152 | First fix wire -ceilings/walls |  | 2026-05-15 | 2026-05-16 | 1
152 | First fix wire -ceilings/walls |  | 2026-05-22 | 2026-05-23 | 1
152 | First fix wire -ceilings/walls |  | 2026-05-29 | 2026-05-30 | 1
152 | First fix wire -ceilings/walls |  | 2026-06-06 | 2026-06-07 | 1
152 | First fix wire -ceilings/walls |  | 2026-06-13 | 2026-06-14 | 1
152 | First fix wire -ceilings/walls |  | 2026-06-20 | 2026-06-21 | 1
| first fix plumbing |  | 2025-12-07 | 2025-12-11 | 4
| first fix plumbing |  | 2025-12-13 | 2025-12-16 | 2
| first fix plumbing |  | 2025-12-19 | 2025-12-24 | 4
| first fix plumbing |  | 2025-12-26 | 2025-12-29 | 2
| first fix plumbing |  | 2026-01-05 | 2026-01-06 | 2
| first fix plumbing |  | 2026-01-11 | 2026-01-13 | 2
| first fix plumbing |  | 2026-01-19 | 2026-01-21 | 3
| first fix plumbing |  | 2026-01-25 | 2026-03-03 | 27
| first fix plumbing |  | 2026-03-06 | 2026-03-07 | 1
| first fix plumbing |  | 2026-03-13 | 2026-03-14 | 1
| first fix plumbing |  | 2026-03-20 | 2026-03-21 | 1
| first fix plumbing |  | 2026-03-27 | 2026-03-28 | 1
| first fix plumbing |  | 2026-04-04 | 2026-04-05 | 1
| first fix plumbing |  | 2026-04-11 | 2026-04-12 | 1
| first fix plumbing |  | 2026-04-18 | 2026-04-19 | 1
| first fix plumbing |  | 2026-04-25 | 2026-04-26 | 1
| first fix plumbing |  | 2026-05-01 | 2026-05-02 | 1
| first fix plumbing |  | 2026-05-08 | 2026-05-09 | 1
| first fix plumbing |  | 2026-05-15 | 2026-05-16 | 1
| first fix plumbing |  | 2026-05-22 | 2026-05-23 | 1
| first fix plumbing |  | 2026-05-29 | 2026-05-30 | 1
| first fix plumbing |  | 2026-06-06 | 2026-06-07 | 1
| first fix plumbing |  | 2026-06-13 | 2026-06-14 | 1
| first fix plumbing |  | 2026-06-20 | 2026-06-21 | 1
| Wall void closure checklist sign off |  | 2025-12-07 | 2025-12-11 | 4
| Wall void closure checklist sign off |  | 2025-12-13 | 2025-12-16 | 2
| Wall void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
| Wall void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
| Wall void closure checklist sign off |  | 2026-01-05 | 2026-01-06 | 2
| Wall void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
| Wall void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
| Wall void closure checklist sign off |  | 2026-01-25 | 2026-03-03 | 27
| Wall void closure checklist sign off |  | 2026-03-06 | 2026-03-07 | 1
| Wall void closure checklist sign off |  | 2026-03-13 | 2026-03-14 | 1
| Wall void closure checklist sign off |  | 2026-03-20 | 2026-03-21 | 1
| Wall void closure checklist sign off |  | 2026-03-27 | 2026-03-28 | 1
| Wall void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
| Wall void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
| Wall void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
| Wall void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
| Wall void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
| Wall void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
| Wall void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
| Wall void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
| Wall void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
| Wall void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
| Wall void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
| Wall void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
2nd board walls | 2nd board walls |  | 2025-12-07 | 2025-12-11 | 4
2nd board walls | 2nd board walls |  | 2025-12-13 | 2025-12-16 | 2
2nd board walls | 2nd board walls |  | 2025-12-19 | 2025-12-24 | 4
2nd board walls | 2nd board walls |  | 2025-12-26 | 2025-12-29 | 2
2nd board walls | 2nd board walls |  | 2026-01-05 | 2026-01-06 | 2
2nd board walls | 2nd board walls |  | 2026-01-11 | 2026-01-13 | 2
2nd board walls | 2nd board walls |  | 2026-01-19 | 2026-01-21 | 3
2nd board walls | 2nd board walls |  | 2026-01-25 | 2026-03-03 | 27
2nd board walls | 2nd board walls |  | 2026-03-06 | 2026-03-07 | 1
2nd board walls | 2nd board walls |  | 2026-03-13 | 2026-03-14 | 1
2nd board walls | 2nd board walls |  | 2026-03-20 | 2026-03-21 | 1
2nd board walls | 2nd board walls |  | 2026-03-27 | 2026-03-28 | 1
2nd board walls | 2nd board walls |  | 2026-04-04 | 2026-04-05 | 1
2nd board walls | 2nd board walls |  | 2026-04-11 | 2026-04-12 | 1
2nd board walls | 2nd board walls |  | 2026-04-18 | 2026-04-19 | 1
2nd board walls | 2nd board walls |  | 2026-04-25 | 2026-04-26 | 1
2nd board walls | 2nd board walls |  | 2026-05-01 | 2026-05-02 | 1
2nd board walls | 2nd board walls |  | 2026-05-08 | 2026-05-09 | 1
2nd board walls | 2nd board walls |  | 2026-05-15 | 2026-05-16 | 1
2nd board walls | 2nd board walls |  | 2026-05-22 | 2026-05-23 | 1
2nd board walls | 2nd board walls |  | 2026-05-29 | 2026-05-30 | 1
2nd board walls | 2nd board walls |  | 2026-06-06 | 2026-06-07 | 1
2nd board walls | 2nd board walls |  | 2026-06-13 | 2026-06-14 | 1
2nd board walls | 2nd board walls |  | 2026-06-20 | 2026-06-21 | 1
| Firestop to RWP/SVP wall penetrations |  | 2025-12-07 | 2025-12-16 | 7
| Firestop to RWP/SVP wall penetrations |  | 2025-12-19 | 2025-12-24 | 4
| Firestop to RWP/SVP wall penetrations |  | 2025-12-26 | 2025-12-29 | 2
| Firestop to RWP/SVP wall penetrations |  | 2026-01-05 | 2026-01-06 | 2
| Firestop to RWP/SVP wall penetrations |  | 2026-01-12 | 2026-01-21 | 8
| Firestop to RWP/SVP wall penetrations |  | 2026-01-25 | 2026-03-07 | 30
| Firestop to RWP/SVP wall penetrations |  | 2026-03-13 | 2026-03-14 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-03-20 | 2026-03-21 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-03-27 | 2026-03-28 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-04-04 | 2026-04-05 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-04-11 | 2026-04-12 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-04-18 | 2026-04-19 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-04-25 | 2026-04-26 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-05-01 | 2026-05-02 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-05-08 | 2026-05-09 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-05-15 | 2026-05-16 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-05-22 | 2026-05-23 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-05-29 | 2026-05-30 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-06-06 | 2026-06-07 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-06-13 | 2026-06-14 | 1
| Firestop to RWP/SVP wall penetrations |  | 2026-06-20 | 2026-06-21 | 1
156 | Install Vents/ducts |  | 2025-12-07 | 2025-12-11 | 4
156 | Install Vents/ducts |  | 2025-12-13 | 2025-12-24 | 8
156 | Install Vents/ducts |  | 2025-12-26 | 2025-12-29 | 2
156 | Install Vents/ducts |  | 2026-01-05 | 2026-01-06 | 2
156 | Install Vents/ducts |  | 2026-01-11 | 2026-01-13 | 2
156 | Install Vents/ducts |  | 2026-01-19 | 2026-01-21 | 3
156 | Install Vents/ducts |  | 2026-01-25 | 2026-03-03 | 27
156 | Install Vents/ducts |  | 2026-03-06 | 2026-03-07 | 1
156 | Install Vents/ducts |  | 2026-03-13 | 2026-03-14 | 1
156 | Install Vents/ducts |  | 2026-03-20 | 2026-03-21 | 1
156 | Install Vents/ducts |  | 2026-03-27 | 2026-03-28 | 1
156 | Install Vents/ducts |  | 2026-04-04 | 2026-04-05 | 1
156 | Install Vents/ducts |  | 2026-04-11 | 2026-04-12 | 1
156 | Install Vents/ducts |  | 2026-04-18 | 2026-04-19 | 1
156 | Install Vents/ducts |  | 2026-04-25 | 2026-04-26 | 1
156 | Install Vents/ducts |  | 2026-05-01 | 2026-05-02 | 1
156 | Install Vents/ducts |  | 2026-05-08 | 2026-05-09 | 1
156 | Install Vents/ducts |  | 2026-05-15 | 2026-05-16 | 1
156 | Install Vents/ducts |  | 2026-05-22 | 2026-05-23 | 1
156 | Install Vents/ducts |  | 2026-05-29 | 2026-05-30 | 1
156 | Install Vents/ducts |  | 2026-06-06 | 2026-06-07 | 1
156 | Install Vents/ducts |  | 2026-06-13 | 2026-06-14 | 1
156 | Install Vents/ducts |  | 2026-06-20 | 2026-06-21 | 1
| 1st fix sprinkler |  | 2025-12-07 | 2025-12-11 | 4
| 1st fix sprinkler |  | 2025-12-13 | 2025-12-24 | 8
| 1st fix sprinkler |  | 2025-12-26 | 2025-12-29 | 2
| 1st fix sprinkler |  | 2026-01-05 | 2026-01-06 | 2
| 1st fix sprinkler |  | 2026-01-11 | 2026-01-13 | 2
| 1st fix sprinkler |  | 2026-01-19 | 2026-01-21 | 3
| 1st fix sprinkler |  | 2026-01-25 | 2026-03-03 | 27
| 1st fix sprinkler |  | 2026-03-06 | 2026-03-07 | 1
| 1st fix sprinkler |  | 2026-03-13 | 2026-03-14 | 1
| 1st fix sprinkler |  | 2026-03-20 | 2026-03-21 | 1
| 1st fix sprinkler |  | 2026-03-27 | 2026-03-28 | 1
| 1st fix sprinkler |  | 2026-04-04 | 2026-04-05 | 1
| 1st fix sprinkler |  | 2026-04-11 | 2026-04-12 | 1
| 1st fix sprinkler |  | 2026-04-18 | 2026-04-19 | 1
| 1st fix sprinkler |  | 2026-04-25 | 2026-04-26 | 1
| 1st fix sprinkler |  | 2026-05-01 | 2026-05-02 | 1
| 1st fix sprinkler |  | 2026-05-08 | 2026-05-09 | 1
| 1st fix sprinkler |  | 2026-05-15 | 2026-05-16 | 1
| 1st fix sprinkler |  | 2026-05-22 | 2026-05-23 | 1
| 1st fix sprinkler |  | 2026-05-29 | 2026-05-30 | 1
| 1st fix sprinkler |  | 2026-06-06 | 2026-06-07 | 1
| 1st fix sprinkler |  | 2026-06-13 | 2026-06-14 | 1
| 1st fix sprinkler |  | 2026-06-20 | 2026-06-21 | 1
157 | RED |  | 2025-12-07 | 2025-12-11 | 4
157 | RED |  | 2025-12-13 | 2025-12-29 | 11
157 | RED |  | 2026-01-05 | 2026-01-06 | 2
157 | RED |  | 2026-01-11 | 2026-01-23 | 10
157 | RED |  | 2026-01-25 | 2026-03-02 | 26
157 | RED |  | 2026-03-06 | 2026-03-07 | 1
157 | RED |  | 2026-03-13 | 2026-03-14 | 1
157 | RED |  | 2026-03-20 | 2026-03-21 | 1
157 | RED |  | 2026-03-27 | 2026-03-28 | 1
157 | RED |  | 2026-04-04 | 2026-04-05 | 1
157 | RED |  | 2026-04-11 | 2026-04-12 | 1
157 | RED |  | 2026-04-18 | 2026-04-19 | 1
157 | RED |  | 2026-04-25 | 2026-04-26 | 1
157 | RED |  | 2026-05-01 | 2026-05-02 | 1
157 | RED |  | 2026-05-08 | 2026-05-09 | 1
157 | RED |  | 2026-05-15 | 2026-05-16 | 1
157 | RED |  | 2026-05-22 | 2026-05-23 | 1
157 | RED |  | 2026-05-29 | 2026-05-30 | 1
157 | RED |  | 2026-06-06 | 2026-06-07 | 1
157 | RED |  | 2026-06-13 | 2026-06-14 | 1
157 | RED |  | 2026-06-20 | 2026-06-21 | 1
158 | PANACEA |  | 2025-12-07 | 2025-12-11 | 4
158 | PANACEA |  | 2025-12-13 | 2025-12-29 | 11
158 | PANACEA |  | 2026-01-05 | 2026-01-06 | 2
158 | PANACEA |  | 2026-01-11 | 2026-01-13 | 2
158 | PANACEA |  | 2026-01-19 | 2026-03-03 | 32
158 | PANACEA |  | 2026-03-06 | 2026-03-07 | 1
158 | PANACEA |  | 2026-03-13 | 2026-03-14 | 1
158 | PANACEA |  | 2026-03-20 | 2026-03-21 | 1
158 | PANACEA |  | 2026-03-27 | 2026-03-28 | 1
158 | PANACEA |  | 2026-04-04 | 2026-04-05 | 1
158 | PANACEA |  | 2026-04-11 | 2026-04-12 | 1
158 | PANACEA |  | 2026-04-18 | 2026-04-19 | 1
158 | PANACEA |  | 2026-04-25 | 2026-04-26 | 1
158 | PANACEA |  | 2026-05-01 | 2026-05-02 | 1
158 | PANACEA |  | 2026-05-08 | 2026-05-09 | 1
158 | PANACEA |  | 2026-05-15 | 2026-05-16 | 1
158 | PANACEA |  | 2026-05-22 | 2026-05-23 | 1
158 | PANACEA |  | 2026-05-29 | 2026-05-30 | 1
158 | PANACEA |  | 2026-06-06 | 2026-06-07 | 1
158 | PANACEA |  | 2026-06-13 | 2026-06-14 | 1
158 | PANACEA |  | 2026-06-20 | 2026-06-21 | 1
159 | CARA |  | 2025-12-07 | 2025-12-11 | 4
159 | CARA |  | 2025-12-13 | 2025-12-16 | 2
159 | CARA |  | 2025-12-19 | 2025-12-29 | 7
159 | CARA |  | 2026-01-05 | 2026-01-06 | 2
159 | CARA |  | 2026-01-11 | 2026-01-13 | 2
159 | CARA |  | 2026-01-19 | 2026-01-21 | 3
159 | CARA |  | 2026-01-25 | 2026-03-07 | 30
159 | CARA |  | 2026-03-13 | 2026-03-14 | 1
159 | CARA |  | 2026-03-20 | 2026-03-21 | 1
159 | CARA |  | 2026-03-27 | 2026-03-28 | 1
159 | CARA |  | 2026-04-04 | 2026-04-05 | 1
159 | CARA |  | 2026-04-11 | 2026-04-12 | 1
159 | CARA |  | 2026-04-18 | 2026-04-19 | 1
159 | CARA |  | 2026-04-25 | 2026-04-26 | 1
159 | CARA |  | 2026-05-01 | 2026-05-02 | 1
159 | CARA |  | 2026-05-08 | 2026-05-09 | 1
159 | CARA |  | 2026-05-15 | 2026-05-16 | 1
159 | CARA |  | 2026-05-22 | 2026-05-23 | 1
159 | CARA |  | 2026-05-29 | 2026-05-30 | 1
159 | CARA |  | 2026-06-06 | 2026-06-07 | 1
159 | CARA |  | 2026-06-13 | 2026-06-14 | 1
159 | CARA |  | 2026-06-20 | 2026-06-21 | 1
160 | Sprinkler 2nd fix fix & test |  | 2025-12-07 | 2025-12-11 | 4
160 | Sprinkler 2nd fix fix & test |  | 2025-12-13 | 2025-12-16 | 2
160 | Sprinkler 2nd fix fix & test |  | 2025-12-19 | 2025-12-29 | 7
160 | Sprinkler 2nd fix fix & test |  | 2026-01-05 | 2026-01-06 | 2
160 | Sprinkler 2nd fix fix & test |  | 2026-01-11 | 2026-01-13 | 2
160 | Sprinkler 2nd fix fix & test |  | 2026-01-19 | 2026-01-21 | 3
160 | Sprinkler 2nd fix fix & test |  | 2026-01-23 | 2026-03-03 | 28
160 | Sprinkler 2nd fix fix & test |  | 2026-03-06 | 2026-03-08 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-03-13 | 2026-03-14 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-03-20 | 2026-03-21 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-03-27 | 2026-03-28 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-04-04 | 2026-04-05 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-04-11 | 2026-04-12 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-04-18 | 2026-04-19 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-04-25 | 2026-04-26 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-05-01 | 2026-05-02 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-05-08 | 2026-05-09 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-05-15 | 2026-05-16 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-05-22 | 2026-05-23 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-05-29 | 2026-05-30 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-06-06 | 2026-06-07 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-06-13 | 2026-06-14 | 1
160 | Sprinkler 2nd fix fix & test |  | 2026-06-20 | 2026-06-21 | 1
161 | Ceilings - board (cut holes for lights) |  | 2025-12-07 | 2025-12-11 | 4
161 | Ceilings - board (cut holes for lights) |  | 2025-12-13 | 2025-12-16 | 2
161 | Ceilings - board (cut holes for lights) |  | 2025-12-19 | 2025-12-29 | 7
161 | Ceilings - board (cut holes for lights) |  | 2026-01-05 | 2026-01-13 | 7
161 | Ceilings - board (cut holes for lights) |  | 2026-01-19 | 2026-01-21 | 3
161 | Ceilings - board (cut holes for lights) |  | 2026-01-23 | 2026-02-28 | 26
161 | Ceilings - board (cut holes for lights) |  | 2026-03-06 | 2026-03-07 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-03-09 | 2026-03-11 | 3
161 | Ceilings - board (cut holes for lights) |  | 2026-03-13 | 2026-03-14 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-03-20 | 2026-03-21 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-03-27 | 2026-03-28 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-04-04 | 2026-04-05 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-04-11 | 2026-04-12 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-04-18 | 2026-04-19 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-04-25 | 2026-04-26 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-05-01 | 2026-05-02 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-05-08 | 2026-05-09 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-05-15 | 2026-05-16 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-05-22 | 2026-05-23 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-05-29 | 2026-05-30 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-06-06 | 2026-06-07 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-06-13 | 2026-06-14 | 1
161 | Ceilings - board (cut holes for lights) |  | 2026-06-20 | 2026-06-21 | 1
162 | Plaster spray |  | 2025-12-07 | 2025-12-11 | 4
162 | Plaster spray |  | 2025-12-13 | 2025-12-16 | 2
162 | Plaster spray |  | 2025-12-19 | 2025-12-29 | 7
162 | Plaster spray |  | 2026-01-05 | 2026-01-13 | 7
162 | Plaster spray |  | 2026-01-19 | 2026-01-21 | 3
162 | Plaster spray |  | 2026-01-24 | 2026-02-28 | 25
162 | Plaster spray |  | 2026-03-06 | 2026-03-07 | 1
162 | Plaster spray |  | 2026-03-11 | 2026-03-16 | 4
162 | Plaster spray |  | 2026-03-20 | 2026-03-21 | 1
162 | Plaster spray |  | 2026-03-27 | 2026-03-28 | 1
162 | Plaster spray |  | 2026-04-04 | 2026-04-05 | 1
162 | Plaster spray |  | 2026-04-11 | 2026-04-12 | 1
162 | Plaster spray |  | 2026-04-18 | 2026-04-19 | 1
162 | Plaster spray |  | 2026-04-25 | 2026-04-26 | 1
162 | Plaster spray |  | 2026-05-01 | 2026-05-02 | 1
162 | Plaster spray |  | 2026-05-08 | 2026-05-09 | 1
162 | Plaster spray |  | 2026-05-15 | 2026-05-16 | 1
162 | Plaster spray |  | 2026-05-22 | 2026-05-23 | 1
162 | Plaster spray |  | 2026-05-29 | 2026-05-30 | 1
162 | Plaster spray |  | 2026-06-06 | 2026-06-07 | 1
162 | Plaster spray |  | 2026-06-13 | 2026-06-14 | 1
162 | Plaster spray |  | 2026-06-20 | 2026-06-21 | 1
163 | Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-11 | 4
163 | Levveling screed /smoothing compound |  | 2025-12-13 | 2025-12-16 | 2
163 | Levveling screed /smoothing compound |  | 2025-12-19 | 2025-12-29 | 7
163 | Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-13 | 7
163 | Levveling screed /smoothing compound |  | 2026-01-19 | 2026-01-21 | 3
163 | Levveling screed /smoothing compound |  | 2026-01-24 | 2026-02-28 | 25
163 | Levveling screed /smoothing compound |  | 2026-03-06 | 2026-03-07 | 1
163 | Levveling screed /smoothing compound |  | 2026-03-13 | 2026-03-14 | 1
163 | Levveling screed /smoothing compound |  | 2026-03-17 | 2026-03-23 | 5
163 | Levveling screed /smoothing compound |  | 2026-03-27 | 2026-03-28 | 1
163 | Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
163 | Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
163 | Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
163 | Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
163 | Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
163 | Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
163 | Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
163 | Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
163 | Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
163 | Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
163 | Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
163 | Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
164 | Drying out |  | 2025-12-07 | 2025-12-11 | 4
164 | Drying out |  | 2025-12-13 | 2025-12-16 | 2
164 | Drying out |  | 2025-12-19 | 2025-12-24 | 4
164 | Drying out |  | 2025-12-26 | 2025-12-29 | 2
164 | Drying out |  | 2026-01-05 | 2026-01-13 | 7
164 | Drying out |  | 2026-01-19 | 2026-01-21 | 3
164 | Drying out |  | 2026-01-25 | 2026-02-28 | 25
164 | Drying out |  | 2026-03-06 | 2026-03-07 | 1
164 | Drying out |  | 2026-03-13 | 2026-03-14 | 1
164 | Drying out |  | 2026-03-20 | 2026-03-28 | 6
164 | Drying out |  | 2026-04-04 | 2026-04-05 | 1
164 | Drying out |  | 2026-04-11 | 2026-04-12 | 1
164 | Drying out |  | 2026-04-18 | 2026-04-19 | 1
164 | Drying out |  | 2026-04-25 | 2026-04-26 | 1
164 | Drying out |  | 2026-05-01 | 2026-05-02 | 1
164 | Drying out |  | 2026-05-08 | 2026-05-09 | 1
164 | Drying out |  | 2026-05-15 | 2026-05-16 | 1
164 | Drying out |  | 2026-05-22 | 2026-05-23 | 1
164 | Drying out |  | 2026-05-29 | 2026-05-30 | 1
164 | Drying out |  | 2026-06-06 | 2026-06-07 | 1
164 | Drying out |  | 2026-06-13 | 2026-06-14 | 1
164 | Drying out |  | 2026-06-20 | 2026-06-21 | 1
164 | Drying out |  | 2026-06-25 | 2026-06-30 | 4
165 | Mist coat |  | 2025-12-07 | 2025-12-11 | 4
165 | Mist coat |  | 2025-12-13 | 2025-12-16 | 2
165 | Mist coat |  | 2025-12-19 | 2025-12-24 | 4
165 | Mist coat |  | 2025-12-26 | 2025-12-29 | 2
165 | Mist coat |  | 2026-01-05 | 2026-01-13 | 7
165 | Mist coat |  | 2026-01-19 | 2026-01-21 | 3
165 | Mist coat |  | 2026-01-25 | 2026-02-28 | 25
165 | Mist coat |  | 2026-03-06 | 2026-03-07 | 1
165 | Mist coat |  | 2026-03-13 | 2026-03-14 | 1
165 | Mist coat |  | 2026-03-20 | 2026-03-21 | 1
165 | Mist coat |  | 2026-03-24 | 2026-03-28 | 4
165 | Mist coat |  | 2026-04-04 | 2026-04-05 | 1
165 | Mist coat |  | 2026-04-11 | 2026-04-12 | 1
165 | Mist coat |  | 2026-04-18 | 2026-04-19 | 1
165 | Mist coat |  | 2026-04-25 | 2026-04-26 | 1
165 | Mist coat |  | 2026-05-01 | 2026-05-02 | 1
165 | Mist coat |  | 2026-05-08 | 2026-05-09 | 1
165 | Mist coat |  | 2026-05-15 | 2026-05-16 | 1
165 | Mist coat |  | 2026-05-22 | 2026-05-23 | 1
165 | Mist coat |  | 2026-05-29 | 2026-05-30 | 1
165 | Mist coat |  | 2026-06-06 | 2026-06-07 | 1
165 | Mist coat |  | 2026-06-13 | 2026-06-14 | 1
165 | Mist coat |  | 2026-06-20 | 2026-06-21 | 1
| Vanity 1st fix framing |  | 2025-12-07 | 2025-12-11 | 4
| Vanity 1st fix framing |  | 2025-12-13 | 2025-12-16 | 2
| Vanity 1st fix framing |  | 2025-12-19 | 2025-12-24 | 4
| Vanity 1st fix framing |  | 2025-12-26 | 2025-12-29 | 2
| Vanity 1st fix framing |  | 2026-01-05 | 2026-01-13 | 7
| Vanity 1st fix framing |  | 2026-01-19 | 2026-01-21 | 3
| Vanity 1st fix framing |  | 2026-01-25 | 2026-02-28 | 25
| Vanity 1st fix framing |  | 2026-03-06 | 2026-03-07 | 1
| Vanity 1st fix framing |  | 2026-03-13 | 2026-03-14 | 1
| Vanity 1st fix framing |  | 2026-03-18 | 2026-03-21 | 3
| Vanity 1st fix framing |  | 2026-03-27 | 2026-03-28 | 1
| Vanity 1st fix framing |  | 2026-04-04 | 2026-04-05 | 1
| Vanity 1st fix framing |  | 2026-04-11 | 2026-04-12 | 1
| Vanity 1st fix framing |  | 2026-04-18 | 2026-04-19 | 1
| Vanity 1st fix framing |  | 2026-04-25 | 2026-04-26 | 1
| Vanity 1st fix framing |  | 2026-05-01 | 2026-05-02 | 1
| Vanity 1st fix framing |  | 2026-05-08 | 2026-05-09 | 1
| Vanity 1st fix framing |  | 2026-05-15 | 2026-05-16 | 1
| Vanity 1st fix framing |  | 2026-05-22 | 2026-05-23 | 1
| Vanity 1st fix framing |  | 2026-05-29 | 2026-05-30 | 1
| Vanity 1st fix framing |  | 2026-06-06 | 2026-06-07 | 1
| Vanity 1st fix framing |  | 2026-06-13 | 2026-06-14 | 1
| Vanity 1st fix framing |  | 2026-06-20 | 2026-06-21 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-11 | 4
166 | Kitchen 1st fix,units tops & appliances |  | 2025-12-13 | 2025-12-16 | 2
166 | Kitchen 1st fix,units tops & appliances |  | 2025-12-19 | 2025-12-24 | 4
166 | Kitchen 1st fix,units tops & appliances |  | 2025-12-26 | 2025-12-29 | 2
166 | Kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-06 | 2
166 | Kitchen 1st fix,units tops & appliances |  | 2026-01-11 | 2026-01-13 | 2
166 | Kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-21 | 3
166 | Kitchen 1st fix,units tops & appliances |  | 2026-01-25 | 2026-03-03 | 27
166 | Kitchen 1st fix,units tops & appliances |  | 2026-03-06 | 2026-03-07 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-03-13 | 2026-03-14 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-03-20 | 2026-03-21 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-03-27 | 2026-03-28 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-12 | 5
166 | Kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-05-15 | 2026-05-16 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-05-22 | 2026-05-23 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
166 | Kitchen 1st fix,units tops & appliances |  | 2026-06-20 | 2026-06-21 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2025-12-07 | 2025-12-11 | 4
| Joinery 1st fix -doors, frames ,skirting |  | 2025-12-13 | 2025-12-16 | 2
| Joinery 1st fix -doors, frames ,skirting |  | 2025-12-19 | 2025-12-24 | 4
| Joinery 1st fix -doors, frames ,skirting |  | 2025-12-26 | 2025-12-29 | 2
| Joinery 1st fix -doors, frames ,skirting |  | 2026-01-05 | 2026-01-06 | 2
| Joinery 1st fix -doors, frames ,skirting |  | 2026-01-11 | 2026-01-13 | 2
| Joinery 1st fix -doors, frames ,skirting |  | 2026-01-19 | 2026-01-21 | 3
| Joinery 1st fix -doors, frames ,skirting |  | 2026-01-25 | 2026-03-03 | 27
| Joinery 1st fix -doors, frames ,skirting |  | 2026-03-06 | 2026-03-07 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-03-13 | 2026-03-14 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-03-20 | 2026-03-21 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-03-27 | 2026-03-28 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-04-03 | 2026-04-09 | 5
| Joinery 1st fix -doors, frames ,skirting |  | 2026-04-11 | 2026-04-12 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-04-18 | 2026-04-19 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-04-25 | 2026-04-26 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-05-01 | 2026-05-02 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-05-08 | 2026-05-09 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-05-15 | 2026-05-16 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-05-22 | 2026-05-23 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-05-29 | 2026-05-30 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-06-06 | 2026-06-07 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-06-13 | 2026-06-14 | 1
| Joinery 1st fix -doors, frames ,skirting |  | 2026-06-20 | 2026-06-21 | 1
| Floor and wall tiling |  | 2025-12-07 | 2025-12-11 | 4
| Floor and wall tiling |  | 2025-12-13 | 2025-12-16 | 2
| Floor and wall tiling |  | 2025-12-19 | 2025-12-24 | 4
| Floor and wall tiling |  | 2025-12-26 | 2025-12-29 | 2
| Floor and wall tiling |  | 2026-01-05 | 2026-01-06 | 2
| Floor and wall tiling |  | 2026-01-11 | 2026-01-13 | 2
| Floor and wall tiling |  | 2026-01-19 | 2026-01-21 | 3
| Floor and wall tiling |  | 2026-01-25 | 2026-03-03 | 27
| Floor and wall tiling |  | 2026-03-06 | 2026-03-07 | 1
| Floor and wall tiling |  | 2026-03-13 | 2026-03-14 | 1
| Floor and wall tiling |  | 2026-03-20 | 2026-03-21 | 1
| Floor and wall tiling |  | 2026-03-27 | 2026-04-05 | 6
| Floor and wall tiling |  | 2026-04-11 | 2026-04-12 | 1
| Floor and wall tiling |  | 2026-04-18 | 2026-04-19 | 1
| Floor and wall tiling |  | 2026-04-25 | 2026-04-26 | 1
| Floor and wall tiling |  | 2026-05-01 | 2026-05-02 | 1
| Floor and wall tiling |  | 2026-05-08 | 2026-05-09 | 1
| Floor and wall tiling |  | 2026-05-15 | 2026-05-16 | 1
| Floor and wall tiling |  | 2026-05-22 | 2026-05-23 | 1
| Floor and wall tiling |  | 2026-05-29 | 2026-05-30 | 1
| Floor and wall tiling |  | 2026-06-06 | 2026-06-07 | 1
| Floor and wall tiling |  | 2026-06-13 | 2026-06-14 | 1
| Floor and wall tiling |  | 2026-06-20 | 2026-06-21 | 1
| Control point 4 CP 4 |  | 2025-12-07 | 2025-12-11 | 4
| Control point 4 CP 4 |  | 2025-12-13 | 2025-12-16 | 2
| Control point 4 CP 4 |  | 2025-12-19 | 2025-12-24 | 4
| Control point 4 CP 4 |  | 2025-12-26 | 2025-12-29 | 2
| Control point 4 CP 4 |  | 2026-01-05 | 2026-01-06 | 2
| Control point 4 CP 4 |  | 2026-01-11 | 2026-01-13 | 2
| Control point 4 CP 4 |  | 2026-01-19 | 2026-01-21 | 3
| Control point 4 CP 4 |  | 2026-01-25 | 2026-03-07 | 30
| Control point 4 CP 4 |  | 2026-03-13 | 2026-03-14 | 1
| Control point 4 CP 4 |  | 2026-03-20 | 2026-03-21 | 1
| Control point 4 CP 4 |  | 2026-03-27 | 2026-03-28 | 1
| Control point 4 CP 4 |  | 2026-04-04 | 2026-04-05 | 1
| Control point 4 CP 4 |  | 2026-04-11 | 2026-04-12 | 1
| Control point 4 CP 4 |  | 2026-04-18 | 2026-04-19 | 1
| Control point 4 CP 4 |  | 2026-04-25 | 2026-04-26 | 1
| Control point 4 CP 4 |  | 2026-05-01 | 2026-05-02 | 1
| Control point 4 CP 4 |  | 2026-05-08 | 2026-05-09 | 1
| Control point 4 CP 4 |  | 2026-05-15 | 2026-05-16 | 1
| Control point 4 CP 4 |  | 2026-05-22 | 2026-05-23 | 1
| Control point 4 CP 4 |  | 2026-05-29 | 2026-05-30 | 1
| Control point 4 CP 4 |  | 2026-06-06 | 2026-06-07 | 1
| Control point 4 CP 4 |  | 2026-06-13 | 2026-06-14 | 1
| Control point 4 CP 4 |  | 2026-06-20 | 2026-06-21 | 1
| service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-11 | 4
| service cupbaord -plywood flooring |  | 2025-12-13 | 2025-12-16 | 2
| service cupbaord -plywood flooring |  | 2025-12-19 | 2025-12-24 | 4
| service cupbaord -plywood flooring |  | 2025-12-26 | 2025-12-29 | 2
| service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-06 | 2
| service cupbaord -plywood flooring |  | 2026-01-11 | 2026-01-13 | 2
| service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-21 | 3
| service cupbaord -plywood flooring |  | 2026-01-25 | 2026-03-07 | 30
| service cupbaord -plywood flooring |  | 2026-03-13 | 2026-03-14 | 1
| service cupbaord -plywood flooring |  | 2026-03-20 | 2026-03-21 | 1
| service cupbaord -plywood flooring |  | 2026-03-27 | 2026-03-28 | 1
| service cupbaord -plywood flooring |  | 2026-04-03 | 2026-04-06 | 2
| service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
| service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
| service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
| service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
| service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
| service cupbaord -plywood flooring |  | 2026-05-15 | 2026-05-16 | 1
| service cupbaord -plywood flooring |  | 2026-05-22 | 2026-05-23 | 1
| service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
| service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
| service cupbaord -plywood flooring |  | 2026-06-13 | 2026-06-14 | 1
| service cupbaord -plywood flooring |  | 2026-06-20 | 2026-06-21 | 1
| service cupboard decoration |  | 2025-12-07 | 2025-12-11 | 4
| service cupboard decoration |  | 2025-12-13 | 2025-12-16 | 2
| service cupboard decoration |  | 2025-12-19 | 2025-12-24 | 4
| service cupboard decoration |  | 2025-12-26 | 2025-12-29 | 2
| service cupboard decoration |  | 2026-01-05 | 2026-01-06 | 2
| service cupboard decoration |  | 2026-01-11 | 2026-01-13 | 2
| service cupboard decoration |  | 2026-01-19 | 2026-01-21 | 3
| service cupboard decoration |  | 2026-01-25 | 2026-03-07 | 30
| service cupboard decoration |  | 2026-03-13 | 2026-03-14 | 1
| service cupboard decoration |  | 2026-03-20 | 2026-03-21 | 1
| service cupboard decoration |  | 2026-03-27 | 2026-03-28 | 1
| service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
| service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
| service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
| service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
| service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
| service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
| service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
| service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
| service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
| service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
| service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
| service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-07 | 2025-12-11 | 4
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-13 | 2025-12-16 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-19 | 2025-12-24 | 4
| service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-26 | 2025-12-29 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-05 | 2026-01-06 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-11 | 2026-01-13 | 2
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-19 | 2026-01-21 | 3
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-25 | 2026-03-07 | 30
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-13 | 2026-03-14 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-20 | 2026-03-21 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-03-27 | 2026-03-28 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-04 | 2026-04-05 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-11 | 2026-04-12 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-18 | 2026-04-19 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-25 | 2026-04-26 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-01 | 2026-05-02 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-08 | 2026-05-09 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-15 | 2026-05-16 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-22 | 2026-05-23 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-29 | 2026-05-30 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-06 | 2026-06-07 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-13 | 2026-06-14 | 1
| service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-11 | 4
| Amtico flooring /Bathrooms |  | 2025-12-13 | 2025-12-16 | 2
| Amtico flooring /Bathrooms |  | 2025-12-19 | 2025-12-24 | 4
| Amtico flooring /Bathrooms |  | 2025-12-26 | 2025-12-29 | 2
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-06 | 2
| Amtico flooring /Bathrooms |  | 2026-01-11 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-21 | 3
| Amtico flooring /Bathrooms |  | 2026-01-25 | 2026-03-07 | 30
| Amtico flooring /Bathrooms |  | 2026-03-13 | 2026-03-14 | 1
| Amtico flooring /Bathrooms |  | 2026-03-20 | 2026-03-21 | 1
| Amtico flooring /Bathrooms |  | 2026-03-27 | 2026-03-28 | 1
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-11 | 4
167 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-13 | 2025-12-16 | 2
167 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-19 | 2025-12-24 | 4
167 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-26 | 2025-12-29 | 2
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-06 | 2
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-11 | 2026-01-13 | 2
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-21 | 3
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-25 | 2026-03-07 | 30
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-03-13 | 2026-03-14 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-03-20 | 2026-03-21 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-03-27 | 2026-03-28 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-05 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-15 | 2026-05-16 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-22 | 2026-05-23 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-13 | 2026-06-14 | 1
167 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-20 | 2026-06-21 | 1
169 | Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-11 | 4
169 | Electrical 2nd fix & live testing |  | 2025-12-13 | 2025-12-16 | 2
169 | Electrical 2nd fix & live testing |  | 2025-12-19 | 2025-12-24 | 4
169 | Electrical 2nd fix & live testing |  | 2025-12-26 | 2025-12-29 | 2
169 | Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-06 | 2
169 | Electrical 2nd fix & live testing |  | 2026-01-11 | 2026-01-13 | 2
169 | Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
169 | Electrical 2nd fix & live testing |  | 2026-01-25 | 2026-03-03 | 27
169 | Electrical 2nd fix & live testing |  | 2026-03-06 | 2026-03-07 | 1
169 | Electrical 2nd fix & live testing |  | 2026-03-13 | 2026-03-14 | 1
169 | Electrical 2nd fix & live testing |  | 2026-03-20 | 2026-03-21 | 1
169 | Electrical 2nd fix & live testing |  | 2026-03-27 | 2026-03-28 | 1
169 | Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
169 | Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
169 | Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
169 | Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
169 | Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
169 | Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
169 | Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
169 | Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
169 | Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
169 | Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
169 | Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
169 | Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
170 | Builders clean |  | 2025-12-07 | 2025-12-11 | 4
170 | Builders clean |  | 2025-12-13 | 2025-12-16 | 2
170 | Builders clean |  | 2025-12-19 | 2025-12-24 | 4
170 | Builders clean |  | 2025-12-26 | 2025-12-29 | 2
170 | Builders clean |  | 2026-01-05 | 2026-01-06 | 2
170 | Builders clean |  | 2026-01-11 | 2026-01-13 | 2
170 | Builders clean |  | 2026-01-19 | 2026-01-21 | 3
170 | Builders clean |  | 2026-01-25 | 2026-03-03 | 27
170 | Builders clean |  | 2026-03-06 | 2026-03-07 | 1
170 | Builders clean |  | 2026-03-13 | 2026-03-14 | 1
170 | Builders clean |  | 2026-03-20 | 2026-03-21 | 1
170 | Builders clean |  | 2026-03-27 | 2026-03-28 | 1
170 | Builders clean |  | 2026-04-04 | 2026-04-05 | 1
170 | Builders clean |  | 2026-04-11 | 2026-04-12 | 1
170 | Builders clean |  | 2026-04-18 | 2026-04-19 | 1
170 | Builders clean |  | 2026-04-25 | 2026-04-26 | 1
170 | Builders clean |  | 2026-05-01 | 2026-05-02 | 1
170 | Builders clean |  | 2026-05-08 | 2026-05-09 | 1
170 | Builders clean |  | 2026-05-15 | 2026-05-16 | 1
170 | Builders clean |  | 2026-05-22 | 2026-05-23 | 1
170 | Builders clean |  | 2026-05-29 | 2026-05-30 | 1
170 | Builders clean |  | 2026-06-06 | 2026-06-07 | 1
170 | Builders clean |  | 2026-06-13 | 2026-06-14 | 1
170 | Builders clean |  | 2026-06-20 | 2026-06-21 | 1
171 | Pre -dec -snagging |  | 2025-12-07 | 2025-12-11 | 4
171 | Pre -dec -snagging |  | 2025-12-13 | 2025-12-16 | 2
171 | Pre -dec -snagging |  | 2025-12-19 | 2025-12-24 | 4
171 | Pre -dec -snagging |  | 2025-12-26 | 2025-12-29 | 2
171 | Pre -dec -snagging |  | 2026-01-05 | 2026-01-06 | 2
171 | Pre -dec -snagging |  | 2026-01-11 | 2026-01-13 | 2
171 | Pre -dec -snagging |  | 2026-01-19 | 2026-01-21 | 3
171 | Pre -dec -snagging |  | 2026-01-25 | 2026-03-03 | 27
171 | Pre -dec -snagging |  | 2026-03-06 | 2026-03-07 | 1
171 | Pre -dec -snagging |  | 2026-03-13 | 2026-03-14 | 1
171 | Pre -dec -snagging |  | 2026-03-20 | 2026-03-21 | 1
171 | Pre -dec -snagging |  | 2026-03-27 | 2026-03-28 | 1
171 | Pre -dec -snagging |  | 2026-04-04 | 2026-04-05 | 1
171 | Pre -dec -snagging |  | 2026-04-11 | 2026-04-12 | 1
171 | Pre -dec -snagging |  | 2026-04-18 | 2026-04-19 | 1
171 | Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
171 | Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
171 | Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
171 | Pre -dec -snagging |  | 2026-05-15 | 2026-05-16 | 1
171 | Pre -dec -snagging |  | 2026-05-22 | 2026-05-23 | 1
171 | Pre -dec -snagging |  | 2026-05-29 | 2026-05-30 | 1
171 | Pre -dec -snagging |  | 2026-06-06 | 2026-06-07 | 1
171 | Pre -dec -snagging |  | 2026-06-13 | 2026-06-14 | 1
171 | Pre -dec -snagging |  | 2026-06-20 | 2026-06-21 | 1
172 | Decoration |  | 2025-12-07 | 2025-12-11 | 4
172 | Decoration |  | 2025-12-13 | 2025-12-16 | 2
172 | Decoration |  | 2025-12-19 | 2025-12-24 | 4
172 | Decoration |  | 2025-12-26 | 2025-12-29 | 2
172 | Decoration |  | 2026-01-05 | 2026-01-06 | 2
172 | Decoration |  | 2026-01-11 | 2026-01-13 | 2
172 | Decoration |  | 2026-01-19 | 2026-01-21 | 3
172 | Decoration |  | 2026-01-25 | 2026-03-03 | 27
172 | Decoration |  | 2026-03-06 | 2026-03-07 | 1
172 | Decoration |  | 2026-03-13 | 2026-03-14 | 1
172 | Decoration |  | 2026-03-20 | 2026-03-21 | 1
172 | Decoration |  | 2026-03-27 | 2026-03-28 | 1
172 | Decoration |  | 2026-04-04 | 2026-04-05 | 1
172 | Decoration |  | 2026-04-11 | 2026-04-12 | 1
172 | Decoration |  | 2026-04-18 | 2026-04-19 | 1
172 | Decoration |  | 2026-04-25 | 2026-04-26 | 1
172 | Decoration |  | 2026-05-01 | 2026-05-02 | 1
172 | Decoration |  | 2026-05-05 | 2026-05-11 | 5
172 | Decoration |  | 2026-05-15 | 2026-05-16 | 1
172 | Decoration |  | 2026-05-22 | 2026-05-23 | 1
172 | Decoration |  | 2026-05-29 | 2026-05-30 | 1
172 | Decoration |  | 2026-06-06 | 2026-06-07 | 1
172 | Decoration |  | 2026-06-13 | 2026-06-14 | 1
172 | Decoration |  | 2026-06-20 | 2026-06-21 | 1
173 | Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-16 | 7
173 | Amtico flooring /Carpets |  | 2025-12-19 | 2025-12-24 | 4
173 | Amtico flooring /Carpets |  | 2025-12-26 | 2025-12-29 | 2
173 | Amtico flooring /Carpets |  | 2026-01-05 | 2026-01-06 | 2
173 | Amtico flooring /Carpets |  | 2026-01-11 | 2026-01-13 | 2
173 | Amtico flooring /Carpets |  | 2026-01-19 | 2026-01-21 | 3
173 | Amtico flooring /Carpets |  | 2026-01-25 | 2026-03-03 | 27
173 | Amtico flooring /Carpets |  | 2026-03-06 | 2026-03-07 | 1
173 | Amtico flooring /Carpets |  | 2026-03-13 | 2026-03-14 | 1
173 | Amtico flooring /Carpets |  | 2026-03-20 | 2026-03-21 | 1
173 | Amtico flooring /Carpets |  | 2026-03-27 | 2026-03-28 | 1
173 | Amtico flooring /Carpets |  | 2026-04-04 | 2026-04-05 | 1
173 | Amtico flooring /Carpets |  | 2026-04-11 | 2026-04-12 | 1
173 | Amtico flooring /Carpets |  | 2026-04-18 | 2026-04-19 | 1
173 | Amtico flooring /Carpets |  | 2026-04-25 | 2026-04-26 | 1
173 | Amtico flooring /Carpets |  | 2026-05-01 | 2026-05-02 | 1
173 | Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
173 | Amtico flooring /Carpets |  | 2026-05-12 | 2026-05-16 | 4
173 | Amtico flooring /Carpets |  | 2026-05-22 | 2026-05-23 | 1
173 | Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
173 | Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
173 | Amtico flooring /Carpets |  | 2026-06-13 | 2026-06-14 | 1
173 | Amtico flooring /Carpets |  | 2026-06-20 | 2026-06-21 | 1
174 | De snag all trades |  | 2025-12-07 | 2025-12-16 | 7
174 | De snag all trades |  | 2025-12-19 | 2025-12-29 | 7
174 | De snag all trades |  | 2026-01-05 | 2026-01-06 | 2
174 | De snag all trades |  | 2026-01-11 | 2026-01-13 | 2
174 | De snag all trades |  | 2026-01-19 | 2026-01-21 | 3
174 | De snag all trades |  | 2026-01-25 | 2026-03-03 | 27
174 | De snag all trades |  | 2026-03-06 | 2026-03-07 | 1
174 | De snag all trades |  | 2026-03-13 | 2026-03-14 | 1
174 | De snag all trades |  | 2026-03-20 | 2026-03-21 | 1
174 | De snag all trades |  | 2026-03-27 | 2026-03-28 | 1
174 | De snag all trades |  | 2026-04-04 | 2026-04-05 | 1
174 | De snag all trades |  | 2026-04-11 | 2026-04-12 | 1
174 | De snag all trades |  | 2026-04-18 | 2026-04-19 | 1
174 | De snag all trades |  | 2026-04-25 | 2026-04-26 | 1
174 | De snag all trades |  | 2026-05-01 | 2026-05-02 | 1
174 | De snag all trades |  | 2026-05-08 | 2026-05-09 | 1
174 | De snag all trades |  | 2026-05-15 | 2026-05-23 | 6
174 | De snag all trades |  | 2026-05-29 | 2026-05-30 | 1
174 | De snag all trades |  | 2026-06-06 | 2026-06-07 | 1
174 | De snag all trades |  | 2026-06-13 | 2026-06-14 | 1
174 | De snag all trades |  | 2026-06-20 | 2026-06-21 | 1
175 | Sparkle clean |  | 2025-12-07 | 2025-12-16 | 7
175 | Sparkle clean |  | 2025-12-19 | 2025-12-29 | 7
175 | Sparkle clean |  | 2026-01-05 | 2026-01-06 | 2
175 | Sparkle clean |  | 2026-01-11 | 2026-01-13 | 2
175 | Sparkle clean |  | 2026-01-19 | 2026-01-21 | 3
175 | Sparkle clean |  | 2026-01-25 | 2026-03-03 | 27
175 | Sparkle clean |  | 2026-03-06 | 2026-03-07 | 1
175 | Sparkle clean |  | 2026-03-13 | 2026-03-14 | 1
175 | Sparkle clean |  | 2026-03-20 | 2026-03-21 | 1
175 | Sparkle clean |  | 2026-03-27 | 2026-03-28 | 1
175 | Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
175 | Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
175 | Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
175 | Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
175 | Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
175 | Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
175 | Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
175 | Sparkle clean |  | 2026-05-22 | 2026-05-30 | 6
175 | Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
175 | Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
175 | Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
176 | Mastic |  | 2025-12-07 | 2025-12-24 | 13
176 | Mastic |  | 2025-12-26 | 2025-12-29 | 2
176 | Mastic |  | 2026-01-05 | 2026-01-06 | 2
176 | Mastic |  | 2026-01-11 | 2026-01-13 | 2
176 | Mastic |  | 2026-01-19 | 2026-01-21 | 3
176 | Mastic |  | 2026-01-25 | 2026-03-03 | 27
176 | Mastic |  | 2026-03-06 | 2026-03-07 | 1
176 | Mastic |  | 2026-03-13 | 2026-03-14 | 1
176 | Mastic |  | 2026-03-20 | 2026-03-21 | 1
176 | Mastic |  | 2026-03-27 | 2026-03-28 | 1
176 | Mastic |  | 2026-04-04 | 2026-04-05 | 1
176 | Mastic |  | 2026-04-11 | 2026-04-12 | 1
176 | Mastic |  | 2026-04-18 | 2026-04-19 | 1
176 | Mastic |  | 2026-04-25 | 2026-04-26 | 1
176 | Mastic |  | 2026-05-01 | 2026-05-02 | 1
176 | Mastic |  | 2026-05-08 | 2026-05-09 | 1
176 | Mastic |  | 2026-05-15 | 2026-05-16 | 1
176 | Mastic |  | 2026-05-22 | 2026-05-23 | 1
176 | Mastic |  | 2026-05-29 | 2026-06-02 | 3
176 | Mastic |  | 2026-06-06 | 2026-06-07 | 1
176 | Mastic |  | 2026-06-13 | 2026-06-14 | 1
176 | Mastic |  | 2026-06-20 | 2026-06-21 | 1
177 | Handover to client |  | 2025-12-07 | 2025-12-11 | 4
177 | Handover to client |  | 2025-12-13 | 2025-12-15 | 1
177 | Handover to client |  | 2025-12-19 | 2025-12-29 | 7
177 | Handover to client |  | 2026-01-05 | 2026-01-06 | 2
177 | Handover to client |  | 2026-01-11 | 2026-01-13 | 2
177 | Handover to client |  | 2026-01-19 | 2026-01-21 | 3
177 | Handover to client |  | 2026-01-25 | 2026-03-03 | 27
177 | Handover to client |  | 2026-03-06 | 2026-03-07 | 1
177 | Handover to client |  | 2026-03-13 | 2026-03-14 | 1
177 | Handover to client |  | 2026-03-20 | 2026-03-21 | 1
177 | Handover to client |  | 2026-03-27 | 2026-03-28 | 1
177 | Handover to client |  | 2026-04-04 | 2026-04-05 | 1
177 | Handover to client |  | 2026-04-11 | 2026-04-12 | 1
177 | Handover to client |  | 2026-04-18 | 2026-04-19 | 1
177 | Handover to client |  | 2026-04-25 | 2026-04-26 | 1
177 | Handover to client |  | 2026-05-01 | 2026-05-02 | 1
177 | Handover to client |  | 2026-05-08 | 2026-05-09 | 1
177 | Handover to client |  | 2026-05-15 | 2026-05-16 | 1
177 | Handover to client |  | 2026-05-22 | 2026-05-23 | 1
177 | Handover to client |  | 2026-05-29 | 2026-05-30 | 1
177 | Handover to client |  | 2026-06-06 | 2026-06-07 | 1
177 | Handover to client |  | 2026-06-13 | 2026-06-15 | 1
177 | Handover to client |  | 2026-06-20 | 2026-06-21 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2025-12-07 | 2025-12-11 | 4
178 | Level 6Apartment fit out -cluster 2 |  | 2025-12-13 | 2025-12-15 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2025-12-19 | 2025-12-22 | 2
178 | Level 6Apartment fit out -cluster 2 |  | 2025-12-26 | 2026-01-02 | 6
178 | Level 6Apartment fit out -cluster 2 |  | 2026-01-05 | 2026-01-06 | 2
178 | Level 6Apartment fit out -cluster 2 |  | 2026-01-11 | 2026-01-13 | 2
178 | Level 6Apartment fit out -cluster 2 |  | 2026-01-19 | 2026-01-20 | 2
178 | Level 6Apartment fit out -cluster 2 |  | 2026-01-25 | 2026-03-03 | 27
178 | Level 6Apartment fit out -cluster 2 |  | 2026-03-06 | 2026-03-07 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-03-13 | 2026-03-14 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-03-20 | 2026-03-21 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-03-27 | 2026-03-28 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-04-04 | 2026-04-05 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-04-11 | 2026-04-12 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-04-18 | 2026-04-19 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-04-25 | 2026-04-26 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-05-01 | 2026-05-02 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-05-08 | 2026-05-09 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-05-15 | 2026-05-16 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-05-22 | 2026-05-23 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-05-29 | 2026-05-30 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-06-06 | 2026-06-07 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-06-13 | 2026-06-14 | 1
178 | Level 6Apartment fit out -cluster 2 |  | 2026-06-20 | 2026-06-21 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2025-12-07 | 2025-12-11 | 4
179 | 1st fix electrical back boxes Edencroft |  | 2025-12-13 | 2025-12-16 | 2
179 | 1st fix electrical back boxes Edencroft |  | 2025-12-19 | 2025-12-22 | 2
179 | 1st fix electrical back boxes Edencroft |  | 2025-12-26 | 2025-12-29 | 2
179 | 1st fix electrical back boxes Edencroft |  | 2026-01-05 | 2026-01-13 | 7
179 | 1st fix electrical back boxes Edencroft |  | 2026-01-16 | 2026-01-22 | 5
179 | 1st fix electrical back boxes Edencroft |  | 2026-01-25 | 2026-03-03 | 27
179 | 1st fix electrical back boxes Edencroft |  | 2026-03-06 | 2026-03-07 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-03-13 | 2026-03-14 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-03-20 | 2026-03-21 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-03-27 | 2026-03-28 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-04-04 | 2026-04-05 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-04-11 | 2026-04-12 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-04-18 | 2026-04-19 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-04-25 | 2026-04-26 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-05-01 | 2026-05-02 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-05-08 | 2026-05-09 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-05-15 | 2026-05-16 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-05-22 | 2026-05-23 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-05-29 | 2026-05-30 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-06-06 | 2026-06-07 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-06-13 | 2026-06-14 | 1
179 | 1st fix electrical back boxes Edencroft |  | 2026-06-20 | 2026-06-21 | 1
| 1st fix partitions/pattreses one side |  | 2025-12-07 | 2025-12-11 | 4
| 1st fix partitions/pattreses one side |  | 2025-12-13 | 2025-12-16 | 2
| 1st fix partitions/pattreses one side |  | 2025-12-19 | 2025-12-22 | 2
| 1st fix partitions/pattreses one side |  | 2025-12-26 | 2025-12-29 | 2
| 1st fix partitions/pattreses one side |  | 2026-01-05 | 2026-01-13 | 7
| 1st fix partitions/pattreses one side |  | 2026-01-19 | 2026-03-03 | 32
| 1st fix partitions/pattreses one side |  | 2026-03-06 | 2026-03-07 | 1
| 1st fix partitions/pattreses one side |  | 2026-03-13 | 2026-03-14 | 1
| 1st fix partitions/pattreses one side |  | 2026-03-20 | 2026-03-21 | 1
| 1st fix partitions/pattreses one side |  | 2026-03-27 | 2026-03-28 | 1
| 1st fix partitions/pattreses one side |  | 2026-04-04 | 2026-04-05 | 1
| 1st fix partitions/pattreses one side |  | 2026-04-11 | 2026-04-12 | 1
| 1st fix partitions/pattreses one side |  | 2026-04-18 | 2026-04-19 | 1
| 1st fix partitions/pattreses one side |  | 2026-04-25 | 2026-04-26 | 1
| 1st fix partitions/pattreses one side |  | 2026-05-01 | 2026-05-02 | 1
| 1st fix partitions/pattreses one side |  | 2026-05-08 | 2026-05-09 | 1
| 1st fix partitions/pattreses one side |  | 2026-05-15 | 2026-05-16 | 1
| 1st fix partitions/pattreses one side |  | 2026-05-22 | 2026-05-23 | 1
| 1st fix partitions/pattreses one side |  | 2026-05-29 | 2026-05-30 | 1
| 1st fix partitions/pattreses one side |  | 2026-06-06 | 2026-06-07 | 1
| 1st fix partitions/pattreses one side |  | 2026-06-13 | 2026-06-14 | 1
| 1st fix partitions/pattreses one side |  | 2026-06-20 | 2026-06-21 | 1
180 | First fix wire -ceilings/walls |  | 2025-12-07 | 2025-12-11 | 4
180 | First fix wire -ceilings/walls |  | 2025-12-13 | 2025-12-16 | 2
180 | First fix wire -ceilings/walls |  | 2025-12-19 | 2025-12-24 | 4
180 | First fix wire -ceilings/walls |  | 2025-12-26 | 2025-12-29 | 2
180 | First fix wire -ceilings/walls |  | 2026-01-05 | 2026-01-06 | 2
180 | First fix wire -ceilings/walls |  | 2026-01-09 | 2026-01-15 | 5
180 | First fix wire -ceilings/walls |  | 2026-01-19 | 2026-01-21 | 3
180 | First fix wire -ceilings/walls |  | 2026-01-25 | 2026-03-03 | 27
180 | First fix wire -ceilings/walls |  | 2026-03-06 | 2026-03-07 | 1
180 | First fix wire -ceilings/walls |  | 2026-03-13 | 2026-03-14 | 1
180 | First fix wire -ceilings/walls |  | 2026-03-20 | 2026-03-21 | 1
180 | First fix wire -ceilings/walls |  | 2026-03-27 | 2026-03-28 | 1
180 | First fix wire -ceilings/walls |  | 2026-04-04 | 2026-04-05 | 1
180 | First fix wire -ceilings/walls |  | 2026-04-11 | 2026-04-12 | 1
180 | First fix wire -ceilings/walls |  | 2026-04-18 | 2026-04-19 | 1
180 | First fix wire -ceilings/walls |  | 2026-04-25 | 2026-04-26 | 1
180 | First fix wire -ceilings/walls |  | 2026-05-01 | 2026-05-02 | 1
180 | First fix wire -ceilings/walls |  | 2026-05-08 | 2026-05-09 | 1
180 | First fix wire -ceilings/walls |  | 2026-05-15 | 2026-05-16 | 1
180 | First fix wire -ceilings/walls |  | 2026-05-22 | 2026-05-23 | 1
180 | First fix wire -ceilings/walls |  | 2026-05-29 | 2026-05-30 | 1
180 | First fix wire -ceilings/walls |  | 2026-06-06 | 2026-06-07 | 1
180 | First fix wire -ceilings/walls |  | 2026-06-13 | 2026-06-14 | 1
180 | First fix wire -ceilings/walls |  | 2026-06-20 | 2026-06-21 | 1
181 | first fix plumbing |  | 2025-12-07 | 2025-12-11 | 4
181 | first fix plumbing |  | 2025-12-13 | 2025-12-16 | 2
181 | first fix plumbing |  | 2025-12-19 | 2025-12-24 | 4
181 | first fix plumbing |  | 2025-12-26 | 2025-12-29 | 2
181 | first fix plumbing |  | 2026-01-05 | 2026-01-06 | 2
181 | first fix plumbing |  | 2026-01-11 | 2026-01-20 | 7
181 | first fix plumbing |  | 2026-01-26 | 2026-03-03 | 27
181 | first fix plumbing |  | 2026-03-06 | 2026-03-07 | 1
181 | first fix plumbing |  | 2026-03-13 | 2026-03-14 | 1
181 | first fix plumbing |  | 2026-03-20 | 2026-03-21 | 1
181 | first fix plumbing |  | 2026-03-27 | 2026-03-28 | 1
181 | first fix plumbing |  | 2026-04-04 | 2026-04-05 | 1
181 | first fix plumbing |  | 2026-04-11 | 2026-04-12 | 1
181 | first fix plumbing |  | 2026-04-18 | 2026-04-19 | 1
181 | first fix plumbing |  | 2026-04-25 | 2026-04-26 | 1
181 | first fix plumbing |  | 2026-05-01 | 2026-05-02 | 1
181 | first fix plumbing |  | 2026-05-08 | 2026-05-09 | 1
181 | first fix plumbing |  | 2026-05-15 | 2026-05-16 | 1
181 | first fix plumbing |  | 2026-05-22 | 2026-05-23 | 1
181 | first fix plumbing |  | 2026-05-29 | 2026-05-30 | 1
181 | first fix plumbing |  | 2026-06-06 | 2026-06-07 | 1
181 | first fix plumbing |  | 2026-06-13 | 2026-06-14 | 1
181 | first fix plumbing |  | 2026-06-20 | 2026-06-21 | 1
182 | SVP & RWP install |  | 2025-12-07 | 2025-12-11 | 4
182 | SVP & RWP install |  | 2025-12-13 | 2025-12-16 | 2
182 | SVP & RWP install |  | 2025-12-19 | 2025-12-24 | 4
182 | SVP & RWP install |  | 2025-12-26 | 2025-12-29 | 2
182 | SVP & RWP install |  | 2026-01-05 | 2026-01-06 | 2
182 | SVP & RWP install |  | 2026-01-11 | 2026-01-13 | 2
182 | SVP & RWP install |  | 2026-01-19 | 2026-01-20 | 2
182 | SVP & RWP install |  | 2026-01-26 | 2026-03-03 | 27
182 | SVP & RWP install |  | 2026-03-06 | 2026-03-07 | 1
182 | SVP & RWP install |  | 2026-03-13 | 2026-03-14 | 1
182 | SVP & RWP install |  | 2026-03-20 | 2026-03-21 | 1
182 | SVP & RWP install |  | 2026-03-27 | 2026-03-28 | 1
182 | SVP & RWP install |  | 2026-04-04 | 2026-04-05 | 1
182 | SVP & RWP install |  | 2026-04-11 | 2026-04-12 | 1
182 | SVP & RWP install |  | 2026-04-18 | 2026-04-19 | 1
182 | SVP & RWP install |  | 2026-04-25 | 2026-04-26 | 1
182 | SVP & RWP install |  | 2026-05-01 | 2026-05-02 | 1
182 | SVP & RWP install |  | 2026-05-08 | 2026-05-09 | 1
182 | SVP & RWP install |  | 2026-05-15 | 2026-05-16 | 1
182 | SVP & RWP install |  | 2026-05-22 | 2026-05-23 | 1
182 | SVP & RWP install |  | 2026-05-29 | 2026-05-30 | 1
182 | SVP & RWP install |  | 2026-06-06 | 2026-06-07 | 1
182 | SVP & RWP install |  | 2026-06-13 | 2026-06-14 | 1
182 | SVP & RWP install |  | 2026-06-20 | 2026-06-21 | 1
183 | Firestop to RWP & SVP |  | 2025-12-07 | 2025-12-11 | 4
183 | Firestop to RWP & SVP |  | 2025-12-13 | 2025-12-16 | 2
183 | Firestop to RWP & SVP |  | 2025-12-19 | 2025-12-24 | 4
183 | Firestop to RWP & SVP |  | 2025-12-26 | 2025-12-29 | 2
183 | Firestop to RWP & SVP |  | 2026-01-05 | 2026-01-06 | 2
183 | Firestop to RWP & SVP |  | 2026-01-11 | 2026-01-13 | 2
183 | Firestop to RWP & SVP |  | 2026-01-19 | 2026-01-21 | 3
183 | Firestop to RWP & SVP |  | 2026-01-25 | 2026-03-03 | 27
183 | Firestop to RWP & SVP |  | 2026-03-06 | 2026-03-07 | 1
183 | Firestop to RWP & SVP |  | 2026-03-13 | 2026-03-14 | 1
183 | Firestop to RWP & SVP |  | 2026-03-20 | 2026-03-21 | 1
183 | Firestop to RWP & SVP |  | 2026-03-27 | 2026-03-28 | 1
183 | Firestop to RWP & SVP |  | 2026-04-04 | 2026-04-05 | 1
183 | Firestop to RWP & SVP |  | 2026-04-11 | 2026-04-12 | 1
183 | Firestop to RWP & SVP |  | 2026-04-18 | 2026-04-19 | 1
183 | Firestop to RWP & SVP |  | 2026-04-25 | 2026-04-26 | 1
183 | Firestop to RWP & SVP |  | 2026-05-01 | 2026-05-02 | 1
183 | Firestop to RWP & SVP |  | 2026-05-08 | 2026-05-09 | 1
183 | Firestop to RWP & SVP |  | 2026-05-15 | 2026-05-16 | 1
183 | Firestop to RWP & SVP |  | 2026-05-22 | 2026-05-23 | 1
183 | Firestop to RWP & SVP |  | 2026-05-29 | 2026-05-30 | 1
183 | Firestop to RWP & SVP |  | 2026-06-06 | 2026-06-07 | 1
183 | Firestop to RWP & SVP |  | 2026-06-13 | 2026-06-14 | 1
183 | Firestop to RWP & SVP |  | 2026-06-20 | 2026-06-21 | 1
184 | CONTROL POINT 2 (CP2) |  | 2025-12-07 | 2025-12-16 | 7
184 | CONTROL POINT 2 (CP2) |  | 2025-12-19 | 2025-12-24 | 4
184 | CONTROL POINT 2 (CP2) |  | 2025-12-26 | 2025-12-29 | 2
184 | CONTROL POINT 2 (CP2) |  | 2026-01-05 | 2026-01-06 | 2
184 | CONTROL POINT 2 (CP2) |  | 2026-01-11 | 2026-01-13 | 2
184 | CONTROL POINT 2 (CP2) |  | 2026-01-19 | 2026-03-03 | 32
184 | CONTROL POINT 2 (CP2) |  | 2026-03-06 | 2026-03-07 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-03-13 | 2026-03-14 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-03-20 | 2026-03-21 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-03-27 | 2026-03-28 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-04-04 | 2026-04-05 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-04-11 | 2026-04-12 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-04-18 | 2026-04-19 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-04-25 | 2026-04-26 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-05-01 | 2026-05-02 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-05-08 | 2026-05-09 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-05-15 | 2026-05-16 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-05-22 | 2026-05-23 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-05-29 | 2026-05-30 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-06-06 | 2026-06-07 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-06-13 | 2026-06-14 | 1
184 | CONTROL POINT 2 (CP2) |  | 2026-06-20 | 2026-06-21 | 1
185 | Wall void closure checklist sign off |  | 2025-12-07 | 2025-12-16 | 7
185 | Wall void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
185 | Wall void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
185 | Wall void closure checklist sign off |  | 2026-01-05 | 2026-01-06 | 2
185 | Wall void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
185 | Wall void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
185 | Wall void closure checklist sign off |  | 2026-01-25 | 2026-03-03 | 27
185 | Wall void closure checklist sign off |  | 2026-03-06 | 2026-03-07 | 1
185 | Wall void closure checklist sign off |  | 2026-03-13 | 2026-03-14 | 1
185 | Wall void closure checklist sign off |  | 2026-03-20 | 2026-03-21 | 1
185 | Wall void closure checklist sign off |  | 2026-03-27 | 2026-03-28 | 1
185 | Wall void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
185 | Wall void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
185 | Wall void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
185 | Wall void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
185 | Wall void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
185 | Wall void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
185 | Wall void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
185 | Wall void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
185 | Wall void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
185 | Wall void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
185 | Wall void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
185 | Wall void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
186 | 2nd fix Partitions - insulation and board |  | 2025-12-07 | 2025-12-16 | 7
186 | 2nd fix Partitions - insulation and board |  | 2025-12-19 | 2025-12-24 | 4
186 | 2nd fix Partitions - insulation and board |  | 2025-12-26 | 2025-12-29 | 2
186 | 2nd fix Partitions - insulation and board |  | 2026-01-05 | 2026-01-06 | 2
186 | 2nd fix Partitions - insulation and board |  | 2026-01-11 | 2026-01-13 | 2
186 | 2nd fix Partitions - insulation and board |  | 2026-01-19 | 2026-01-21 | 3
186 | 2nd fix Partitions - insulation and board |  | 2026-01-25 | 2026-03-03 | 27
186 | 2nd fix Partitions - insulation and board |  | 2026-03-06 | 2026-03-07 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-03-13 | 2026-03-14 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-03-20 | 2026-03-21 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-03-27 | 2026-03-28 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-04-04 | 2026-04-05 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-04-11 | 2026-04-12 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-04-18 | 2026-04-19 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-04-25 | 2026-04-26 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-05-01 | 2026-05-02 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-05-08 | 2026-05-09 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-05-15 | 2026-05-16 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-05-22 | 2026-05-23 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-05-29 | 2026-05-30 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-06-06 | 2026-06-07 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-06-13 | 2026-06-14 | 1
186 | 2nd fix Partitions - insulation and board |  | 2026-06-20 | 2026-06-21 | 1
187 | Install Vents/ducts |  | 2025-12-07 | 2025-12-16 | 7
187 | Install Vents/ducts |  | 2025-12-19 | 2025-12-24 | 4
187 | Install Vents/ducts |  | 2025-12-26 | 2025-12-29 | 2
187 | Install Vents/ducts |  | 2026-01-05 | 2026-01-06 | 2
187 | Install Vents/ducts |  | 2026-01-11 | 2026-01-13 | 2
187 | Install Vents/ducts |  | 2026-01-19 | 2026-01-21 | 3
187 | Install Vents/ducts |  | 2026-01-25 | 2026-04-01 | 48
187 | Install Vents/ducts |  | 2026-04-04 | 2026-04-05 | 1
187 | Install Vents/ducts |  | 2026-04-11 | 2026-04-12 | 1
187 | Install Vents/ducts |  | 2026-04-18 | 2026-04-19 | 1
187 | Install Vents/ducts |  | 2026-04-25 | 2026-04-26 | 1
187 | Install Vents/ducts |  | 2026-05-01 | 2026-05-02 | 1
187 | Install Vents/ducts |  | 2026-05-08 | 2026-05-09 | 1
187 | Install Vents/ducts |  | 2026-05-15 | 2026-05-16 | 1
187 | Install Vents/ducts |  | 2026-05-22 | 2026-05-23 | 1
187 | Install Vents/ducts |  | 2026-05-29 | 2026-05-30 | 1
187 | Install Vents/ducts |  | 2026-06-06 | 2026-06-07 | 1
187 | Install Vents/ducts |  | 2026-06-13 | 2026-06-14 | 1
187 | Install Vents/ducts |  | 2026-06-20 | 2026-06-21 | 1
188 | CONTROL POINT 3 (CP3) |  | 2025-12-07 | 2025-12-16 | 7
188 | CONTROL POINT 3 (CP3) |  | 2025-12-19 | 2025-12-29 | 7
188 | CONTROL POINT 3 (CP3) |  | 2026-01-05 | 2026-01-06 | 2
188 | CONTROL POINT 3 (CP3) |  | 2026-01-11 | 2026-01-13 | 2
188 | CONTROL POINT 3 (CP3) |  | 2026-01-19 | 2026-01-21 | 3
188 | CONTROL POINT 3 (CP3) |  | 2026-01-25 | 2026-04-01 | 48
188 | CONTROL POINT 3 (CP3) |  | 2026-04-04 | 2026-04-05 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-04-11 | 2026-04-12 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-04-18 | 2026-04-19 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-04-25 | 2026-04-26 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-05-01 | 2026-05-02 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-05-08 | 2026-05-09 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-05-15 | 2026-05-16 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-05-22 | 2026-05-23 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-05-29 | 2026-05-30 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-06-06 | 2026-06-07 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-06-13 | 2026-06-14 | 1
188 | CONTROL POINT 3 (CP3) |  | 2026-06-20 | 2026-06-21 | 1
189 | Ceiling void closure checklist sign off |  | 2025-12-07 | 2025-12-16 | 7
189 | Ceiling void closure checklist sign off |  | 2025-12-19 | 2025-12-29 | 7
189 | Ceiling void closure checklist sign off |  | 2026-01-05 | 2026-01-13 | 7
189 | Ceiling void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
189 | Ceiling void closure checklist sign off |  | 2026-01-25 | 2026-04-01 | 48
189 | Ceiling void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
189 | Ceiling void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
189 | Ceiling void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
189 | Ceiling void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
189 | Ceiling void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
189 | Ceiling void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
189 | Ceiling void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
189 | Ceiling void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
189 | Ceiling void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
189 | Ceiling void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
189 | Ceiling void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
189 | Ceiling void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
190 | Ceilings metal only |  | 2025-12-07 | 2025-12-16 | 7
190 | Ceilings metal only |  | 2025-12-19 | 2025-12-29 | 7
190 | Ceilings metal only |  | 2026-01-05 | 2026-01-13 | 7
190 | Ceilings metal only |  | 2026-01-19 | 2026-01-21 | 3
190 | Ceilings metal only |  | 2026-01-25 | 2026-04-01 | 48
190 | Ceilings metal only |  | 2026-04-04 | 2026-04-05 | 1
190 | Ceilings metal only |  | 2026-04-11 | 2026-04-12 | 1
190 | Ceilings metal only |  | 2026-04-18 | 2026-04-19 | 1
190 | Ceilings metal only |  | 2026-04-25 | 2026-04-26 | 1
190 | Ceilings metal only |  | 2026-05-01 | 2026-05-02 | 1
190 | Ceilings metal only |  | 2026-05-08 | 2026-05-09 | 1
190 | Ceilings metal only |  | 2026-05-15 | 2026-05-16 | 1
190 | Ceilings metal only |  | 2026-05-22 | 2026-05-23 | 1
190 | Ceilings metal only |  | 2026-05-29 | 2026-05-30 | 1
190 | Ceilings metal only |  | 2026-06-06 | 2026-06-07 | 1
190 | Ceilings metal only |  | 2026-06-13 | 2026-06-14 | 1
190 | Ceilings metal only |  | 2026-06-20 | 2026-06-21 | 1
191 | Sprinkler 1st fix & test |  | 2025-12-07 | 2025-12-11 | 4
191 | Sprinkler 1st fix & test |  | 2025-12-13 | 2025-12-16 | 2
191 | Sprinkler 1st fix & test |  | 2025-12-19 | 2025-12-29 | 7
191 | Sprinkler 1st fix & test |  | 2026-01-05 | 2026-01-13 | 7
191 | Sprinkler 1st fix & test |  | 2026-01-19 | 2026-01-21 | 3
191 | Sprinkler 1st fix & test |  | 2026-01-25 | 2026-04-01 | 48
191 | Sprinkler 1st fix & test |  | 2026-04-04 | 2026-04-05 | 1
191 | Sprinkler 1st fix & test |  | 2026-04-11 | 2026-04-12 | 1
191 | Sprinkler 1st fix & test |  | 2026-04-18 | 2026-04-19 | 1
191 | Sprinkler 1st fix & test |  | 2026-04-25 | 2026-04-26 | 1
191 | Sprinkler 1st fix & test |  | 2026-05-01 | 2026-05-02 | 1
191 | Sprinkler 1st fix & test |  | 2026-05-08 | 2026-05-09 | 1
191 | Sprinkler 1st fix & test |  | 2026-05-15 | 2026-05-16 | 1
191 | Sprinkler 1st fix & test |  | 2026-05-22 | 2026-05-23 | 1
191 | Sprinkler 1st fix & test |  | 2026-05-29 | 2026-05-30 | 1
191 | Sprinkler 1st fix & test |  | 2026-06-06 | 2026-06-07 | 1
191 | Sprinkler 1st fix & test |  | 2026-06-13 | 2026-06-14 | 1
191 | Sprinkler 1st fix & test |  | 2026-06-20 | 2026-06-21 | 1
192 | Ceilings - board (cut holes for lights) |  | 2025-12-07 | 2025-12-11 | 4
192 | Ceilings - board (cut holes for lights) |  | 2025-12-13 | 2025-12-29 | 11
192 | Ceilings - board (cut holes for lights) |  | 2026-01-05 | 2026-01-13 | 7
192 | Ceilings - board (cut holes for lights) |  | 2026-01-19 | 2026-01-21 | 3
192 | Ceilings - board (cut holes for lights) |  | 2026-01-25 | 2026-04-01 | 48
192 | Ceilings - board (cut holes for lights) |  | 2026-04-04 | 2026-04-05 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-04-11 | 2026-04-12 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-04-18 | 2026-04-19 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-04-25 | 2026-04-26 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-05-01 | 2026-05-02 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-05-08 | 2026-05-09 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-05-15 | 2026-05-16 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-05-22 | 2026-05-23 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-05-29 | 2026-05-30 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-06-06 | 2026-06-07 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-06-13 | 2026-06-14 | 1
192 | Ceilings - board (cut holes for lights) |  | 2026-06-20 | 2026-06-21 | 1
193 | Plaster spray |  | 2025-12-07 | 2025-12-11 | 4
193 | Plaster spray |  | 2025-12-13 | 2025-12-29 | 11
193 | Plaster spray |  | 2026-01-05 | 2026-01-13 | 7
193 | Plaster spray |  | 2026-01-19 | 2026-04-01 | 53
193 | Plaster spray |  | 2026-04-04 | 2026-04-05 | 1
193 | Plaster spray |  | 2026-04-11 | 2026-04-12 | 1
193 | Plaster spray |  | 2026-04-18 | 2026-04-19 | 1
193 | Plaster spray |  | 2026-04-25 | 2026-04-26 | 1
193 | Plaster spray |  | 2026-05-01 | 2026-05-02 | 1
193 | Plaster spray |  | 2026-05-08 | 2026-05-09 | 1
193 | Plaster spray |  | 2026-05-15 | 2026-05-16 | 1
193 | Plaster spray |  | 2026-05-22 | 2026-05-23 | 1
193 | Plaster spray |  | 2026-05-29 | 2026-05-30 | 1
193 | Plaster spray |  | 2026-06-06 | 2026-06-07 | 1
193 | Plaster spray |  | 2026-06-13 | 2026-06-14 | 1
193 | Plaster spray |  | 2026-06-20 | 2026-06-21 | 1
194 | Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-11 | 4
194 | Levveling screed /smoothing compound |  | 2025-12-13 | 2025-12-16 | 2
194 | Levveling screed /smoothing compound |  | 2025-12-19 | 2025-12-24 | 4
194 | Levveling screed /smoothing compound |  | 2025-12-26 | 2025-12-29 | 2
194 | Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-06 | 2
194 | Levveling screed /smoothing compound |  | 2026-01-11 | 2026-01-13 | 2
194 | Levveling screed /smoothing compound |  | 2026-01-19 | 2026-04-01 | 53
194 | Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
194 | Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
194 | Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
194 | Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
194 | Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
194 | Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
194 | Levveling screed /smoothing compound |  | 2026-05-15 | 2026-05-16 | 1
194 | Levveling screed /smoothing compound |  | 2026-05-22 | 2026-05-23 | 1
194 | Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
194 | Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
194 | Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
194 | Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
195 | Drying out |  | 2025-12-07 | 2025-12-11 | 4
195 | Drying out |  | 2025-12-13 | 2025-12-16 | 2
195 | Drying out |  | 2025-12-19 | 2025-12-24 | 4
195 | Drying out |  | 2025-12-26 | 2025-12-29 | 2
195 | Drying out |  | 2026-01-05 | 2026-01-06 | 2
195 | Drying out |  | 2026-01-11 | 2026-01-13 | 2
195 | Drying out |  | 2026-01-19 | 2026-04-01 | 53
195 | Drying out |  | 2026-04-04 | 2026-04-05 | 1
195 | Drying out |  | 2026-04-11 | 2026-04-12 | 1
195 | Drying out |  | 2026-04-18 | 2026-04-19 | 1
195 | Drying out |  | 2026-04-25 | 2026-04-26 | 1
195 | Drying out |  | 2026-05-01 | 2026-05-02 | 1
195 | Drying out |  | 2026-05-08 | 2026-05-09 | 1
195 | Drying out |  | 2026-05-15 | 2026-05-16 | 1
195 | Drying out |  | 2026-05-22 | 2026-05-23 | 1
195 | Drying out |  | 2026-05-29 | 2026-05-30 | 1
195 | Drying out |  | 2026-06-06 | 2026-06-07 | 1
195 | Drying out |  | 2026-06-13 | 2026-06-14 | 1
195 | Drying out |  | 2026-06-20 | 2026-06-21 | 1
196 | Mist coat |  | 2025-12-07 | 2025-12-11 | 4
196 | Mist coat |  | 2025-12-13 | 2025-12-16 | 2
196 | Mist coat |  | 2025-12-19 | 2025-12-24 | 4
196 | Mist coat |  | 2025-12-26 | 2025-12-29 | 2
196 | Mist coat |  | 2026-01-05 | 2026-01-06 | 2
196 | Mist coat |  | 2026-01-11 | 2026-01-13 | 2
196 | Mist coat |  | 2026-01-19 | 2026-01-21 | 3
196 | Mist coat |  | 2026-01-25 | 2026-04-01 | 48
196 | Mist coat |  | 2026-04-04 | 2026-04-05 | 1
196 | Mist coat |  | 2026-04-11 | 2026-04-12 | 1
196 | Mist coat |  | 2026-04-18 | 2026-04-19 | 1
196 | Mist coat |  | 2026-04-25 | 2026-04-26 | 1
196 | Mist coat |  | 2026-05-01 | 2026-05-02 | 1
196 | Mist coat |  | 2026-05-08 | 2026-05-09 | 1
196 | Mist coat |  | 2026-05-15 | 2026-05-16 | 1
196 | Mist coat |  | 2026-05-22 | 2026-05-23 | 1
196 | Mist coat |  | 2026-05-29 | 2026-05-30 | 1
196 | Mist coat |  | 2026-06-06 | 2026-06-07 | 1
196 | Mist coat |  | 2026-06-13 | 2026-06-14 | 1
196 | Mist coat |  | 2026-06-20 | 2026-06-21 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-11 | 4
197 | Kitchen 1st fix,units tops & appliances |  | 2025-12-13 | 2025-12-16 | 2
197 | Kitchen 1st fix,units tops & appliances |  | 2025-12-19 | 2025-12-24 | 4
197 | Kitchen 1st fix,units tops & appliances |  | 2025-12-26 | 2025-12-29 | 2
197 | Kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-06 | 2
197 | Kitchen 1st fix,units tops & appliances |  | 2026-01-11 | 2026-01-13 | 2
197 | Kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-21 | 3
197 | Kitchen 1st fix,units tops & appliances |  | 2026-01-25 | 2026-04-01 | 48
197 | Kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-05 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-05-15 | 2026-05-16 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-05-22 | 2026-05-23 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
197 | Kitchen 1st fix,units tops & appliances |  | 2026-06-20 | 2026-06-21 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-11 | 4
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-13 | 2025-12-16 | 2
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-19 | 2025-12-24 | 4
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-26 | 2025-12-29 | 2
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-05 | 2026-01-06 | 2
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-11 | 2026-01-13 | 2
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-19 | 2026-01-21 | 3
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-25 | 2026-04-01 | 48
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-04 | 2026-04-05 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-18 | 2026-04-19 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-25 | 2026-04-26 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-01 | 2026-05-02 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-15 | 2026-05-16 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-22 | 2026-05-23 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-29 | 2026-05-30 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-06 | 2026-06-07 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-13 | 2026-06-14 | 1
198 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-20 | 2026-06-21 | 1
| Floor and wall tiling |  | 2025-12-07 | 2025-12-11 | 4
| Floor and wall tiling |  | 2025-12-13 | 2025-12-16 | 2
| Floor and wall tiling |  | 2025-12-19 | 2025-12-24 | 4
| Floor and wall tiling |  | 2025-12-26 | 2025-12-29 | 2
| Floor and wall tiling |  | 2026-01-05 | 2026-01-06 | 2
| Floor and wall tiling |  | 2026-01-11 | 2026-01-13 | 2
| Floor and wall tiling |  | 2026-01-19 | 2026-01-21 | 3
| Floor and wall tiling |  | 2026-01-25 | 2026-04-01 | 48
| Floor and wall tiling |  | 2026-04-04 | 2026-04-05 | 1
| Floor and wall tiling |  | 2026-04-11 | 2026-04-12 | 1
| Floor and wall tiling |  | 2026-04-18 | 2026-04-19 | 1
| Floor and wall tiling |  | 2026-04-25 | 2026-04-26 | 1
| Floor and wall tiling |  | 2026-05-01 | 2026-05-02 | 1
| Floor and wall tiling |  | 2026-05-08 | 2026-05-09 | 1
| Floor and wall tiling |  | 2026-05-15 | 2026-05-16 | 1
| Floor and wall tiling |  | 2026-05-22 | 2026-05-23 | 1
| Floor and wall tiling |  | 2026-05-29 | 2026-05-30 | 1
| Floor and wall tiling |  | 2026-06-06 | 2026-06-07 | 1
| Floor and wall tiling |  | 2026-06-13 | 2026-06-14 | 1
| Floor and wall tiling |  | 2026-06-20 | 2026-06-21 | 1
199 | Control point 4 CP 4 |  | 2025-12-07 | 2025-12-11 | 4
199 | Control point 4 CP 4 |  | 2025-12-13 | 2025-12-16 | 2
199 | Control point 4 CP 4 |  | 2025-12-19 | 2025-12-24 | 4
199 | Control point 4 CP 4 |  | 2025-12-26 | 2025-12-29 | 2
199 | Control point 4 CP 4 |  | 2026-01-05 | 2026-01-06 | 2
199 | Control point 4 CP 4 |  | 2026-01-11 | 2026-01-13 | 2
199 | Control point 4 CP 4 |  | 2026-01-19 | 2026-01-21 | 3
199 | Control point 4 CP 4 |  | 2026-01-25 | 2026-04-01 | 48
199 | Control point 4 CP 4 |  | 2026-04-04 | 2026-04-05 | 1
199 | Control point 4 CP 4 |  | 2026-04-11 | 2026-04-12 | 1
199 | Control point 4 CP 4 |  | 2026-04-18 | 2026-04-19 | 1
199 | Control point 4 CP 4 |  | 2026-04-25 | 2026-04-26 | 1
199 | Control point 4 CP 4 |  | 2026-05-01 | 2026-05-02 | 1
199 | Control point 4 CP 4 |  | 2026-05-08 | 2026-05-09 | 1
199 | Control point 4 CP 4 |  | 2026-05-15 | 2026-05-16 | 1
199 | Control point 4 CP 4 |  | 2026-05-22 | 2026-05-23 | 1
199 | Control point 4 CP 4 |  | 2026-05-29 | 2026-05-30 | 1
199 | Control point 4 CP 4 |  | 2026-06-06 | 2026-06-07 | 1
199 | Control point 4 CP 4 |  | 2026-06-13 | 2026-06-14 | 1
199 | Control point 4 CP 4 |  | 2026-06-20 | 2026-06-21 | 1
200 | service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-11 | 4
200 | service cupbaord -plywood flooring |  | 2025-12-13 | 2025-12-16 | 2
200 | service cupbaord -plywood flooring |  | 2025-12-19 | 2025-12-24 | 4
200 | service cupbaord -plywood flooring |  | 2025-12-26 | 2025-12-29 | 2
200 | service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-06 | 2
200 | service cupbaord -plywood flooring |  | 2026-01-11 | 2026-01-13 | 2
200 | service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-21 | 3
200 | service cupbaord -plywood flooring |  | 2026-01-25 | 2026-04-01 | 48
200 | service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
200 | service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
200 | service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
200 | service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
200 | service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
200 | service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
200 | service cupbaord -plywood flooring |  | 2026-05-15 | 2026-05-16 | 1
200 | service cupbaord -plywood flooring |  | 2026-05-22 | 2026-05-23 | 1
200 | service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
200 | service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
200 | service cupbaord -plywood flooring |  | 2026-06-13 | 2026-06-14 | 1
200 | service cupbaord -plywood flooring |  | 2026-06-20 | 2026-06-21 | 1
201 | service cupboard decoration |  | 2025-12-07 | 2025-12-11 | 4
201 | service cupboard decoration |  | 2025-12-13 | 2025-12-16 | 2
201 | service cupboard decoration |  | 2025-12-19 | 2025-12-24 | 4
201 | service cupboard decoration |  | 2025-12-26 | 2026-01-02 | 6
201 | service cupboard decoration |  | 2026-01-05 | 2026-01-06 | 2
201 | service cupboard decoration |  | 2026-01-11 | 2026-01-13 | 2
201 | service cupboard decoration |  | 2026-01-19 | 2026-01-21 | 3
201 | service cupboard decoration |  | 2026-01-25 | 2026-04-01 | 48
201 | service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
201 | service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
201 | service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
201 | service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
201 | service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
201 | service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
201 | service cupboard decoration |  | 2026-05-15 | 2026-05-16 | 1
201 | service cupboard decoration |  | 2026-05-22 | 2026-05-23 | 1
201 | service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
201 | service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
201 | service cupboard decoration |  | 2026-06-13 | 2026-06-14 | 1
201 | service cupboard decoration |  | 2026-06-20 | 2026-06-21 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-07 | 2025-12-11 | 4
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-13 | 2025-12-16 | 2
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-19 | 2025-12-24 | 4
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-26 | 2025-12-29 | 2
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-03 | 2026-01-09 | 5
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-11 | 2026-01-13 | 2
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-19 | 2026-01-20 | 2
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-25 | 2026-04-01 | 48
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-04 | 2026-04-05 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-11 | 2026-04-12 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-18 | 2026-04-19 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-25 | 2026-04-26 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-01 | 2026-05-02 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-08 | 2026-05-09 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-15 | 2026-05-16 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-22 | 2026-05-23 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-29 | 2026-05-30 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-06 | 2026-06-07 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-13 | 2026-06-14 | 1
202 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-20 | 2026-06-21 | 1
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-11 | 4
| Amtico flooring /Bathrooms |  | 2025-12-13 | 2025-12-16 | 2
| Amtico flooring /Bathrooms |  | 2025-12-19 | 2025-12-24 | 4
| Amtico flooring /Bathrooms |  | 2025-12-26 | 2025-12-29 | 2
| Amtico flooring /Bathrooms |  | 2026-01-03 | 2026-01-09 | 5
| Amtico flooring /Bathrooms |  | 2026-01-11 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-20 | 2
| Amtico flooring /Bathrooms |  | 2026-01-25 | 2026-04-01 | 48
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-15 | 2026-05-16 | 1
| Amtico flooring /Bathrooms |  | 2026-05-22 | 2026-05-23 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2026-06-13 | 2026-06-14 | 1
| Amtico flooring /Bathrooms |  | 2026-06-20 | 2026-06-21 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-11 | 4
203 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-13 | 2025-12-16 | 2
203 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-19 | 2025-12-24 | 4
203 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-26 | 2025-12-29 | 2
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-07 | 3
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-11 | 2026-01-13 | 2
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-20 | 2
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-23 | 2026-04-01 | 49
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-05 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-15 | 2026-05-16 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-22 | 2026-05-23 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-13 | 2026-06-14 | 1
203 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-20 | 2026-06-21 | 1
| Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-11 | 4
| Electrical 2nd fix & live testing |  | 2025-12-13 | 2025-12-16 | 2
| Electrical 2nd fix & live testing |  | 2025-12-19 | 2025-12-24 | 4
| Electrical 2nd fix & live testing |  | 2025-12-26 | 2025-12-29 | 2
| Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-07 | 3
| Electrical 2nd fix & live testing |  | 2026-01-11 | 2026-01-13 | 2
| Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-04-01 | 53
| Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
| Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
| Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
| Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
| Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
| Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
| Electrical 2nd fix & live testing |  | 2026-05-15 | 2026-05-16 | 1
| Electrical 2nd fix & live testing |  | 2026-05-22 | 2026-05-23 | 1
| Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
| Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
| Electrical 2nd fix & live testing |  | 2026-06-13 | 2026-06-14 | 1
| Electrical 2nd fix & live testing |  | 2026-06-20 | 2026-06-21 | 1
204 | Builders clean |  | 2025-12-07 | 2025-12-11 | 4
204 | Builders clean |  | 2025-12-13 | 2025-12-16 | 2
204 | Builders clean |  | 2025-12-19 | 2025-12-24 | 4
204 | Builders clean |  | 2025-12-26 | 2025-12-29 | 2
204 | Builders clean |  | 2026-01-05 | 2026-01-07 | 3
204 | Builders clean |  | 2026-01-12 | 2026-01-13 | 2
204 | Builders clean |  | 2026-01-16 | 2026-04-01 | 54
204 | Builders clean |  | 2026-04-04 | 2026-04-05 | 1
204 | Builders clean |  | 2026-04-11 | 2026-04-12 | 1
204 | Builders clean |  | 2026-04-18 | 2026-04-19 | 1
204 | Builders clean |  | 2026-04-25 | 2026-04-26 | 1
204 | Builders clean |  | 2026-05-01 | 2026-05-02 | 1
204 | Builders clean |  | 2026-05-08 | 2026-05-09 | 1
204 | Builders clean |  | 2026-05-15 | 2026-05-16 | 1
204 | Builders clean |  | 2026-05-22 | 2026-05-23 | 1
204 | Builders clean |  | 2026-05-29 | 2026-05-30 | 1
204 | Builders clean |  | 2026-06-06 | 2026-06-07 | 1
204 | Builders clean |  | 2026-06-13 | 2026-06-14 | 1
204 | Builders clean |  | 2026-06-20 | 2026-06-21 | 1
205 | Pre -dec -snagging |  | 2025-12-07 | 2025-12-11 | 4
205 | Pre -dec -snagging |  | 2025-12-13 | 2025-12-16 | 2
205 | Pre -dec -snagging |  | 2025-12-19 | 2025-12-24 | 4
205 | Pre -dec -snagging |  | 2025-12-26 | 2025-12-29 | 2
205 | Pre -dec -snagging |  | 2026-01-05 | 2026-01-07 | 3
205 | Pre -dec -snagging |  | 2026-01-11 | 2026-01-13 | 2
205 | Pre -dec -snagging |  | 2026-01-17 | 2026-01-23 | 5
205 | Pre -dec -snagging |  | 2026-01-25 | 2026-04-01 | 48
205 | Pre -dec -snagging |  | 2026-04-04 | 2026-04-05 | 1
205 | Pre -dec -snagging |  | 2026-04-11 | 2026-04-12 | 1
205 | Pre -dec -snagging |  | 2026-04-18 | 2026-04-19 | 1
205 | Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
205 | Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
205 | Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
205 | Pre -dec -snagging |  | 2026-05-15 | 2026-05-16 | 1
205 | Pre -dec -snagging |  | 2026-05-22 | 2026-05-23 | 1
205 | Pre -dec -snagging |  | 2026-05-29 | 2026-05-30 | 1
205 | Pre -dec -snagging |  | 2026-06-06 | 2026-06-07 | 1
205 | Pre -dec -snagging |  | 2026-06-13 | 2026-06-14 | 1
205 | Pre -dec -snagging |  | 2026-06-20 | 2026-06-21 | 1
206 | Decoration |  | 2025-12-07 | 2025-12-11 | 4
206 | Decoration |  | 2025-12-13 | 2025-12-16 | 2
206 | Decoration |  | 2025-12-19 | 2025-12-24 | 4
206 | Decoration |  | 2025-12-26 | 2025-12-29 | 2
206 | Decoration |  | 2026-01-05 | 2026-01-07 | 3
206 | Decoration |  | 2026-01-11 | 2026-01-13 | 2
206 | Decoration |  | 2026-01-19 | 2026-01-21 | 3
206 | Decoration |  | 2026-01-25 | 2026-04-01 | 48
206 | Decoration |  | 2026-04-04 | 2026-04-05 | 1
206 | Decoration |  | 2026-04-11 | 2026-04-12 | 1
206 | Decoration |  | 2026-04-18 | 2026-04-19 | 1
206 | Decoration |  | 2026-04-25 | 2026-04-26 | 1
206 | Decoration |  | 2026-05-01 | 2026-05-02 | 1
206 | Decoration |  | 2026-05-08 | 2026-05-09 | 1
206 | Decoration |  | 2026-05-12 | 2026-05-18 | 5
206 | Decoration |  | 2026-05-22 | 2026-05-23 | 1
206 | Decoration |  | 2026-05-29 | 2026-05-30 | 1
206 | Decoration |  | 2026-06-06 | 2026-06-07 | 1
206 | Decoration |  | 2026-06-13 | 2026-06-14 | 1
206 | Decoration |  | 2026-06-20 | 2026-06-21 | 1
207 | Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-11 | 4
207 | Amtico flooring /Carpets |  | 2025-12-13 | 2025-12-16 | 2
207 | Amtico flooring /Carpets |  | 2025-12-19 | 2025-12-24 | 4
207 | Amtico flooring /Carpets |  | 2025-12-26 | 2025-12-29 | 2
207 | Amtico flooring /Carpets |  | 2026-01-05 | 2026-01-07 | 3
207 | Amtico flooring /Carpets |  | 2026-01-11 | 2026-01-13 | 2
207 | Amtico flooring /Carpets |  | 2026-01-19 | 2026-01-21 | 3
207 | Amtico flooring /Carpets |  | 2026-01-25 | 2026-04-01 | 48
207 | Amtico flooring /Carpets |  | 2026-04-04 | 2026-04-05 | 1
207 | Amtico flooring /Carpets |  | 2026-04-11 | 2026-04-12 | 1
207 | Amtico flooring /Carpets |  | 2026-04-18 | 2026-04-19 | 1
207 | Amtico flooring /Carpets |  | 2026-04-25 | 2026-04-26 | 1
207 | Amtico flooring /Carpets |  | 2026-05-01 | 2026-05-02 | 1
207 | Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
207 | Amtico flooring /Carpets |  | 2026-05-15 | 2026-05-16 | 1
207 | Amtico flooring /Carpets |  | 2026-05-19 | 2026-05-23 | 4
207 | Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
207 | Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
207 | Amtico flooring /Carpets |  | 2026-06-13 | 2026-06-14 | 1
207 | Amtico flooring /Carpets |  | 2026-06-20 | 2026-06-21 | 1
208 | De snag all trades |  | 2025-12-07 | 2025-12-11 | 4
208 | De snag all trades |  | 2025-12-13 | 2025-12-16 | 2
208 | De snag all trades |  | 2025-12-19 | 2025-12-24 | 4
208 | De snag all trades |  | 2025-12-26 | 2025-12-29 | 2
208 | De snag all trades |  | 2026-01-05 | 2026-01-07 | 3
208 | De snag all trades |  | 2026-01-11 | 2026-01-13 | 2
208 | De snag all trades |  | 2026-01-19 | 2026-01-21 | 3
208 | De snag all trades |  | 2026-01-25 | 2026-04-01 | 48
208 | De snag all trades |  | 2026-04-04 | 2026-04-05 | 1
208 | De snag all trades |  | 2026-04-11 | 2026-04-12 | 1
208 | De snag all trades |  | 2026-04-18 | 2026-04-19 | 1
208 | De snag all trades |  | 2026-04-25 | 2026-04-26 | 1
208 | De snag all trades |  | 2026-05-01 | 2026-05-02 | 1
208 | De snag all trades |  | 2026-05-08 | 2026-05-09 | 1
208 | De snag all trades |  | 2026-05-15 | 2026-05-16 | 1
208 | De snag all trades |  | 2026-05-22 | 2026-05-30 | 6
208 | De snag all trades |  | 2026-06-06 | 2026-06-07 | 1
208 | De snag all trades |  | 2026-06-13 | 2026-06-14 | 1
208 | De snag all trades |  | 2026-06-20 | 2026-06-21 | 1
209 | Sparkle clean |  | 2025-12-07 | 2025-12-11 | 4
209 | Sparkle clean |  | 2025-12-13 | 2025-12-16 | 2
209 | Sparkle clean |  | 2025-12-19 | 2025-12-24 | 4
209 | Sparkle clean |  | 2025-12-26 | 2025-12-29 | 2
209 | Sparkle clean |  | 2026-01-05 | 2026-01-07 | 3
209 | Sparkle clean |  | 2026-01-11 | 2026-01-13 | 2
209 | Sparkle clean |  | 2026-01-19 | 2026-01-21 | 3
209 | Sparkle clean |  | 2026-01-25 | 2026-04-01 | 48
209 | Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
209 | Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
209 | Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
209 | Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
209 | Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
209 | Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
209 | Sparkle clean |  | 2026-05-15 | 2026-05-16 | 1
209 | Sparkle clean |  | 2026-05-22 | 2026-05-23 | 1
209 | Sparkle clean |  | 2026-05-29 | 2026-06-07 | 6
209 | Sparkle clean |  | 2026-06-13 | 2026-06-14 | 1
209 | Sparkle clean |  | 2026-06-20 | 2026-06-21 | 1
210 | Mastic |  | 2025-12-07 | 2025-12-11 | 4
210 | Mastic |  | 2025-12-13 | 2025-12-16 | 2
210 | Mastic |  | 2025-12-19 | 2025-12-24 | 4
210 | Mastic |  | 2025-12-26 | 2025-12-29 | 2
210 | Mastic |  | 2026-01-05 | 2026-01-07 | 3
210 | Mastic |  | 2026-01-11 | 2026-01-13 | 2
210 | Mastic |  | 2026-01-19 | 2026-01-21 | 3
210 | Mastic |  | 2026-01-25 | 2026-04-01 | 48
210 | Mastic |  | 2026-04-04 | 2026-04-05 | 1
210 | Mastic |  | 2026-04-11 | 2026-04-12 | 1
210 | Mastic |  | 2026-04-18 | 2026-04-19 | 1
210 | Mastic |  | 2026-04-25 | 2026-04-26 | 1
210 | Mastic |  | 2026-05-01 | 2026-05-02 | 1
210 | Mastic |  | 2026-05-08 | 2026-05-09 | 1
210 | Mastic |  | 2026-05-15 | 2026-05-16 | 1
210 | Mastic |  | 2026-05-22 | 2026-05-23 | 1
210 | Mastic |  | 2026-05-29 | 2026-05-30 | 1
210 | Mastic |  | 2026-06-06 | 2026-06-09 | 2
210 | Mastic |  | 2026-06-13 | 2026-06-14 | 1
210 | Mastic |  | 2026-06-20 | 2026-06-21 | 1
211 | Handover to client |  | 2025-12-07 | 2025-12-11 | 4
211 | Handover to client |  | 2025-12-13 | 2025-12-16 | 2
211 | Handover to client |  | 2025-12-19 | 2025-12-24 | 4
211 | Handover to client |  | 2025-12-26 | 2025-12-29 | 2
211 | Handover to client |  | 2026-01-05 | 2026-01-07 | 3
211 | Handover to client |  | 2026-01-11 | 2026-01-13 | 2
211 | Handover to client |  | 2026-01-19 | 2026-01-21 | 3
211 | Handover to client |  | 2026-01-25 | 2026-04-01 | 48
211 | Handover to client |  | 2026-04-04 | 2026-04-05 | 1
211 | Handover to client |  | 2026-04-11 | 2026-04-12 | 1
211 | Handover to client |  | 2026-04-18 | 2026-04-19 | 1
211 | Handover to client |  | 2026-04-25 | 2026-04-26 | 1
211 | Handover to client |  | 2026-05-01 | 2026-05-02 | 1
211 | Handover to client |  | 2026-05-08 | 2026-05-09 | 1
211 | Handover to client |  | 2026-05-15 | 2026-05-16 | 1
211 | Handover to client |  | 2026-05-22 | 2026-05-23 | 1
211 | Handover to client |  | 2026-05-29 | 2026-05-30 | 1
211 | Handover to client |  | 2026-06-06 | 2026-06-07 | 1
211 | Handover to client |  | 2026-06-13 | 2026-06-14 | 1
211 | Handover to client |  | 2026-06-20 | 2026-06-21 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2025-12-07 | 2025-12-11 | 4
212 | Level 7Apartment fit out -cluster 1 |  | 2025-12-13 | 2025-12-16 | 2
212 | Level 7Apartment fit out -cluster 1 |  | 2025-12-19 | 2025-12-24 | 4
212 | Level 7Apartment fit out -cluster 1 |  | 2025-12-26 | 2025-12-29 | 2
212 | Level 7Apartment fit out -cluster 1 |  | 2026-01-05 | 2026-01-07 | 3
212 | Level 7Apartment fit out -cluster 1 |  | 2026-01-11 | 2026-01-13 | 2
212 | Level 7Apartment fit out -cluster 1 |  | 2026-01-19 | 2026-01-21 | 3
212 | Level 7Apartment fit out -cluster 1 |  | 2026-01-25 | 2026-04-01 | 48
212 | Level 7Apartment fit out -cluster 1 |  | 2026-04-04 | 2026-04-05 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-04-11 | 2026-04-12 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-04-18 | 2026-04-19 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-04-25 | 2026-04-26 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-05-01 | 2026-05-02 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-05-08 | 2026-05-09 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-05-15 | 2026-05-16 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-05-22 | 2026-05-23 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-05-29 | 2026-05-30 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-06-06 | 2026-06-07 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-06-13 | 2026-06-14 | 1
212 | Level 7Apartment fit out -cluster 1 |  | 2026-06-20 | 2026-06-21 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2025-12-07 | 2025-12-11 | 4
213 | 1st fix electrical back boxes Edencroft |  | 2025-12-13 | 2025-12-16 | 2
213 | 1st fix electrical back boxes Edencroft |  | 2025-12-19 | 2025-12-24 | 4
213 | 1st fix electrical back boxes Edencroft |  | 2025-12-26 | 2025-12-29 | 2
213 | 1st fix electrical back boxes Edencroft |  | 2026-01-05 | 2026-01-07 | 3
213 | 1st fix electrical back boxes Edencroft |  | 2026-01-11 | 2026-01-13 | 2
213 | 1st fix electrical back boxes Edencroft |  | 2026-01-19 | 2026-01-21 | 3
213 | 1st fix electrical back boxes Edencroft |  | 2026-01-25 | 2026-04-01 | 48
213 | 1st fix electrical back boxes Edencroft |  | 2026-04-04 | 2026-04-05 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-04-11 | 2026-04-12 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-04-18 | 2026-04-19 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-04-25 | 2026-04-26 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-05-01 | 2026-05-02 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-05-08 | 2026-05-09 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-05-15 | 2026-05-16 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-05-22 | 2026-05-23 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-05-29 | 2026-05-30 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-06-06 | 2026-06-07 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-06-13 | 2026-06-14 | 1
213 | 1st fix electrical back boxes Edencroft |  | 2026-06-20 | 2026-06-21 | 1
214 | 1st fix partitions/pattreses one side |  | 2025-12-07 | 2025-12-11 | 4
214 | 1st fix partitions/pattreses one side |  | 2025-12-13 | 2025-12-16 | 2
214 | 1st fix partitions/pattreses one side |  | 2025-12-19 | 2025-12-24 | 4
214 | 1st fix partitions/pattreses one side |  | 2025-12-26 | 2025-12-29 | 2
214 | 1st fix partitions/pattreses one side |  | 2026-01-05 | 2026-01-07 | 3
214 | 1st fix partitions/pattreses one side |  | 2026-01-11 | 2026-01-13 | 2
214 | 1st fix partitions/pattreses one side |  | 2026-01-19 | 2026-01-21 | 3
214 | 1st fix partitions/pattreses one side |  | 2026-01-25 | 2026-04-01 | 48
214 | 1st fix partitions/pattreses one side |  | 2026-04-04 | 2026-04-05 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-04-11 | 2026-04-12 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-04-18 | 2026-04-19 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-04-25 | 2026-04-26 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-05-01 | 2026-05-02 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-05-08 | 2026-05-09 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-05-15 | 2026-05-16 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-05-22 | 2026-05-23 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-05-29 | 2026-05-30 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-06-06 | 2026-06-07 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-06-13 | 2026-06-14 | 1
214 | 1st fix partitions/pattreses one side |  | 2026-06-20 | 2026-06-21 | 1
215 | First fix wire -ceilings/walls |  | 2025-12-07 | 2025-12-11 | 4
215 | First fix wire -ceilings/walls |  | 2025-12-13 | 2025-12-16 | 2
215 | First fix wire -ceilings/walls |  | 2025-12-19 | 2025-12-24 | 4
215 | First fix wire -ceilings/walls |  | 2025-12-26 | 2025-12-29 | 2
215 | First fix wire -ceilings/walls |  | 2026-01-05 | 2026-01-07 | 3
215 | First fix wire -ceilings/walls |  | 2026-01-11 | 2026-01-13 | 2
215 | First fix wire -ceilings/walls |  | 2026-01-19 | 2026-01-21 | 3
215 | First fix wire -ceilings/walls |  | 2026-01-25 | 2026-04-01 | 48
215 | First fix wire -ceilings/walls |  | 2026-04-04 | 2026-04-05 | 1
215 | First fix wire -ceilings/walls |  | 2026-04-11 | 2026-04-12 | 1
215 | First fix wire -ceilings/walls |  | 2026-04-18 | 2026-04-19 | 1
215 | First fix wire -ceilings/walls |  | 2026-04-25 | 2026-04-26 | 1
215 | First fix wire -ceilings/walls |  | 2026-05-01 | 2026-05-02 | 1
215 | First fix wire -ceilings/walls |  | 2026-05-08 | 2026-05-09 | 1
215 | First fix wire -ceilings/walls |  | 2026-05-15 | 2026-05-16 | 1
215 | First fix wire -ceilings/walls |  | 2026-05-22 | 2026-05-23 | 1
215 | First fix wire -ceilings/walls |  | 2026-05-29 | 2026-05-30 | 1
215 | First fix wire -ceilings/walls |  | 2026-06-06 | 2026-06-07 | 1
215 | First fix wire -ceilings/walls |  | 2026-06-13 | 2026-06-14 | 1
215 | First fix wire -ceilings/walls |  | 2026-06-20 | 2026-06-21 | 1
216 | first fix plumbing |  | 2025-12-07 | 2025-12-11 | 4
216 | first fix plumbing |  | 2025-12-13 | 2025-12-16 | 2
216 | first fix plumbing |  | 2025-12-19 | 2025-12-24 | 4
216 | first fix plumbing |  | 2025-12-26 | 2025-12-29 | 2
216 | first fix plumbing |  | 2026-01-05 | 2026-01-07 | 3
216 | first fix plumbing |  | 2026-01-11 | 2026-01-13 | 2
216 | first fix plumbing |  | 2026-01-19 | 2026-01-21 | 3
216 | first fix plumbing |  | 2026-01-25 | 2026-04-01 | 48
216 | first fix plumbing |  | 2026-04-04 | 2026-04-05 | 1
216 | first fix plumbing |  | 2026-04-11 | 2026-04-12 | 1
216 | first fix plumbing |  | 2026-04-18 | 2026-04-19 | 1
216 | first fix plumbing |  | 2026-04-25 | 2026-04-26 | 1
216 | first fix plumbing |  | 2026-05-01 | 2026-05-02 | 1
216 | first fix plumbing |  | 2026-05-08 | 2026-05-09 | 1
216 | first fix plumbing |  | 2026-05-15 | 2026-05-16 | 1
216 | first fix plumbing |  | 2026-05-22 | 2026-05-23 | 1
216 | first fix plumbing |  | 2026-05-29 | 2026-05-30 | 1
216 | first fix plumbing |  | 2026-06-06 | 2026-06-07 | 1
216 | first fix plumbing |  | 2026-06-13 | 2026-06-14 | 1
216 | first fix plumbing |  | 2026-06-20 | 2026-06-21 | 1
217 | SVP & RWP install |  | 2025-12-07 | 2025-12-11 | 4
217 | SVP & RWP install |  | 2025-12-13 | 2025-12-16 | 2
217 | SVP & RWP install |  | 2025-12-19 | 2025-12-24 | 4
217 | SVP & RWP install |  | 2025-12-26 | 2025-12-29 | 2
217 | SVP & RWP install |  | 2026-01-05 | 2026-01-07 | 3
217 | SVP & RWP install |  | 2026-01-11 | 2026-01-13 | 2
217 | SVP & RWP install |  | 2026-01-19 | 2026-01-21 | 3
217 | SVP & RWP install |  | 2026-01-25 | 2026-04-01 | 48
217 | SVP & RWP install |  | 2026-04-04 | 2026-04-05 | 1
217 | SVP & RWP install |  | 2026-04-11 | 2026-04-12 | 1
217 | SVP & RWP install |  | 2026-04-18 | 2026-04-19 | 1
217 | SVP & RWP install |  | 2026-04-25 | 2026-04-26 | 1
217 | SVP & RWP install |  | 2026-05-01 | 2026-05-02 | 1
217 | SVP & RWP install |  | 2026-05-08 | 2026-05-09 | 1
217 | SVP & RWP install |  | 2026-05-15 | 2026-05-16 | 1
217 | SVP & RWP install |  | 2026-05-22 | 2026-05-23 | 1
217 | SVP & RWP install |  | 2026-05-29 | 2026-05-30 | 1
217 | SVP & RWP install |  | 2026-06-06 | 2026-06-07 | 1
217 | SVP & RWP install |  | 2026-06-13 | 2026-06-14 | 1
217 | SVP & RWP install |  | 2026-06-20 | 2026-06-21 | 1
218 | Firestop to RWP & SVP |  | 2025-12-07 | 2025-12-11 | 4
218 | Firestop to RWP & SVP |  | 2025-12-13 | 2025-12-16 | 2
218 | Firestop to RWP & SVP |  | 2025-12-19 | 2025-12-24 | 4
218 | Firestop to RWP & SVP |  | 2025-12-26 | 2025-12-29 | 2
218 | Firestop to RWP & SVP |  | 2026-01-05 | 2026-01-07 | 3
218 | Firestop to RWP & SVP |  | 2026-01-11 | 2026-01-13 | 2
218 | Firestop to RWP & SVP |  | 2026-01-19 | 2026-01-21 | 3
218 | Firestop to RWP & SVP |  | 2026-01-25 | 2026-04-01 | 48
218 | Firestop to RWP & SVP |  | 2026-04-04 | 2026-04-05 | 1
218 | Firestop to RWP & SVP |  | 2026-04-11 | 2026-04-12 | 1
218 | Firestop to RWP & SVP |  | 2026-04-18 | 2026-04-19 | 1
218 | Firestop to RWP & SVP |  | 2026-04-25 | 2026-04-26 | 1
218 | Firestop to RWP & SVP |  | 2026-05-01 | 2026-05-02 | 1
218 | Firestop to RWP & SVP |  | 2026-05-08 | 2026-05-09 | 1
218 | Firestop to RWP & SVP |  | 2026-05-15 | 2026-05-16 | 1
218 | Firestop to RWP & SVP |  | 2026-05-22 | 2026-05-23 | 1
218 | Firestop to RWP & SVP |  | 2026-05-29 | 2026-05-30 | 1
218 | Firestop to RWP & SVP |  | 2026-06-06 | 2026-06-07 | 1
218 | Firestop to RWP & SVP |  | 2026-06-13 | 2026-06-14 | 1
218 | Firestop to RWP & SVP |  | 2026-06-20 | 2026-06-21 | 1
219 | CONTROL POINT 2 (CP2) |  | 2025-12-07 | 2025-12-11 | 4
219 | CONTROL POINT 2 (CP2) |  | 2025-12-13 | 2025-12-16 | 2
219 | CONTROL POINT 2 (CP2) |  | 2025-12-19 | 2025-12-24 | 4
219 | CONTROL POINT 2 (CP2) |  | 2025-12-26 | 2025-12-29 | 2
219 | CONTROL POINT 2 (CP2) |  | 2026-01-05 | 2026-01-07 | 3
219 | CONTROL POINT 2 (CP2) |  | 2026-01-11 | 2026-01-13 | 2
219 | CONTROL POINT 2 (CP2) |  | 2026-01-19 | 2026-01-21 | 3
219 | CONTROL POINT 2 (CP2) |  | 2026-01-25 | 2026-04-01 | 48
219 | CONTROL POINT 2 (CP2) |  | 2026-04-04 | 2026-04-05 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-04-11 | 2026-04-12 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-04-18 | 2026-04-19 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-04-25 | 2026-04-26 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-05-01 | 2026-05-02 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-05-08 | 2026-05-09 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-05-15 | 2026-05-16 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-05-22 | 2026-05-23 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-05-29 | 2026-05-30 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-06-06 | 2026-06-07 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-06-13 | 2026-06-14 | 1
219 | CONTROL POINT 2 (CP2) |  | 2026-06-20 | 2026-06-21 | 1
220 | Wall void closure checklist sign off |  | 2025-12-07 | 2025-12-11 | 4
220 | Wall void closure checklist sign off |  | 2025-12-13 | 2025-12-16 | 2
220 | Wall void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
220 | Wall void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
220 | Wall void closure checklist sign off |  | 2026-01-05 | 2026-01-07 | 3
220 | Wall void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
220 | Wall void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
220 | Wall void closure checklist sign off |  | 2026-01-25 | 2026-04-01 | 48
220 | Wall void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
220 | Wall void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
220 | Wall void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
220 | Wall void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
220 | Wall void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
220 | Wall void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
220 | Wall void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
220 | Wall void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
220 | Wall void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
220 | Wall void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
220 | Wall void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
220 | Wall void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
221 | 2nd fix Partitions - insulation and board |  | 2025-12-07 | 2025-12-11 | 4
221 | 2nd fix Partitions - insulation and board |  | 2025-12-13 | 2025-12-16 | 2
221 | 2nd fix Partitions - insulation and board |  | 2025-12-19 | 2025-12-24 | 4
221 | 2nd fix Partitions - insulation and board |  | 2025-12-26 | 2025-12-29 | 2
221 | 2nd fix Partitions - insulation and board |  | 2026-01-05 | 2026-01-07 | 3
221 | 2nd fix Partitions - insulation and board |  | 2026-01-11 | 2026-01-13 | 2
221 | 2nd fix Partitions - insulation and board |  | 2026-01-19 | 2026-01-21 | 3
221 | 2nd fix Partitions - insulation and board |  | 2026-01-25 | 2026-04-01 | 48
221 | 2nd fix Partitions - insulation and board |  | 2026-04-04 | 2026-04-05 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-04-11 | 2026-04-12 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-04-18 | 2026-04-19 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-04-25 | 2026-04-26 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-05-01 | 2026-05-02 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-05-08 | 2026-05-09 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-05-15 | 2026-05-16 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-05-22 | 2026-05-23 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-05-29 | 2026-05-30 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-06-06 | 2026-06-07 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-06-13 | 2026-06-14 | 1
221 | 2nd fix Partitions - insulation and board |  | 2026-06-20 | 2026-06-21 | 1
222 | Install Vents/ducts |  | 2025-12-07 | 2025-12-11 | 4
222 | Install Vents/ducts |  | 2025-12-13 | 2025-12-16 | 2
222 | Install Vents/ducts |  | 2025-12-19 | 2025-12-24 | 4
222 | Install Vents/ducts |  | 2025-12-26 | 2025-12-29 | 2
222 | Install Vents/ducts |  | 2026-01-05 | 2026-01-07 | 3
222 | Install Vents/ducts |  | 2026-01-11 | 2026-01-13 | 2
222 | Install Vents/ducts |  | 2026-01-19 | 2026-01-21 | 3
222 | Install Vents/ducts |  | 2026-01-25 | 2026-04-01 | 48
222 | Install Vents/ducts |  | 2026-04-04 | 2026-04-05 | 1
222 | Install Vents/ducts |  | 2026-04-11 | 2026-04-12 | 1
222 | Install Vents/ducts |  | 2026-04-18 | 2026-04-19 | 1
222 | Install Vents/ducts |  | 2026-04-25 | 2026-04-26 | 1
222 | Install Vents/ducts |  | 2026-05-01 | 2026-05-02 | 1
222 | Install Vents/ducts |  | 2026-05-08 | 2026-05-09 | 1
222 | Install Vents/ducts |  | 2026-05-15 | 2026-05-16 | 1
222 | Install Vents/ducts |  | 2026-05-22 | 2026-05-23 | 1
222 | Install Vents/ducts |  | 2026-05-29 | 2026-05-30 | 1
222 | Install Vents/ducts |  | 2026-06-06 | 2026-06-07 | 1
222 | Install Vents/ducts |  | 2026-06-13 | 2026-06-14 | 1
222 | Install Vents/ducts |  | 2026-06-20 | 2026-06-21 | 1
| CONTROL POINT 3 (CP3) |  | 2025-12-07 | 2025-12-11 | 4
| CONTROL POINT 3 (CP3) |  | 2025-12-13 | 2025-12-16 | 2
| CONTROL POINT 3 (CP3) |  | 2025-12-19 | 2025-12-24 | 4
| CONTROL POINT 3 (CP3) |  | 2025-12-26 | 2025-12-29 | 2
| CONTROL POINT 3 (CP3) |  | 2026-01-05 | 2026-01-07 | 3
| CONTROL POINT 3 (CP3) |  | 2026-01-11 | 2026-01-13 | 2
| CONTROL POINT 3 (CP3) |  | 2026-01-19 | 2026-01-21 | 3
| CONTROL POINT 3 (CP3) |  | 2026-01-25 | 2026-04-01 | 48
| CONTROL POINT 3 (CP3) |  | 2026-04-04 | 2026-04-05 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-11 | 2026-04-12 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-18 | 2026-04-19 | 1
| CONTROL POINT 3 (CP3) |  | 2026-04-25 | 2026-04-26 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-01 | 2026-05-02 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-08 | 2026-05-09 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-15 | 2026-05-16 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-22 | 2026-05-23 | 1
| CONTROL POINT 3 (CP3) |  | 2026-05-29 | 2026-05-30 | 1
| CONTROL POINT 3 (CP3) |  | 2026-06-06 | 2026-06-07 | 1
| CONTROL POINT 3 (CP3) |  | 2026-06-13 | 2026-06-14 | 1
| CONTROL POINT 3 (CP3) |  | 2026-06-20 | 2026-06-21 | 1
223 | Ceiling void closure checklist sign off |  | 2025-12-07 | 2025-12-11 | 4
223 | Ceiling void closure checklist sign off |  | 2025-12-13 | 2025-12-16 | 2
223 | Ceiling void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
223 | Ceiling void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
223 | Ceiling void closure checklist sign off |  | 2026-01-05 | 2026-01-07 | 3
223 | Ceiling void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
223 | Ceiling void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
223 | Ceiling void closure checklist sign off |  | 2026-01-25 | 2026-04-01 | 48
223 | Ceiling void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
223 | Ceiling void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
223 | Ceiling void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
223 | Ceiling void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
223 | Ceiling void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
223 | Ceiling void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
223 | Ceiling void closure checklist sign off |  | 2026-05-15 | 2026-05-16 | 1
223 | Ceiling void closure checklist sign off |  | 2026-05-22 | 2026-05-23 | 1
223 | Ceiling void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
223 | Ceiling void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
223 | Ceiling void closure checklist sign off |  | 2026-06-13 | 2026-06-14 | 1
223 | Ceiling void closure checklist sign off |  | 2026-06-20 | 2026-06-21 | 1
224 | Ceilings metal only |  | 2025-12-07 | 2025-12-11 | 4
224 | Ceilings metal only |  | 2025-12-13 | 2025-12-16 | 2
224 | Ceilings metal only |  | 2025-12-19 | 2025-12-24 | 4
224 | Ceilings metal only |  | 2025-12-26 | 2025-12-29 | 2
224 | Ceilings metal only |  | 2026-01-05 | 2026-01-07 | 3
224 | Ceilings metal only |  | 2026-01-11 | 2026-01-13 | 2
224 | Ceilings metal only |  | 2026-01-19 | 2026-01-21 | 3
224 | Ceilings metal only |  | 2026-01-25 | 2026-04-01 | 48
224 | Ceilings metal only |  | 2026-04-04 | 2026-04-05 | 1
224 | Ceilings metal only |  | 2026-04-11 | 2026-04-12 | 1
224 | Ceilings metal only |  | 2026-04-18 | 2026-04-19 | 1
224 | Ceilings metal only |  | 2026-04-25 | 2026-04-26 | 1
224 | Ceilings metal only |  | 2026-05-01 | 2026-05-02 | 1
224 | Ceilings metal only |  | 2026-05-08 | 2026-05-09 | 1
224 | Ceilings metal only |  | 2026-05-15 | 2026-05-16 | 1
224 | Ceilings metal only |  | 2026-05-22 | 2026-05-23 | 1
224 | Ceilings metal only |  | 2026-05-29 | 2026-05-30 | 1
224 | Ceilings metal only |  | 2026-06-06 | 2026-06-07 | 1
224 | Ceilings metal only |  | 2026-06-13 | 2026-06-14 | 1
224 | Ceilings metal only |  | 2026-06-20 | 2026-06-21 | 1
225 | Sprinkler 1st fix & test |  | 2025-12-07 | 2025-12-11 | 4
225 | Sprinkler 1st fix & test |  | 2025-12-13 | 2025-12-16 | 2
225 | Sprinkler 1st fix & test |  | 2025-12-19 | 2025-12-24 | 4
225 | Sprinkler 1st fix & test |  | 2025-12-26 | 2025-12-29 | 2
225 | Sprinkler 1st fix & test |  | 2026-01-05 | 2026-01-07 | 3
225 | Sprinkler 1st fix & test |  | 2026-01-11 | 2026-01-13 | 2
225 | Sprinkler 1st fix & test |  | 2026-01-19 | 2026-01-21 | 3
225 | Sprinkler 1st fix & test |  | 2026-01-25 | 2026-04-01 | 48
225 | Sprinkler 1st fix & test |  | 2026-04-04 | 2026-04-05 | 1
225 | Sprinkler 1st fix & test |  | 2026-04-11 | 2026-04-12 | 1
225 | Sprinkler 1st fix & test |  | 2026-04-18 | 2026-04-19 | 1
225 | Sprinkler 1st fix & test |  | 2026-04-25 | 2026-04-26 | 1
225 | Sprinkler 1st fix & test |  | 2026-05-01 | 2026-05-02 | 1
225 | Sprinkler 1st fix & test |  | 2026-05-08 | 2026-05-09 | 1
225 | Sprinkler 1st fix & test |  | 2026-05-15 | 2026-05-16 | 1
225 | Sprinkler 1st fix & test |  | 2026-05-22 | 2026-05-23 | 1
225 | Sprinkler 1st fix & test |  | 2026-05-29 | 2026-05-30 | 1
225 | Sprinkler 1st fix & test |  | 2026-06-06 | 2026-06-07 | 1
225 | Sprinkler 1st fix & test |  | 2026-06-13 | 2026-06-14 | 1
225 | Sprinkler 1st fix & test |  | 2026-06-20 | 2026-06-21 | 1
226 | Ceilings - board (cut holes for lights) |  | 2025-12-07 | 2025-12-11 | 4
226 | Ceilings - board (cut holes for lights) |  | 2025-12-13 | 2025-12-16 | 2
226 | Ceilings - board (cut holes for lights) |  | 2025-12-19 | 2025-12-24 | 4
226 | Ceilings - board (cut holes for lights) |  | 2025-12-26 | 2025-12-29 | 2
226 | Ceilings - board (cut holes for lights) |  | 2026-01-05 | 2026-01-07 | 3
226 | Ceilings - board (cut holes for lights) |  | 2026-01-11 | 2026-01-13 | 2
226 | Ceilings - board (cut holes for lights) |  | 2026-01-19 | 2026-01-21 | 3
226 | Ceilings - board (cut holes for lights) |  | 2026-01-25 | 2026-04-01 | 48
226 | Ceilings - board (cut holes for lights) |  | 2026-04-04 | 2026-04-05 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-04-11 | 2026-04-12 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-04-18 | 2026-04-19 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-04-25 | 2026-04-26 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-05-01 | 2026-05-02 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-05-08 | 2026-05-09 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-05-15 | 2026-05-16 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-05-22 | 2026-05-23 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-05-29 | 2026-05-30 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-06-06 | 2026-06-07 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-06-13 | 2026-06-14 | 1
226 | Ceilings - board (cut holes for lights) |  | 2026-06-20 | 2026-06-21 | 1
227 | Plaster spray |  | 2025-12-07 | 2025-12-11 | 4
227 | Plaster spray |  | 2025-12-13 | 2025-12-16 | 2
227 | Plaster spray |  | 2025-12-19 | 2025-12-24 | 4
227 | Plaster spray |  | 2025-12-26 | 2025-12-29 | 2
227 | Plaster spray |  | 2026-01-05 | 2026-01-07 | 3
227 | Plaster spray |  | 2026-01-11 | 2026-01-13 | 2
227 | Plaster spray |  | 2026-01-19 | 2026-01-21 | 3
227 | Plaster spray |  | 2026-01-25 | 2026-04-01 | 48
227 | Plaster spray |  | 2026-04-04 | 2026-04-05 | 1
227 | Plaster spray |  | 2026-04-11 | 2026-04-12 | 1
227 | Plaster spray |  | 2026-04-18 | 2026-04-19 | 1
227 | Plaster spray |  | 2026-04-25 | 2026-04-26 | 1
227 | Plaster spray |  | 2026-05-01 | 2026-05-02 | 1
227 | Plaster spray |  | 2026-05-08 | 2026-05-09 | 1
227 | Plaster spray |  | 2026-05-22 | 2026-05-23 | 1
227 | Plaster spray |  | 2026-05-29 | 2026-05-30 | 1
227 | Plaster spray |  | 2026-06-06 | 2026-06-07 | 1
227 | Plaster spray |  | 2026-06-13 | 2026-06-14 | 1
227 | Plaster spray |  | 2026-06-20 | 2026-06-21 | 1
228 | Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-11 | 4
228 | Levveling screed /smoothing compound |  | 2025-12-13 | 2025-12-16 | 2
228 | Levveling screed /smoothing compound |  | 2025-12-19 | 2025-12-24 | 4
228 | Levveling screed /smoothing compound |  | 2025-12-26 | 2025-12-29 | 2
228 | Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-07 | 3
228 | Levveling screed /smoothing compound |  | 2026-01-11 | 2026-01-13 | 2
228 | Levveling screed /smoothing compound |  | 2026-01-19 | 2026-01-21 | 3
228 | Levveling screed /smoothing compound |  | 2026-01-25 | 2026-04-01 | 48
228 | Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
228 | Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
228 | Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
228 | Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
228 | Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
228 | Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
228 | Levveling screed /smoothing compound |  | 2026-05-29 | 2026-05-30 | 1
228 | Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
228 | Levveling screed /smoothing compound |  | 2026-06-13 | 2026-06-14 | 1
228 | Levveling screed /smoothing compound |  | 2026-06-20 | 2026-06-21 | 1
229 | Drying out |  | 2025-12-07 | 2025-12-11 | 4
229 | Drying out |  | 2025-12-13 | 2025-12-16 | 2
229 | Drying out |  | 2025-12-19 | 2025-12-24 | 4
229 | Drying out |  | 2025-12-26 | 2025-12-29 | 2
229 | Drying out |  | 2026-01-05 | 2026-01-07 | 3
229 | Drying out |  | 2026-01-11 | 2026-01-13 | 2
229 | Drying out |  | 2026-01-19 | 2026-01-21 | 3
229 | Drying out |  | 2026-01-25 | 2026-04-01 | 48
229 | Drying out |  | 2026-04-04 | 2026-04-05 | 1
229 | Drying out |  | 2026-04-11 | 2026-04-12 | 1
229 | Drying out |  | 2026-04-18 | 2026-04-19 | 1
229 | Drying out |  | 2026-04-25 | 2026-04-26 | 1
229 | Drying out |  | 2026-05-01 | 2026-05-02 | 1
229 | Drying out |  | 2026-05-08 | 2026-05-09 | 1
229 | Drying out |  | 2026-05-29 | 2026-05-30 | 1
229 | Drying out |  | 2026-06-06 | 2026-06-07 | 1
229 | Drying out |  | 2026-06-13 | 2026-06-14 | 1
229 | Drying out |  | 2026-06-20 | 2026-06-21 | 1
230 | Mist coat |  | 2025-12-07 | 2025-12-11 | 4
230 | Mist coat |  | 2025-12-13 | 2025-12-16 | 2
230 | Mist coat |  | 2025-12-19 | 2025-12-24 | 4
230 | Mist coat |  | 2025-12-26 | 2025-12-29 | 2
230 | Mist coat |  | 2026-01-05 | 2026-01-07 | 3
230 | Mist coat |  | 2026-01-11 | 2026-01-13 | 2
230 | Mist coat |  | 2026-01-19 | 2026-01-21 | 3
230 | Mist coat |  | 2026-01-25 | 2026-04-01 | 48
230 | Mist coat |  | 2026-04-04 | 2026-04-05 | 1
230 | Mist coat |  | 2026-04-11 | 2026-04-12 | 1
230 | Mist coat |  | 2026-04-18 | 2026-04-19 | 1
230 | Mist coat |  | 2026-04-25 | 2026-04-26 | 1
230 | Mist coat |  | 2026-05-01 | 2026-05-02 | 1
230 | Mist coat |  | 2026-05-08 | 2026-05-09 | 1
230 | Mist coat |  | 2026-05-29 | 2026-05-30 | 1
230 | Mist coat |  | 2026-06-06 | 2026-06-07 | 1
230 | Mist coat |  | 2026-06-13 | 2026-06-14 | 1
230 | Mist coat |  | 2026-06-20 | 2026-06-21 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-11 | 4
231 | Kitchen 1st fix,units tops & appliances |  | 2025-12-13 | 2025-12-16 | 2
231 | Kitchen 1st fix,units tops & appliances |  | 2025-12-19 | 2025-12-24 | 4
231 | Kitchen 1st fix,units tops & appliances |  | 2025-12-26 | 2025-12-29 | 2
231 | Kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-07 | 3
231 | Kitchen 1st fix,units tops & appliances |  | 2026-01-11 | 2026-01-13 | 2
231 | Kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-21 | 3
231 | Kitchen 1st fix,units tops & appliances |  | 2026-01-25 | 2026-04-01 | 48
231 | Kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-05 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-05-29 | 2026-05-30 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
231 | Kitchen 1st fix,units tops & appliances |  | 2026-06-13 | 2026-06-14 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-11 | 4
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-13 | 2025-12-16 | 2
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-19 | 2025-12-24 | 4
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-26 | 2026-01-07 | 9
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-11 | 2026-01-13 | 2
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-19 | 2026-01-21 | 3
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-25 | 2026-04-01 | 48
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-04 | 2026-04-05 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-18 | 2026-04-19 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-25 | 2026-04-26 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-01 | 2026-05-02 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-29 | 2026-05-30 | 1
232 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-06-06 | 2026-06-07 | 1
233 | Floor and wall tiling JD tiling |  | 2025-12-07 | 2025-12-11 | 4
233 | Floor and wall tiling JD tiling |  | 2025-12-13 | 2025-12-16 | 2
233 | Floor and wall tiling JD tiling |  | 2025-12-19 | 2025-12-24 | 4
233 | Floor and wall tiling JD tiling |  | 2025-12-26 | 2025-12-29 | 2
233 | Floor and wall tiling JD tiling |  | 2026-01-05 | 2026-01-13 | 7
233 | Floor and wall tiling JD tiling |  | 2026-01-19 | 2026-01-21 | 3
233 | Floor and wall tiling JD tiling |  | 2026-01-25 | 2026-04-01 | 48
233 | Floor and wall tiling JD tiling |  | 2026-04-04 | 2026-04-05 | 1
233 | Floor and wall tiling JD tiling |  | 2026-04-11 | 2026-04-12 | 1
233 | Floor and wall tiling JD tiling |  | 2026-04-18 | 2026-04-19 | 1
233 | Floor and wall tiling JD tiling |  | 2026-04-25 | 2026-04-26 | 1
233 | Floor and wall tiling JD tiling |  | 2026-05-01 | 2026-05-02 | 1
233 | Floor and wall tiling JD tiling |  | 2026-05-08 | 2026-05-09 | 1
233 | Floor and wall tiling JD tiling |  | 2026-05-29 | 2026-05-30 | 1
233 | Floor and wall tiling JD tiling |  | 2026-06-06 | 2026-06-07 | 1
234 | Control point 4 CP 4 |  | 2025-12-07 | 2025-12-11 | 4
234 | Control point 4 CP 4 |  | 2025-12-13 | 2025-12-16 | 2
234 | Control point 4 CP 4 |  | 2025-12-19 | 2025-12-24 | 4
234 | Control point 4 CP 4 |  | 2025-12-26 | 2025-12-29 | 2
234 | Control point 4 CP 4 |  | 2026-01-05 | 2026-01-07 | 3
234 | Control point 4 CP 4 |  | 2026-01-11 | 2026-04-01 | 58
234 | Control point 4 CP 4 |  | 2026-04-04 | 2026-04-05 | 1
234 | Control point 4 CP 4 |  | 2026-04-11 | 2026-04-12 | 1
234 | Control point 4 CP 4 |  | 2026-04-18 | 2026-04-19 | 1
234 | Control point 4 CP 4 |  | 2026-04-25 | 2026-04-26 | 1
234 | Control point 4 CP 4 |  | 2026-05-01 | 2026-05-02 | 1
234 | Control point 4 CP 4 |  | 2026-05-08 | 2026-05-09 | 1
234 | Control point 4 CP 4 |  | 2026-05-29 | 2026-05-30 | 1
234 | Control point 4 CP 4 |  | 2026-06-06 | 2026-06-07 | 1
235 | service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-11 | 4
235 | service cupbaord -plywood flooring |  | 2025-12-13 | 2025-12-16 | 2
235 | service cupbaord -plywood flooring |  | 2025-12-19 | 2025-12-24 | 4
235 | service cupbaord -plywood flooring |  | 2025-12-26 | 2025-12-29 | 2
235 | service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-07 | 3
235 | service cupbaord -plywood flooring |  | 2026-01-11 | 2026-01-13 | 2
235 | service cupbaord -plywood flooring |  | 2026-01-19 | 2026-04-01 | 53
235 | service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
235 | service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
235 | service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
235 | service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
235 | service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
235 | service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
235 | service cupbaord -plywood flooring |  | 2026-05-29 | 2026-05-30 | 1
235 | service cupbaord -plywood flooring |  | 2026-06-06 | 2026-06-07 | 1
236 | service cupboard decoration |  | 2025-12-07 | 2025-12-11 | 4
236 | service cupboard decoration |  | 2025-12-13 | 2025-12-16 | 2
236 | service cupboard decoration |  | 2025-12-19 | 2025-12-24 | 4
236 | service cupboard decoration |  | 2025-12-26 | 2025-12-29 | 2
236 | service cupboard decoration |  | 2026-01-05 | 2026-01-07 | 3
236 | service cupboard decoration |  | 2026-01-11 | 2026-01-13 | 2
236 | service cupboard decoration |  | 2026-01-19 | 2026-01-21 | 3
236 | service cupboard decoration |  | 2026-01-25 | 2026-04-01 | 48
236 | service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
236 | service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
236 | service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
236 | service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
236 | service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
236 | service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
236 | service cupboard decoration |  | 2026-05-29 | 2026-05-30 | 1
236 | service cupboard decoration |  | 2026-06-06 | 2026-06-07 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-07 | 2025-12-11 | 4
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-13 | 2025-12-16 | 2
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-19 | 2025-12-24 | 4
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-26 | 2025-12-29 | 2
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-05 | 2026-01-07 | 3
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-11 | 2026-01-13 | 2
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-19 | 2026-01-21 | 3
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-01-25 | 2026-04-01 | 48
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-04 | 2026-04-05 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-11 | 2026-04-12 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-18 | 2026-04-19 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-25 | 2026-04-26 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-01 | 2026-05-02 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-08 | 2026-05-09 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-29 | 2026-05-30 | 1
237 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-06-06 | 2026-06-07 | 1
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2025-12-11 | 4
| Amtico flooring /Bathrooms |  | 2025-12-13 | 2025-12-16 | 2
| Amtico flooring /Bathrooms |  | 2025-12-19 | 2025-12-24 | 4
| Amtico flooring /Bathrooms |  | 2025-12-26 | 2025-12-29 | 2
| Amtico flooring /Bathrooms |  | 2026-01-05 | 2026-01-07 | 3
| Amtico flooring /Bathrooms |  | 2026-01-11 | 2026-01-13 | 2
| Amtico flooring /Bathrooms |  | 2026-01-19 | 2026-01-21 | 3
| Amtico flooring /Bathrooms |  | 2026-01-25 | 2026-04-01 | 48
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2026-05-29 | 2026-05-30 | 1
| Amtico flooring /Bathrooms |  | 2026-06-06 | 2026-06-07 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2025-12-11 | 4
238 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-13 | 2025-12-16 | 2
238 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-19 | 2025-12-24 | 4
238 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-26 | 2025-12-29 | 2
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-05 | 2026-01-07 | 3
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-11 | 2026-01-13 | 2
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-19 | 2026-01-21 | 3
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-01-25 | 2026-04-01 | 48
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-05 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-29 | 2026-05-30 | 1
238 | Plumbing second fix sanitaryware & pressure testing |  | 2026-06-06 | 2026-06-07 | 1
239 | Electrical 2nd fix & live testing |  | 2025-12-07 | 2025-12-11 | 4
239 | Electrical 2nd fix & live testing |  | 2025-12-13 | 2025-12-16 | 2
239 | Electrical 2nd fix & live testing |  | 2025-12-19 | 2025-12-24 | 4
239 | Electrical 2nd fix & live testing |  | 2025-12-26 | 2025-12-29 | 2
239 | Electrical 2nd fix & live testing |  | 2026-01-05 | 2026-01-07 | 3
239 | Electrical 2nd fix & live testing |  | 2026-01-11 | 2026-01-13 | 2
239 | Electrical 2nd fix & live testing |  | 2026-01-19 | 2026-01-21 | 3
239 | Electrical 2nd fix & live testing |  | 2026-01-25 | 2026-04-01 | 48
239 | Electrical 2nd fix & live testing |  | 2026-04-04 | 2026-04-05 | 1
239 | Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
239 | Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
239 | Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
239 | Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
239 | Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
239 | Electrical 2nd fix & live testing |  | 2026-05-29 | 2026-05-30 | 1
239 | Electrical 2nd fix & live testing |  | 2026-06-06 | 2026-06-07 | 1
240 | Builders clean |  | 2025-12-07 | 2025-12-11 | 4
240 | Builders clean |  | 2025-12-13 | 2025-12-16 | 2
240 | Builders clean |  | 2025-12-19 | 2025-12-24 | 4
240 | Builders clean |  | 2025-12-26 | 2025-12-29 | 2
240 | Builders clean |  | 2026-01-05 | 2026-01-07 | 3
240 | Builders clean |  | 2026-01-11 | 2026-01-13 | 2
240 | Builders clean |  | 2026-01-19 | 2026-01-21 | 3
240 | Builders clean |  | 2026-01-25 | 2026-04-01 | 48
240 | Builders clean |  | 2026-04-04 | 2026-04-05 | 1
240 | Builders clean |  | 2026-04-11 | 2026-04-12 | 1
240 | Builders clean |  | 2026-04-18 | 2026-04-19 | 1
240 | Builders clean |  | 2026-04-25 | 2026-04-26 | 1
240 | Builders clean |  | 2026-05-01 | 2026-05-02 | 1
240 | Builders clean |  | 2026-05-08 | 2026-05-09 | 1
240 | Builders clean |  | 2026-05-29 | 2026-05-30 | 1
240 | Builders clean |  | 2026-06-06 | 2026-06-07 | 1
241 | Pre -dec -snagging |  | 2025-12-07 | 2025-12-11 | 4
241 | Pre -dec -snagging |  | 2025-12-13 | 2025-12-16 | 2
241 | Pre -dec -snagging |  | 2025-12-19 | 2025-12-24 | 4
241 | Pre -dec -snagging |  | 2025-12-26 | 2025-12-29 | 2
241 | Pre -dec -snagging |  | 2026-01-05 | 2026-01-07 | 3
241 | Pre -dec -snagging |  | 2026-01-11 | 2026-01-13 | 2
241 | Pre -dec -snagging |  | 2026-01-19 | 2026-01-21 | 3
241 | Pre -dec -snagging |  | 2026-01-25 | 2026-04-01 | 48
241 | Pre -dec -snagging |  | 2026-04-04 | 2026-04-05 | 1
241 | Pre -dec -snagging |  | 2026-04-11 | 2026-04-12 | 1
241 | Pre -dec -snagging |  | 2026-04-18 | 2026-04-19 | 1
241 | Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
241 | Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
241 | Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
241 | Pre -dec -snagging |  | 2026-05-29 | 2026-05-30 | 1
241 | Pre -dec -snagging |  | 2026-06-06 | 2026-06-07 | 1
242 | Decoration |  | 2025-12-07 | 2025-12-11 | 4
242 | Decoration |  | 2025-12-13 | 2025-12-16 | 2
242 | Decoration |  | 2025-12-19 | 2025-12-24 | 4
242 | Decoration |  | 2025-12-26 | 2025-12-29 | 2
242 | Decoration |  | 2026-01-05 | 2026-01-07 | 3
242 | Decoration |  | 2026-01-11 | 2026-01-13 | 2
242 | Decoration |  | 2026-01-19 | 2026-01-21 | 3
242 | Decoration |  | 2026-01-25 | 2026-04-01 | 48
242 | Decoration |  | 2026-04-04 | 2026-04-05 | 1
242 | Decoration |  | 2026-04-11 | 2026-04-12 | 1
242 | Decoration |  | 2026-04-18 | 2026-04-19 | 1
242 | Decoration |  | 2026-04-25 | 2026-04-26 | 1
242 | Decoration |  | 2026-05-01 | 2026-05-02 | 1
242 | Decoration |  | 2026-05-08 | 2026-05-09 | 1
242 | Decoration |  | 2026-05-29 | 2026-05-30 | 1
242 | Decoration |  | 2026-06-06 | 2026-06-07 | 1
243 | Amtico flooring /Carpets |  | 2025-12-07 | 2025-12-11 | 4
243 | Amtico flooring /Carpets |  | 2025-12-13 | 2025-12-16 | 2
243 | Amtico flooring /Carpets |  | 2025-12-19 | 2025-12-24 | 4
243 | Amtico flooring /Carpets |  | 2025-12-26 | 2025-12-29 | 2
243 | Amtico flooring /Carpets |  | 2026-01-05 | 2026-01-07 | 3
243 | Amtico flooring /Carpets |  | 2026-01-11 | 2026-01-13 | 2
243 | Amtico flooring /Carpets |  | 2026-01-19 | 2026-01-21 | 3
243 | Amtico flooring /Carpets |  | 2026-01-25 | 2026-04-01 | 48
243 | Amtico flooring /Carpets |  | 2026-04-04 | 2026-04-05 | 1
243 | Amtico flooring /Carpets |  | 2026-04-11 | 2026-04-12 | 1
243 | Amtico flooring /Carpets |  | 2026-04-18 | 2026-04-19 | 1
243 | Amtico flooring /Carpets |  | 2026-04-25 | 2026-04-26 | 1
243 | Amtico flooring /Carpets |  | 2026-05-01 | 2026-05-02 | 1
243 | Amtico flooring /Carpets |  | 2026-05-08 | 2026-05-09 | 1
243 | Amtico flooring /Carpets |  | 2026-05-29 | 2026-05-30 | 1
243 | Amtico flooring /Carpets |  | 2026-06-06 | 2026-06-07 | 1
244 | De snag all trades |  | 2025-12-07 | 2025-12-11 | 4
244 | De snag all trades |  | 2025-12-13 | 2025-12-16 | 2
244 | De snag all trades |  | 2025-12-19 | 2025-12-24 | 4
244 | De snag all trades |  | 2025-12-26 | 2025-12-29 | 2
244 | De snag all trades |  | 2026-01-05 | 2026-01-07 | 3
244 | De snag all trades |  | 2026-01-11 | 2026-01-13 | 2
244 | De snag all trades |  | 2026-01-19 | 2026-01-21 | 3
244 | De snag all trades |  | 2026-01-25 | 2026-04-01 | 48
244 | De snag all trades |  | 2026-04-04 | 2026-04-05 | 1
244 | De snag all trades |  | 2026-04-11 | 2026-04-12 | 1
244 | De snag all trades |  | 2026-04-18 | 2026-04-19 | 1
244 | De snag all trades |  | 2026-04-25 | 2026-04-26 | 1
244 | De snag all trades |  | 2026-05-01 | 2026-05-02 | 1
244 | De snag all trades |  | 2026-05-08 | 2026-05-09 | 1
244 | De snag all trades |  | 2026-05-29 | 2026-05-30 | 1
244 | De snag all trades |  | 2026-06-06 | 2026-06-07 | 1
245 | Sparkle clean |  | 2025-12-07 | 2025-12-11 | 4
245 | Sparkle clean |  | 2025-12-13 | 2025-12-16 | 2
245 | Sparkle clean |  | 2025-12-19 | 2025-12-24 | 4
245 | Sparkle clean |  | 2025-12-26 | 2025-12-29 | 2
245 | Sparkle clean |  | 2026-01-05 | 2026-01-07 | 3
245 | Sparkle clean |  | 2026-01-11 | 2026-01-13 | 2
245 | Sparkle clean |  | 2026-01-19 | 2026-01-21 | 3
245 | Sparkle clean |  | 2026-01-25 | 2026-04-01 | 48
245 | Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
245 | Sparkle clean |  | 2026-04-11 | 2026-04-12 | 1
245 | Sparkle clean |  | 2026-04-18 | 2026-04-19 | 1
245 | Sparkle clean |  | 2026-04-25 | 2026-04-26 | 1
245 | Sparkle clean |  | 2026-05-01 | 2026-05-02 | 1
245 | Sparkle clean |  | 2026-05-08 | 2026-05-09 | 1
245 | Sparkle clean |  | 2026-05-29 | 2026-05-30 | 1
245 | Sparkle clean |  | 2026-06-06 | 2026-06-07 | 1
246 | Mastic |  | 2025-12-07 | 2025-12-11 | 4
246 | Mastic |  | 2025-12-13 | 2025-12-16 | 2
246 | Mastic |  | 2025-12-19 | 2025-12-24 | 4
246 | Mastic |  | 2025-12-26 | 2025-12-29 | 2
246 | Mastic |  | 2026-01-05 | 2026-01-07 | 3
246 | Mastic |  | 2026-01-11 | 2026-01-13 | 2
246 | Mastic |  | 2026-01-19 | 2026-01-21 | 3
246 | Mastic |  | 2026-01-25 | 2026-04-01 | 48
246 | Mastic |  | 2026-04-04 | 2026-04-05 | 1
246 | Mastic |  | 2026-04-11 | 2026-04-12 | 1
246 | Mastic |  | 2026-04-18 | 2026-04-19 | 1
246 | Mastic |  | 2026-04-25 | 2026-04-26 | 1
246 | Mastic |  | 2026-05-01 | 2026-05-02 | 1
246 | Mastic |  | 2026-05-08 | 2026-05-09 | 1
246 | Mastic |  | 2026-05-29 | 2026-05-30 | 1
246 | Mastic |  | 2026-06-06 | 2026-06-07 | 1
247 | Handover to client |  | 2025-12-07 | 2025-12-11 | 4
247 | Handover to client |  | 2025-12-13 | 2025-12-16 | 2
247 | Handover to client |  | 2025-12-19 | 2025-12-24 | 4
247 | Handover to client |  | 2025-12-26 | 2025-12-29 | 2
247 | Handover to client |  | 2026-01-05 | 2026-01-07 | 3
247 | Handover to client |  | 2026-01-11 | 2026-01-13 | 2
247 | Handover to client |  | 2026-01-19 | 2026-01-21 | 3
247 | Handover to client |  | 2026-01-25 | 2026-04-01 | 48
247 | Handover to client |  | 2026-04-04 | 2026-04-05 | 1
247 | Handover to client |  | 2026-04-11 | 2026-04-12 | 1
247 | Handover to client |  | 2026-04-18 | 2026-04-19 | 1
247 | Handover to client |  | 2026-04-25 | 2026-04-26 | 1
247 | Handover to client |  | 2026-05-01 | 2026-05-02 | 1
247 | Handover to client |  | 2026-05-08 | 2026-05-09 | 1
247 | Handover to client |  | 2026-05-29 | 2026-05-30 | 1
247 | Handover to client |  | 2026-06-06 | 2026-06-07 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2025-12-07 | 2025-12-11 | 4
248 | Level 7Apartment fit out -cluster 2 |  | 2025-12-13 | 2025-12-16 | 2
248 | Level 7Apartment fit out -cluster 2 |  | 2025-12-19 | 2025-12-24 | 4
248 | Level 7Apartment fit out -cluster 2 |  | 2025-12-26 | 2025-12-29 | 2
248 | Level 7Apartment fit out -cluster 2 |  | 2026-01-05 | 2026-01-07 | 3
248 | Level 7Apartment fit out -cluster 2 |  | 2026-01-11 | 2026-01-13 | 2
248 | Level 7Apartment fit out -cluster 2 |  | 2026-01-19 | 2026-01-21 | 3
248 | Level 7Apartment fit out -cluster 2 |  | 2026-01-25 | 2026-04-01 | 48
248 | Level 7Apartment fit out -cluster 2 |  | 2026-04-04 | 2026-04-05 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-04-11 | 2026-04-12 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-04-18 | 2026-04-19 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-04-25 | 2026-04-26 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-05-01 | 2026-05-02 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-05-08 | 2026-05-09 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-05-29 | 2026-05-30 | 1
248 | Level 7Apartment fit out -cluster 2 |  | 2026-06-06 | 2026-06-07 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2025-12-07 | 2025-12-11 | 4
249 | 1st fix electrical back boxes Edencroft |  | 2025-12-13 | 2025-12-16 | 2
249 | 1st fix electrical back boxes Edencroft |  | 2025-12-19 | 2025-12-24 | 4
249 | 1st fix electrical back boxes Edencroft |  | 2025-12-26 | 2025-12-29 | 2
249 | 1st fix electrical back boxes Edencroft |  | 2026-01-05 | 2026-01-07 | 3
249 | 1st fix electrical back boxes Edencroft |  | 2026-01-11 | 2026-01-13 | 2
249 | 1st fix electrical back boxes Edencroft |  | 2026-01-19 | 2026-01-21 | 3
249 | 1st fix electrical back boxes Edencroft |  | 2026-01-25 | 2026-04-01 | 48
249 | 1st fix electrical back boxes Edencroft |  | 2026-04-04 | 2026-04-05 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-04-11 | 2026-04-12 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-04-18 | 2026-04-19 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-04-25 | 2026-04-26 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-05-01 | 2026-05-02 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-05-08 | 2026-05-09 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-05-29 | 2026-05-30 | 1
249 | 1st fix electrical back boxes Edencroft |  | 2026-06-06 | 2026-06-07 | 1
250 | 1st fix partitions/pattreses one side |  | 2025-12-07 | 2025-12-11 | 4
250 | 1st fix partitions/pattreses one side |  | 2025-12-13 | 2025-12-16 | 2
250 | 1st fix partitions/pattreses one side |  | 2025-12-19 | 2025-12-24 | 4
250 | 1st fix partitions/pattreses one side |  | 2025-12-26 | 2025-12-29 | 2
250 | 1st fix partitions/pattreses one side |  | 2026-01-05 | 2026-01-07 | 3
250 | 1st fix partitions/pattreses one side |  | 2026-01-11 | 2026-01-13 | 2
250 | 1st fix partitions/pattreses one side |  | 2026-01-19 | 2026-01-21 | 3
250 | 1st fix partitions/pattreses one side |  | 2026-01-25 | 2026-04-01 | 48
250 | 1st fix partitions/pattreses one side |  | 2026-04-04 | 2026-04-05 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-04-11 | 2026-04-12 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-04-18 | 2026-04-19 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-04-25 | 2026-04-26 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-05-01 | 2026-05-02 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-05-08 | 2026-05-09 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-05-29 | 2026-05-30 | 1
250 | 1st fix partitions/pattreses one side |  | 2026-06-06 | 2026-06-07 | 1
251 | First fix wire -ceilings/walls |  | 2025-12-07 | 2025-12-11 | 4
251 | First fix wire -ceilings/walls |  | 2025-12-13 | 2025-12-16 | 2
251 | First fix wire -ceilings/walls |  | 2025-12-19 | 2025-12-24 | 4
251 | First fix wire -ceilings/walls |  | 2025-12-26 | 2025-12-29 | 2
251 | First fix wire -ceilings/walls |  | 2026-01-05 | 2026-01-07 | 3
251 | First fix wire -ceilings/walls |  | 2026-01-11 | 2026-01-13 | 2
251 | First fix wire -ceilings/walls |  | 2026-01-19 | 2026-01-21 | 3
251 | First fix wire -ceilings/walls |  | 2026-01-25 | 2026-04-01 | 48
251 | First fix wire -ceilings/walls |  | 2026-04-04 | 2026-04-05 | 1
251 | First fix wire -ceilings/walls |  | 2026-04-11 | 2026-04-12 | 1
251 | First fix wire -ceilings/walls |  | 2026-04-18 | 2026-04-19 | 1
251 | First fix wire -ceilings/walls |  | 2026-04-25 | 2026-04-26 | 1
251 | First fix wire -ceilings/walls |  | 2026-05-01 | 2026-05-02 | 1
251 | First fix wire -ceilings/walls |  | 2026-05-08 | 2026-05-09 | 1
251 | First fix wire -ceilings/walls |  | 2026-05-29 | 2026-05-30 | 1
251 | First fix wire -ceilings/walls |  | 2026-06-06 | 2026-06-07 | 1
252 | first fix plumbing |  | 2025-12-07 | 2025-12-11 | 4
252 | first fix plumbing |  | 2025-12-13 | 2025-12-16 | 2
252 | first fix plumbing |  | 2025-12-19 | 2025-12-24 | 4
252 | first fix plumbing |  | 2025-12-26 | 2025-12-29 | 2
252 | first fix plumbing |  | 2026-01-05 | 2026-01-07 | 3
252 | first fix plumbing |  | 2026-01-11 | 2026-01-13 | 2
252 | first fix plumbing |  | 2026-01-19 | 2026-01-21 | 3
252 | first fix plumbing |  | 2026-01-25 | 2026-04-01 | 48
252 | first fix plumbing |  | 2026-04-04 | 2026-04-05 | 1
252 | first fix plumbing |  | 2026-04-11 | 2026-04-12 | 1
252 | first fix plumbing |  | 2026-04-18 | 2026-04-19 | 1
252 | first fix plumbing |  | 2026-04-25 | 2026-04-26 | 1
252 | first fix plumbing |  | 2026-05-01 | 2026-05-02 | 1
252 | first fix plumbing |  | 2026-05-08 | 2026-05-09 | 1
252 | first fix plumbing |  | 2026-05-29 | 2026-05-30 | 1
252 | first fix plumbing |  | 2026-06-06 | 2026-06-07 | 1
253 | SVP & RWP install |  | 2025-12-07 | 2025-12-11 | 4
253 | SVP & RWP install |  | 2025-12-13 | 2025-12-16 | 2
253 | SVP & RWP install |  | 2025-12-19 | 2025-12-24 | 4
253 | SVP & RWP install |  | 2025-12-26 | 2025-12-29 | 2
253 | SVP & RWP install |  | 2026-01-05 | 2026-01-07 | 3
253 | SVP & RWP install |  | 2026-01-11 | 2026-01-13 | 2
253 | SVP & RWP install |  | 2026-01-19 | 2026-01-21 | 3
253 | SVP & RWP install |  | 2026-01-25 | 2026-04-05 | 50
253 | SVP & RWP install |  | 2026-04-11 | 2026-04-12 | 1
253 | SVP & RWP install |  | 2026-04-18 | 2026-04-19 | 1
253 | SVP & RWP install |  | 2026-04-25 | 2026-04-26 | 1
253 | SVP & RWP install |  | 2026-05-01 | 2026-05-02 | 1
253 | SVP & RWP install |  | 2026-05-08 | 2026-05-09 | 1
253 | SVP & RWP install |  | 2026-05-29 | 2026-05-30 | 1
253 | SVP & RWP install |  | 2026-06-06 | 2026-06-07 | 1
254 | Firestop to RWP & SVP |  | 2025-12-07 | 2025-12-11 | 4
254 | Firestop to RWP & SVP |  | 2025-12-13 | 2025-12-16 | 2
254 | Firestop to RWP & SVP |  | 2025-12-19 | 2025-12-24 | 4
254 | Firestop to RWP & SVP |  | 2025-12-26 | 2025-12-29 | 2
254 | Firestop to RWP & SVP |  | 2026-01-05 | 2026-01-07 | 3
254 | Firestop to RWP & SVP |  | 2026-01-11 | 2026-01-13 | 2
254 | Firestop to RWP & SVP |  | 2026-01-19 | 2026-01-21 | 3
254 | Firestop to RWP & SVP |  | 2026-01-25 | 2026-04-05 | 50
254 | Firestop to RWP & SVP |  | 2026-04-11 | 2026-04-12 | 1
254 | Firestop to RWP & SVP |  | 2026-04-18 | 2026-04-19 | 1
254 | Firestop to RWP & SVP |  | 2026-04-25 | 2026-04-26 | 1
254 | Firestop to RWP & SVP |  | 2026-05-01 | 2026-05-02 | 1
254 | Firestop to RWP & SVP |  | 2026-05-08 | 2026-05-09 | 1
254 | Firestop to RWP & SVP |  | 2026-05-29 | 2026-05-30 | 1
254 | Firestop to RWP & SVP |  | 2026-06-06 | 2026-06-07 | 1
| CONTROL POINT 2 (CP2) |  | 2025-12-07 | 2025-12-11 | 4
| CONTROL POINT 2 (CP2) |  | 2025-12-13 | 2025-12-16 | 2
| CONTROL POINT 2 (CP2) |  | 2025-12-19 | 2025-12-24 | 4
| CONTROL POINT 2 (CP2) |  | 2025-12-26 | 2025-12-29 | 2
| CONTROL POINT 2 (CP2) |  | 2026-01-05 | 2026-01-07 | 3
| CONTROL POINT 2 (CP2) |  | 2026-01-11 | 2026-01-13 | 2
| CONTROL POINT 2 (CP2) |  | 2026-01-19 | 2026-01-21 | 3
| CONTROL POINT 2 (CP2) |  | 2026-01-25 | 2026-04-05 | 50
| CONTROL POINT 2 (CP2) |  | 2026-04-11 | 2026-04-12 | 1
| CONTROL POINT 2 (CP2) |  | 2026-04-18 | 2026-04-19 | 1
| CONTROL POINT 2 (CP2) |  | 2026-04-25 | 2026-04-26 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-01 | 2026-05-02 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-08 | 2026-05-09 | 1
| CONTROL POINT 2 (CP2) |  | 2026-05-29 | 2026-05-30 | 1
| CONTROL POINT 2 (CP2) |  | 2026-06-06 | 2026-06-07 | 1
255 | Wall void closure checklist sign off |  | 2025-12-07 | 2025-12-11 | 4
255 | Wall void closure checklist sign off |  | 2025-12-13 | 2025-12-16 | 2
255 | Wall void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
255 | Wall void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
255 | Wall void closure checklist sign off |  | 2026-01-05 | 2026-01-07 | 3
255 | Wall void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
255 | Wall void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
255 | Wall void closure checklist sign off |  | 2026-01-25 | 2026-04-01 | 48
255 | Wall void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
255 | Wall void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
255 | Wall void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
255 | Wall void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
255 | Wall void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
255 | Wall void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
255 | Wall void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
255 | Wall void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
256 | 2nd fix Partitions - insulation and board |  | 2025-12-07 | 2025-12-11 | 4
256 | 2nd fix Partitions - insulation and board |  | 2025-12-13 | 2025-12-16 | 2
256 | 2nd fix Partitions - insulation and board |  | 2025-12-19 | 2025-12-24 | 4
256 | 2nd fix Partitions - insulation and board |  | 2025-12-26 | 2025-12-29 | 2
256 | 2nd fix Partitions - insulation and board |  | 2026-01-05 | 2026-01-07 | 3
256 | 2nd fix Partitions - insulation and board |  | 2026-01-11 | 2026-01-13 | 2
256 | 2nd fix Partitions - insulation and board |  | 2026-01-19 | 2026-01-21 | 3
256 | 2nd fix Partitions - insulation and board |  | 2026-01-25 | 2026-04-01 | 48
256 | 2nd fix Partitions - insulation and board |  | 2026-04-04 | 2026-04-05 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-04-11 | 2026-04-12 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-04-18 | 2026-04-19 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-04-25 | 2026-04-26 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-05-01 | 2026-05-02 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-05-08 | 2026-05-09 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-05-29 | 2026-05-30 | 1
256 | 2nd fix Partitions - insulation and board |  | 2026-06-06 | 2026-06-07 | 1
257 | Install Vents/ducts |  | 2025-12-07 | 2025-12-11 | 4
257 | Install Vents/ducts |  | 2025-12-13 | 2025-12-16 | 2
257 | Install Vents/ducts |  | 2025-12-19 | 2025-12-24 | 4
257 | Install Vents/ducts |  | 2025-12-26 | 2025-12-29 | 2
257 | Install Vents/ducts |  | 2026-01-05 | 2026-01-07 | 3
257 | Install Vents/ducts |  | 2026-01-11 | 2026-01-21 | 8
257 | Install Vents/ducts |  | 2026-01-25 | 2026-04-01 | 48
257 | Install Vents/ducts |  | 2026-04-04 | 2026-04-05 | 1
257 | Install Vents/ducts |  | 2026-04-11 | 2026-04-12 | 1
257 | Install Vents/ducts |  | 2026-04-18 | 2026-04-19 | 1
257 | Install Vents/ducts |  | 2026-04-25 | 2026-04-26 | 1
257 | Install Vents/ducts |  | 2026-05-01 | 2026-05-02 | 1
257 | Install Vents/ducts |  | 2026-05-08 | 2026-05-09 | 1
257 | Install Vents/ducts |  | 2026-05-29 | 2026-05-30 | 1
257 | Install Vents/ducts |  | 2026-06-06 | 2026-06-07 | 1
258 | CONTROL POINT 3 (CP3) |  | 2025-12-07 | 2025-12-11 | 4
258 | CONTROL POINT 3 (CP3) |  | 2025-12-13 | 2025-12-16 | 2
258 | CONTROL POINT 3 (CP3) |  | 2025-12-19 | 2025-12-24 | 4
258 | CONTROL POINT 3 (CP3) |  | 2025-12-26 | 2025-12-29 | 2
258 | CONTROL POINT 3 (CP3) |  | 2026-01-05 | 2026-01-07 | 3
258 | CONTROL POINT 3 (CP3) |  | 2026-01-11 | 2026-01-13 | 2
258 | CONTROL POINT 3 (CP3) |  | 2026-01-19 | 2026-04-01 | 53
258 | CONTROL POINT 3 (CP3) |  | 2026-04-04 | 2026-04-05 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-04-11 | 2026-04-12 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-04-18 | 2026-04-19 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-04-25 | 2026-04-26 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-05-01 | 2026-05-02 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-05-08 | 2026-05-09 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-05-29 | 2026-05-30 | 1
258 | CONTROL POINT 3 (CP3) |  | 2026-06-06 | 2026-06-07 | 1
259 | Ceiling void closure checklist sign off |  | 2025-12-07 | 2025-12-11 | 4
259 | Ceiling void closure checklist sign off |  | 2025-12-13 | 2025-12-16 | 2
259 | Ceiling void closure checklist sign off |  | 2025-12-19 | 2025-12-24 | 4
259 | Ceiling void closure checklist sign off |  | 2025-12-26 | 2025-12-29 | 2
259 | Ceiling void closure checklist sign off |  | 2026-01-05 | 2026-01-07 | 3
259 | Ceiling void closure checklist sign off |  | 2026-01-11 | 2026-01-13 | 2
259 | Ceiling void closure checklist sign off |  | 2026-01-19 | 2026-01-21 | 3
259 | Ceiling void closure checklist sign off |  | 2026-01-25 | 2026-04-01 | 48
259 | Ceiling void closure checklist sign off |  | 2026-04-04 | 2026-04-05 | 1
259 | Ceiling void closure checklist sign off |  | 2026-04-11 | 2026-04-12 | 1
259 | Ceiling void closure checklist sign off |  | 2026-04-18 | 2026-04-19 | 1
259 | Ceiling void closure checklist sign off |  | 2026-04-25 | 2026-04-26 | 1
259 | Ceiling void closure checklist sign off |  | 2026-05-01 | 2026-05-02 | 1
259 | Ceiling void closure checklist sign off |  | 2026-05-08 | 2026-05-09 | 1
259 | Ceiling void closure checklist sign off |  | 2026-05-29 | 2026-05-30 | 1
259 | Ceiling void closure checklist sign off |  | 2026-06-06 | 2026-06-07 | 1
260 | Ceilings metal only |  | 2025-12-07 | 2025-12-11 | 4
260 | Ceilings metal only |  | 2025-12-13 | 2025-12-16 | 2
260 | Ceilings metal only |  | 2025-12-19 | 2025-12-24 | 4
260 | Ceilings metal only |  | 2025-12-26 | 2025-12-29 | 2
260 | Ceilings metal only |  | 2026-01-05 | 2026-01-07 | 3
260 | Ceilings metal only |  | 2026-01-11 | 2026-01-13 | 2
260 | Ceilings metal only |  | 2026-01-19 | 2026-01-21 | 3
260 | Ceilings metal only |  | 2026-01-25 | 2026-04-01 | 48
260 | Ceilings metal only |  | 2026-04-04 | 2026-04-05 | 1
260 | Ceilings metal only |  | 2026-04-11 | 2026-04-12 | 1
260 | Ceilings metal only |  | 2026-04-18 | 2026-04-19 | 1
260 | Ceilings metal only |  | 2026-04-25 | 2026-04-26 | 1
260 | Ceilings metal only |  | 2026-05-01 | 2026-05-02 | 1
260 | Ceilings metal only |  | 2026-05-08 | 2026-05-09 | 1
260 | Ceilings metal only |  | 2026-06-06 | 2026-06-07 | 1
261 | Sprinkler 1st fix & test |  | 2025-12-07 | 2025-12-11 | 4
261 | Sprinkler 1st fix & test |  | 2025-12-13 | 2025-12-16 | 2
261 | Sprinkler 1st fix & test |  | 2025-12-19 | 2025-12-24 | 4
261 | Sprinkler 1st fix & test |  | 2025-12-26 | 2025-12-29 | 2
261 | Sprinkler 1st fix & test |  | 2026-01-05 | 2026-01-07 | 3
261 | Sprinkler 1st fix & test |  | 2026-01-11 | 2026-01-13 | 2
261 | Sprinkler 1st fix & test |  | 2026-01-19 | 2026-01-21 | 3
261 | Sprinkler 1st fix & test |  | 2026-01-25 | 2026-04-01 | 48
261 | Sprinkler 1st fix & test |  | 2026-04-04 | 2026-04-05 | 1
261 | Sprinkler 1st fix & test |  | 2026-04-11 | 2026-04-12 | 1
261 | Sprinkler 1st fix & test |  | 2026-04-18 | 2026-04-19 | 1
261 | Sprinkler 1st fix & test |  | 2026-04-25 | 2026-04-26 | 1
261 | Sprinkler 1st fix & test |  | 2026-05-01 | 2026-05-02 | 1
261 | Sprinkler 1st fix & test |  | 2026-05-08 | 2026-05-09 | 1
261 | Sprinkler 1st fix & test |  | 2026-06-06 | 2026-06-07 | 1
262 | Ceilings - board (cut holes for lights) |  | 2025-12-07 | 2025-12-11 | 4
262 | Ceilings - board (cut holes for lights) |  | 2025-12-13 | 2025-12-16 | 2
262 | Ceilings - board (cut holes for lights) |  | 2025-12-19 | 2025-12-24 | 4
262 | Ceilings - board (cut holes for lights) |  | 2025-12-26 | 2025-12-29 | 2
262 | Ceilings - board (cut holes for lights) |  | 2026-01-05 | 2026-01-07 | 3
262 | Ceilings - board (cut holes for lights) |  | 2026-01-11 | 2026-01-13 | 2
262 | Ceilings - board (cut holes for lights) |  | 2026-01-19 | 2026-01-21 | 3
262 | Ceilings - board (cut holes for lights) |  | 2026-01-25 | 2026-04-01 | 48
262 | Ceilings - board (cut holes for lights) |  | 2026-04-04 | 2026-04-05 | 1
262 | Ceilings - board (cut holes for lights) |  | 2026-04-11 | 2026-04-12 | 1
262 | Ceilings - board (cut holes for lights) |  | 2026-04-18 | 2026-04-19 | 1
262 | Ceilings - board (cut holes for lights) |  | 2026-04-25 | 2026-04-26 | 1
262 | Ceilings - board (cut holes for lights) |  | 2026-05-01 | 2026-05-02 | 1
262 | Ceilings - board (cut holes for lights) |  | 2026-05-08 | 2026-05-09 | 1
262 | Ceilings - board (cut holes for lights) |  | 2026-06-06 | 2026-06-07 | 1
263 | Plaster spray |  | 2025-12-07 | 2025-12-11 | 4
263 | Plaster spray |  | 2025-12-13 | 2025-12-16 | 2
263 | Plaster spray |  | 2025-12-19 | 2025-12-24 | 4
263 | Plaster spray |  | 2025-12-26 | 2025-12-29 | 2
263 | Plaster spray |  | 2026-01-05 | 2026-01-07 | 3
263 | Plaster spray |  | 2026-01-11 | 2026-01-13 | 2
263 | Plaster spray |  | 2026-01-19 | 2026-01-21 | 3
263 | Plaster spray |  | 2026-01-25 | 2026-04-01 | 48
263 | Plaster spray |  | 2026-04-04 | 2026-04-05 | 1
263 | Plaster spray |  | 2026-04-11 | 2026-04-12 | 1
263 | Plaster spray |  | 2026-04-18 | 2026-04-19 | 1
263 | Plaster spray |  | 2026-04-25 | 2026-04-26 | 1
263 | Plaster spray |  | 2026-05-01 | 2026-05-02 | 1
263 | Plaster spray |  | 2026-05-08 | 2026-05-09 | 1
263 | Plaster spray |  | 2026-06-06 | 2026-06-07 | 1
264 | Levveling screed /smoothing compound |  | 2025-12-07 | 2025-12-11 | 4
264 | Levveling screed /smoothing compound |  | 2025-12-13 | 2025-12-16 | 2
264 | Levveling screed /smoothing compound |  | 2025-12-19 | 2025-12-24 | 4
264 | Levveling screed /smoothing compound |  | 2025-12-26 | 2025-12-29 | 2
264 | Levveling screed /smoothing compound |  | 2026-01-05 | 2026-01-07 | 3
264 | Levveling screed /smoothing compound |  | 2026-01-11 | 2026-01-13 | 2
264 | Levveling screed /smoothing compound |  | 2026-01-19 | 2026-01-21 | 3
264 | Levveling screed /smoothing compound |  | 2026-01-25 | 2026-04-01 | 48
264 | Levveling screed /smoothing compound |  | 2026-04-04 | 2026-04-05 | 1
264 | Levveling screed /smoothing compound |  | 2026-04-11 | 2026-04-12 | 1
264 | Levveling screed /smoothing compound |  | 2026-04-18 | 2026-04-19 | 1
264 | Levveling screed /smoothing compound |  | 2026-04-25 | 2026-04-26 | 1
264 | Levveling screed /smoothing compound |  | 2026-05-01 | 2026-05-02 | 1
264 | Levveling screed /smoothing compound |  | 2026-05-08 | 2026-05-09 | 1
264 | Levveling screed /smoothing compound |  | 2026-06-06 | 2026-06-07 | 1
265 | Drying out |  | 2025-12-07 | 2025-12-11 | 4
265 | Drying out |  | 2025-12-13 | 2025-12-16 | 2
265 | Drying out |  | 2025-12-19 | 2025-12-24 | 4
265 | Drying out |  | 2025-12-26 | 2025-12-29 | 2
265 | Drying out |  | 2026-01-05 | 2026-01-07 | 3
265 | Drying out |  | 2026-01-11 | 2026-01-13 | 2
265 | Drying out |  | 2026-01-19 | 2026-01-21 | 3
265 | Drying out |  | 2026-01-25 | 2026-04-01 | 48
265 | Drying out |  | 2026-04-04 | 2026-04-05 | 1
265 | Drying out |  | 2026-04-11 | 2026-04-12 | 1
265 | Drying out |  | 2026-04-18 | 2026-04-19 | 1
265 | Drying out |  | 2026-04-25 | 2026-04-26 | 1
265 | Drying out |  | 2026-05-01 | 2026-05-02 | 1
265 | Drying out |  | 2026-05-08 | 2026-05-09 | 1
265 | Drying out |  | 2026-06-06 | 2026-06-07 | 1
266 | Mist coat |  | 2025-12-07 | 2025-12-11 | 4
266 | Mist coat |  | 2025-12-13 | 2025-12-16 | 2
266 | Mist coat |  | 2025-12-19 | 2025-12-24 | 4
266 | Mist coat |  | 2025-12-26 | 2025-12-29 | 2
266 | Mist coat |  | 2026-01-05 | 2026-01-07 | 3
266 | Mist coat |  | 2026-01-11 | 2026-01-13 | 2
266 | Mist coat |  | 2026-01-19 | 2026-01-21 | 3
266 | Mist coat |  | 2026-01-25 | 2026-04-01 | 48
266 | Mist coat |  | 2026-04-04 | 2026-04-05 | 1
266 | Mist coat |  | 2026-04-11 | 2026-04-12 | 1
266 | Mist coat |  | 2026-04-18 | 2026-04-19 | 1
266 | Mist coat |  | 2026-04-25 | 2026-04-26 | 1
266 | Mist coat |  | 2026-05-01 | 2026-05-02 | 1
266 | Mist coat |  | 2026-05-08 | 2026-05-09 | 1
266 | Mist coat |  | 2026-06-06 | 2026-06-07 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2025-12-07 | 2025-12-11 | 4
267 | Kitchen 1st fix,units tops & appliances |  | 2025-12-13 | 2025-12-16 | 2
267 | Kitchen 1st fix,units tops & appliances |  | 2025-12-19 | 2025-12-24 | 4
267 | Kitchen 1st fix,units tops & appliances |  | 2025-12-26 | 2025-12-29 | 2
267 | Kitchen 1st fix,units tops & appliances |  | 2026-01-05 | 2026-01-07 | 3
267 | Kitchen 1st fix,units tops & appliances |  | 2026-01-11 | 2026-01-13 | 2
267 | Kitchen 1st fix,units tops & appliances |  | 2026-01-19 | 2026-01-21 | 3
267 | Kitchen 1st fix,units tops & appliances |  | 2026-01-25 | 2026-04-01 | 48
267 | Kitchen 1st fix,units tops & appliances |  | 2026-04-04 | 2026-04-05 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2026-04-11 | 2026-04-12 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2026-04-18 | 2026-04-19 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2026-04-25 | 2026-04-26 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2026-05-01 | 2026-05-02 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2026-05-08 | 2026-05-09 | 1
267 | Kitchen 1st fix,units tops & appliances |  | 2026-06-06 | 2026-06-07 | 1
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-07 | 2025-12-11 | 4
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-13 | 2025-12-16 | 2
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-19 | 2025-12-24 | 4
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2025-12-26 | 2025-12-29 | 2
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-05 | 2026-01-07 | 3
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-11 | 2026-01-13 | 2
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-19 | 2026-01-21 | 3
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-01-25 | 2026-04-01 | 48
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-04 | 2026-04-05 | 1
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-11 | 2026-04-12 | 1
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-18 | 2026-04-19 | 1
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-04-25 | 2026-04-26 | 1
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-01 | 2026-05-02 | 1
268 | Joinery 1st fix -doors, frames ,skirtings,archs vanity framing & plinths . |  | 2026-05-08 | 2026-05-09 | 1
269 | Floor and wall tiling JD tiling |  | 2025-12-07 | 2025-12-11 | 4
269 | Floor and wall tiling JD tiling |  | 2025-12-13 | 2025-12-16 | 2
269 | Floor and wall tiling JD tiling |  | 2025-12-19 | 2025-12-24 | 4
269 | Floor and wall tiling JD tiling |  | 2025-12-26 | 2025-12-29 | 2
269 | Floor and wall tiling JD tiling |  | 2026-01-05 | 2026-01-07 | 3
269 | Floor and wall tiling JD tiling |  | 2026-01-11 | 2026-01-13 | 2
269 | Floor and wall tiling JD tiling |  | 2026-01-19 | 2026-01-21 | 3
269 | Floor and wall tiling JD tiling |  | 2026-01-25 | 2026-04-01 | 48
269 | Floor and wall tiling JD tiling |  | 2026-04-04 | 2026-04-05 | 1
269 | Floor and wall tiling JD tiling |  | 2026-04-11 | 2026-04-12 | 1
269 | Floor and wall tiling JD tiling |  | 2026-04-18 | 2026-04-19 | 1
269 | Floor and wall tiling JD tiling |  | 2026-04-25 | 2026-04-26 | 1
269 | Floor and wall tiling JD tiling |  | 2026-05-01 | 2026-05-02 | 1
269 | Floor and wall tiling JD tiling |  | 2026-05-08 | 2026-05-09 | 1
270 | Control point 4 CP 4 |  | 2025-12-07 | 2025-12-11 | 4
270 | Control point 4 CP 4 |  | 2025-12-13 | 2025-12-16 | 2
270 | Control point 4 CP 4 |  | 2025-12-19 | 2025-12-24 | 4
270 | Control point 4 CP 4 |  | 2025-12-26 | 2025-12-29 | 2
270 | Control point 4 CP 4 |  | 2026-01-05 | 2026-01-07 | 3
270 | Control point 4 CP 4 |  | 2026-01-11 | 2026-01-13 | 2
270 | Control point 4 CP 4 |  | 2026-01-19 | 2026-01-21 | 3
270 | Control point 4 CP 4 |  | 2026-01-25 | 2026-04-01 | 48
270 | Control point 4 CP 4 |  | 2026-04-04 | 2026-04-05 | 1
270 | Control point 4 CP 4 |  | 2026-04-11 | 2026-04-12 | 1
270 | Control point 4 CP 4 |  | 2026-04-18 | 2026-04-19 | 1
270 | Control point 4 CP 4 |  | 2026-04-25 | 2026-04-26 | 1
270 | Control point 4 CP 4 |  | 2026-05-01 | 2026-05-02 | 1
270 | Control point 4 CP 4 |  | 2026-05-08 | 2026-05-09 | 1
271 | service cupbaord -plywood flooring |  | 2025-12-07 | 2025-12-11 | 4
271 | service cupbaord -plywood flooring |  | 2025-12-13 | 2025-12-16 | 2
271 | service cupbaord -plywood flooring |  | 2025-12-19 | 2025-12-24 | 4
271 | service cupbaord -plywood flooring |  | 2025-12-26 | 2025-12-29 | 2
271 | service cupbaord -plywood flooring |  | 2026-01-05 | 2026-01-07 | 3
271 | service cupbaord -plywood flooring |  | 2026-01-11 | 2026-01-13 | 2
271 | service cupbaord -plywood flooring |  | 2026-01-19 | 2026-01-21 | 3
271 | service cupbaord -plywood flooring |  | 2026-01-25 | 2026-04-01 | 48
271 | service cupbaord -plywood flooring |  | 2026-04-04 | 2026-04-05 | 1
271 | service cupbaord -plywood flooring |  | 2026-04-11 | 2026-04-12 | 1
271 | service cupbaord -plywood flooring |  | 2026-04-18 | 2026-04-19 | 1
271 | service cupbaord -plywood flooring |  | 2026-04-25 | 2026-04-26 | 1
271 | service cupbaord -plywood flooring |  | 2026-05-01 | 2026-05-02 | 1
271 | service cupbaord -plywood flooring |  | 2026-05-08 | 2026-05-09 | 1
272 | service cupboard decoration |  | 2025-12-07 | 2025-12-11 | 4
272 | service cupboard decoration |  | 2025-12-13 | 2025-12-16 | 2
272 | service cupboard decoration |  | 2025-12-19 | 2025-12-24 | 4
272 | service cupboard decoration |  | 2025-12-26 | 2025-12-29 | 2
272 | service cupboard decoration |  | 2026-01-05 | 2026-01-07 | 3
272 | service cupboard decoration |  | 2026-01-11 | 2026-01-13 | 2
272 | service cupboard decoration |  | 2026-01-19 | 2026-01-21 | 3
272 | service cupboard decoration |  | 2026-01-25 | 2026-04-01 | 48
272 | service cupboard decoration |  | 2026-04-04 | 2026-04-05 | 1
272 | service cupboard decoration |  | 2026-04-11 | 2026-04-12 | 1
272 | service cupboard decoration |  | 2026-04-18 | 2026-04-19 | 1
272 | service cupboard decoration |  | 2026-04-25 | 2026-04-26 | 1
272 | service cupboard decoration |  | 2026-05-01 | 2026-05-02 | 1
272 | service cupboard decoration |  | 2026-05-08 | 2026-05-09 | 1
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2025-12-07 | 2026-04-01 | 83
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-04 | 2026-04-05 | 1
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-11 | 2026-04-12 | 1
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-18 | 2026-04-19 | 1
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-04-25 | 2026-04-26 | 1
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-01 | 2026-05-02 | 1
273 | service cupboard cylinder MVHR pipework installation & ducts |  | 2026-05-08 | 2026-05-09 | 1
| Amtico flooring /Bathrooms |  | 2025-12-07 | 2026-04-01 | 83
| Amtico flooring /Bathrooms |  | 2026-04-04 | 2026-04-05 | 1
| Amtico flooring /Bathrooms |  | 2026-04-11 | 2026-04-12 | 1
| Amtico flooring /Bathrooms |  | 2026-04-18 | 2026-04-19 | 1
| Amtico flooring /Bathrooms |  | 2026-04-25 | 2026-04-26 | 1
| Amtico flooring /Bathrooms |  | 2026-05-01 | 2026-05-02 | 1
| Amtico flooring /Bathrooms |  | 2026-05-08 | 2026-05-09 | 1
274 | Plumbing second fix sanitaryware & pressure testing |  | 2025-12-07 | 2026-04-01 | 83
274 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-04 | 2026-04-05 | 1
274 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-11 | 2026-04-12 | 1
274 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-18 | 2026-04-19 | 1
274 | Plumbing second fix sanitaryware & pressure testing |  | 2026-04-25 | 2026-04-26 | 1
274 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-01 | 2026-05-02 | 1
274 | Plumbing second fix sanitaryware & pressure testing |  | 2026-05-08 | 2026-05-09 | 1
275 | Electrical 2nd fix & live testing |  | 2025-12-07 | 2026-04-05 | 85
275 | Electrical 2nd fix & live testing |  | 2026-04-11 | 2026-04-12 | 1
275 | Electrical 2nd fix & live testing |  | 2026-04-18 | 2026-04-19 | 1
275 | Electrical 2nd fix & live testing |  | 2026-04-25 | 2026-04-26 | 1
275 | Electrical 2nd fix & live testing |  | 2026-05-01 | 2026-05-02 | 1
275 | Electrical 2nd fix & live testing |  | 2026-05-08 | 2026-05-09 | 1
276 | Builders clean |  | 2025-12-07 | 2026-04-05 | 85
276 | Builders clean |  | 2026-04-11 | 2026-04-19 | 5
276 | Builders clean |  | 2026-04-25 | 2026-04-26 | 1
276 | Builders clean |  | 2026-05-01 | 2026-05-02 | 1
276 | Builders clean |  | 2026-05-08 | 2026-05-09 | 1
276 | Builders clean |  | 2026-05-27 | 2026-06-01 | 4
277 | Pre -dec -snagging |  | 2025-12-07 | 2026-04-05 | 85
277 | Pre -dec -snagging |  | 2026-04-11 | 2026-04-19 | 5
277 | Pre -dec -snagging |  | 2026-04-25 | 2026-04-26 | 1
277 | Pre -dec -snagging |  | 2026-05-01 | 2026-05-02 | 1
277 | Pre -dec -snagging |  | 2026-05-08 | 2026-05-09 | 1
277 | Pre -dec -snagging |  | 2026-05-27 | 2026-06-01 | 4
278 | Decoration |  | 2025-12-07 | 2026-04-05 | 85
278 | Decoration |  | 2026-04-11 | 2026-04-19 | 5
278 | Decoration |  | 2026-04-25 | 2026-04-26 | 1
278 | Decoration |  | 2026-05-01 | 2026-05-02 | 1
278 | Decoration |  | 2026-05-08 | 2026-05-09 | 1
278 | Decoration |  | 2026-05-27 | 2026-06-01 | 4
279 | Amtico flooring /Carpets |  | 2025-12-07 | 2026-04-01 | 83
279 | Amtico flooring /Carpets |  | 2026-04-04 | 2026-04-05 | 1
279 | Amtico flooring /Carpets |  | 2026-04-11 | 2026-06-01 | 36
280 | De snag all trades |  | 2025-12-07 | 2026-04-01 | 83
280 | De snag all trades |  | 2026-04-04 | 2026-04-05 | 1
280 | De snag all trades |  | 2026-04-11 | 2026-06-01 | 36
281 | Sparkle clean |  | 2025-12-07 | 2026-04-01 | 83
281 | Sparkle clean |  | 2026-04-04 | 2026-04-05 | 1
281 | Sparkle clean |  | 2026-04-11 | 2026-06-01 | 36
282 | Mastic |  | 2025-12-07 | 2026-04-01 | 83
282 | Mastic |  | 2026-04-04 | 2026-04-05 | 1
282 | Mastic |  | 2026-04-11 | 2026-06-01 | 36
283 | Handover to client |  | 2025-12-07 | 2026-04-01 | 83
283 | Handover to client |  | 2026-04-04 | 2026-04-05 | 1
283 | Handover to client |  | 2026-04-11 | 2026-06-01 | 36
| 284 |  | 2025-12-07 | 2026-04-01 | 83
| 284 |  | 2026-04-04 | 2026-04-05 | 1
| 284 |  | 2026-04-11 | 2026-06-01 | 36
| 285 |  | 2025-12-07 | 2026-04-01 | 83
| 285 |  | 2026-04-04 | 2026-04-05 | 1
| 285 |  | 2026-04-11 | 2026-06-01 | 36
| 286 |  | 2025-12-07 | 2026-04-01 | 83
| 286 |  | 2026-04-04 | 2026-04-05 | 1
| 286 |  | 2026-04-11 | 2026-06-01 | 36
| 287 |  | 2025-12-07 | 2026-04-01 | 83
| 287 |  | 2026-04-04 | 2026-04-05 | 1
| 287 |  | 2026-04-11 | 2026-06-01 | 36
| 288 |  | 2025-12-07 | 2026-04-01 | 83
| 288 |  | 2026-04-04 | 2026-04-05 | 1
| 288 |  | 2026-04-11 | 2026-06-01 | 36
| 289 |  | 2025-12-07 | 2026-04-01 | 83
| 289 |  | 2026-04-04 | 2026-04-05 | 1
| 289 |  | 2026-04-11 | 2026-06-01 | 36
| 290 |  | 2025-12-07 | 2026-04-01 | 83
| 290 |  | 2026-04-04 | 2026-04-05 | 1
| 290 |  | 2026-04-11 | 2026-06-01 | 36
| 291 |  | 2025-12-07 | 2026-04-01 | 83
| 291 |  | 2026-04-04 | 2026-04-05 | 1
| 291 |  | 2026-04-11 | 2026-06-01 | 36
| 292 |  | 2025-12-07 | 2026-04-01 | 83
| 292 |  | 2026-04-04 | 2026-04-05 | 1
| 292 |  | 2026-04-11 | 2026-06-01 | 36
| 293 |  | 2025-12-07 | 2026-04-01 | 83
| 293 |  | 2026-04-04 | 2026-04-05 | 1
| 293 |  | 2026-04-11 | 2026-06-01 | 36
| 294 |  | 2025-12-07 | 2026-04-01 | 83
| 294 |  | 2026-04-04 | 2026-04-05 | 1
| 294 |  | 2026-04-11 | 2026-06-01 | 36
| 295 |  | 2025-12-07 | 2026-04-01 | 83
| 295 |  | 2026-04-04 | 2026-04-05 | 1
| 295 |  | 2026-04-11 | 2026-06-01 | 36
| 296 |  | 2025-12-07 | 2026-04-01 | 83
| 296 |  | 2026-04-04 | 2026-04-05 | 1
| 296 |  | 2026-04-11 | 2026-06-01 | 36
| 297 |  | 2025-12-07 | 2026-04-01 | 83
| 297 |  | 2026-04-04 | 2026-04-05 | 1
| 297 |  | 2026-04-11 | 2026-06-01 | 36
| 298 |  | 2025-12-07 | 2026-04-01 | 83
| 298 |  | 2026-04-04 | 2026-04-05 | 1
| 298 |  | 2026-04-11 | 2026-06-01 | 36
| 299 |  | 2025-12-07 | 2026-04-01 | 83
| 299 |  | 2026-04-04 | 2026-04-05 | 1
| 299 |  | 2026-04-11 | 2026-06-01 | 36
| 300 |  | 2025-12-07 | 2026-04-01 | 83
| 300 |  | 2026-04-04 | 2026-04-05 | 1
| 300 |  | 2026-04-11 | 2026-06-01 | 36
| 301 |  | 2025-12-07 | 2026-04-01 | 83
| 301 |  | 2026-04-04 | 2026-04-05 | 1
| 301 |  | 2026-04-11 | 2026-06-01 | 36
| 302 |  | 2025-12-07 | 2026-04-01 | 83
| 302 |  | 2026-04-04 | 2026-04-05 | 1
| 302 |  | 2026-04-11 | 2026-06-01 | 36
| 303 |  | 2025-12-07 | 2026-04-01 | 83
| 303 |  | 2026-04-04 | 2026-04-05 | 1
| 303 |  | 2026-04-11 | 2026-06-01 | 36
| 304 |  | 2025-12-07 | 2026-04-01 | 83
| 304 |  | 2026-04-04 | 2026-04-05 | 1
| 304 |  | 2026-04-11 | 2026-06-01 | 36
| 305 |  | 2025-12-07 | 2026-04-01 | 83
| 305 |  | 2026-04-04 | 2026-04-05 | 1
| 305 |  | 2026-04-11 | 2026-06-01 | 36