## TaskList
Section | Activity | Contractor | Ops | Duration (days) | Start (dd/mm/yyyy) | Finish (dd/mm/yyyy) | Zone | DepType (FS/SS) | Predecessor Task | Lag (days)
e.g. A 1 01 | Short clear task name | Use names from Admin → Contractors | int | working days (Mon–Fri) | optional | optional | Bathroom/Core/Kitchen… | FS or SS | Task code or ID | ± days
A 1 01 | BWH to structural walls | Panacea | 2 | 3 |  |  | Core
A 1 01 | SVP/RWP install | GPL | 2 | 5 |  |  | Wetrooms | FS | BWH to structural walls
A 1 01 | Fire stop to SVP/RWP | TECL | 2 | 5 |  |  | Wetrooms | SS | SVP/RWP install